## Version Control
AEMO 5MS Functional Deployment Matrix - Version 1.0 Version Control
Version | Date | Comments
1.0 | 13th July, 2020 | AEMO distribution of 'AEMO 5MS Functional Deployment Matrix' to RWG, SWG and ITWG
1.1 | 06th August, 2020 | Added R30 into the staging 30 min tab
1.2 | 10th September, | Updated Preprod dates for Settlement and addtion of "Transition" tab
1.3 | 10th November,2020 | Updated Martix ID R35 and R24
1.4 | 3rd February,2021 | Updated release dates for retail and Settlements delay

## Introduction
AEMO 5MS Functional Deployment Matrix, Version 1.0 Introduction
Ref. # | Details
1 | The 'AEMO 5MS Functional Deployment Matrix' provides NEM Industry Participants with a detailed view of the AEMO 5MS programme delivery of 5MS and GS AEMO functions with consideration to: - AEMO environments i.e. 5MS Staging and PreProduction - AEMO Workstreams i.e. Retail, Dispach and Settlements - NEM Settlement calculations i.e. 30 minute, 5 minute and Global Settlements
2 | This matrix maybe referenced by NEM Industry Particpants to determine when AEMO specific 5MS and GS functional testing can be initiated.
3 | The AEMO 5MS Programme functions have been logically grouped by AEMO Environment and NEM Settlement calculation: - 'Staging_30 min' - All functionality to be delivered into the 5MS Staging environment for functions related to 30-Minute NEM Settlements - 'Staging_5min': All functionality to be delivered into the 5MS Staging environment for functions related to 5-Minute NEM Settlements (5MS) - 'Staging_GS' : All functionality to be delivered into the 5MS Staging environment for functions related to Global Settlements (GS) - 'PreProduction': All functionality to be delivered into the AEMO PreProduction environment for functions related to 30-Minute NEM Settlements, 5-Minute NEM Settlements and Global Settlements
4 | This document is intended to be a living document updated in collaboration with NEM Industry Participants. Related questions and clarifications will be registered within this document and distributed for NEM Industry Participant reference.

## Staging_30 min
AEMO 5MS Functional Deployment Matrix, Version 1.4
Environment: 5MS Staging Environment Settlement: 30 minute Date of MSATS data refresh: 30th July, 2020 AEMO Work Streams: Retail, Dispatch, Settlements
AEMO Functional Matrix ID | AEMO WorkStream | AEMO 5MS Programme: Function | Available for Participant testing | Functional Testing Considerations
R1 | Retail | MDFF NEM12 at any data interval via FTP | 2019-12-01 | Once implemented, no future functional change. Valid for 5, 15 & 30 minute intervals.
R2 | Retail | B2M MTRD MDFF NEM12 at any data interval via MSATS Browser 'B2B Browser > Upload File' pg | 2019-12-01 | Once implemented, no future functional change. Valid for 5, 15 & 30 minute intervals.
R3 | Retail | MDFF NEM13 via FTP | 2020-06-15 | None.
R4 | Retail | B2M MTRD MDFF NEM13 via MSATS Browser 'B2B Browser > Upload File' pg | 2020-06-15 | None.
R5 | Retail | MDMT MDMF Interval and Basic meter data files | 2020-06-15 | None.
R6 | Retail | API Push Functionality for B2M MTRD and MDMT, CATS, NMID | 2020-06-15 | AEMO will update a NEM Participants Push/Pull API functionality on request. This will be available until 31st August 2020 when Participants can directly update Push/Pull functionality via MSATS Browser
R7 | Retail | MSATS Browser 'Metering Data > Data Search' pg | 2020-06-15 | Once implemented, no future functional change. Valid for 5, 15 & 30 minute intervals.
R8 | Retail | MSATS Browser 'B2B Browser > Transforms and Protocols' pg | 2020-08-31 | None.
R9 | Retail | aseXML Schema r39 available | 2020-06-15 | AEMO will update a NEM Participants aseXML schema functionality on request. This will be validate until the 31st August 2020 when Participants can directly update aseXML schema via MSATS Browser.
R10 | Retail | MSATS Browser 'Participants > Participant Schema' pg | 2020-08-31 | None.
R11 | Retail | MSATS Browser 'B2B Browser > B2B Hub Queue' pg | 2020-08-31 | None.
R12 | Retail | MSATS Browser 'Reports and Alerts > Queue Monitoring' pg | 2020-08-31 | None.
R13 | Retail | Retirement of RM reports: RM7, RM8, RM10, RM12, RM14, RM15, RM18, RM19, SDD and SDR | 2020-08-31 | The retired RM reports will not be visible in the MSATS report menus. AEMO will generate a rejection for a retired RM report where requested (API/FTP).
R14 | Retail | CATS report changes : C1, C4, C7, C10, C11 | 2020-08-31 | None.
R15 | Retail | API Pull Functionality for B2M MTRD and MDMT, CATS, NMID | 2020-08-31 | None.
R16 | Retail | CATS CR changes to support new NMI classification codes | 2020-08-31 | None.
R17 | Retail | New Standing Data - Meter Installation Type Codes (MITC), Datastream Type 'N' | 2020-08-31 | There will be no new MITC's in MSATS until LNSP's create them. DataStreamType = 'N' values should be used upon creation of new CNDS records.
R18 | Retail | MSATS NMI discovery Display of TNI2 and Vic TUoS | 2020-08-31 | None.
R19 | Retail | MSATS NMI Master/Summary display of TNI2 and VIC TUoS | 2020-08-31 | None.
R20 | Retail | MSATS Browser 'Settlement Data' pg | 2020-08-31 | None.
R21 | Retail | New RM Report Requests: RM37, RM38, RM39 | 2020-08-31 | New RM reports will not be automatically pushed to Participants. Update to aseXML is required for the new RM Reports.
R22 | Retail | Historic Settlement Runs @ 30 minutes | 2020-08-31 | Participants will be able to verify existing NEM Settlement Runs.
R23 | Retail | Settlement Run @ 30 minutes | 2020-09-17 | AEMO will generate a new 30-minute NEM Settlement Run.
R25 | Retail | Existing Meter Data Reports: RM9, RM11, RM13, RM26 | 2020-08-31 | Existing and new meter data will be reported in the existing RM reports (reflecting the interval length received by AEMO).
R26 | Retail | Existing Settlements Reports @30-min: RM16, RM17, RM20, RM21, RM22, RM25 | 2020-08-31 | Regardless of the granularity of the interval length received by AEMO, the data will be represented in 30 minute intervals.
R29 | Retail | Access to MSATS Browser via Markets Portal | 2020-08-31 | None.
R30 | Retail | B2B Transaction (SORD, CUST, MTRD etc) exchange supported between Participants | 2020-08-31 | None.
S1 | Settlement | 30 and 5 minute reallocations Web UI | 2019-11-01 | None.
S2 | Settlement | Reallocation APIs | 2020-03-16 | AEMO will use manufactured data in the creation of NEM Settlement Invoices. Generation of NEM Settlement invoices will not use prices derived from the 5MS Staging Dispatch solution
S4 | Settlement | Settlements and billing @ 30-min | 2020-03-16 | AEMO will use manufactured data in the creation of NEM Settlement Invoices.
S5 | Settlement | Prelim, Final, and Revision Settlements | 2020-03-16 | AEMO will use manufactured data in the creation of NEM Settlement Invoices.
S6 | Settlement | Invoicing (Tax Invoice, RCTI, Adjustment Note, etc) | 2020-03-16 | AEMO will use manufactured data in the creation of NEM Settlement Invoices.
S7 | Settlement | Reconciliation reports (SR, SS, etc) | 2020-03-16 | AEMO will use manufactured data in the creation of NEM Settlement Invoices.
S8 | Settlement | NEM Reports | 2020-03-16 | AEMO will use manufactured data in the creation of NEM Settlement Invoices.
S9 | Settlement | Data Interchange | 2020-03-16 | None.
S10 | Settlement | Settlements Direct (Production version, no API’s) | 2020-03-16 | Production data copied for Prudential processing.
S11 | Settlement | Prudential and settlement estimation @ 30-min | 2020-05-15 | AEMO will use manufactured data in the creation of NEM Settlement Invoices.
S14 | Settlement | NEM Prudentials Dashboard

## Staging_5min
AEMO 5MS Functional Deployment Matrix, Version 1.4
Environment: 5MS Staging Environment Settlement: 5 minute Date of MSATS data refresh: 30th July, 2020 AEMO Work Streams: Retail, Dispatch, Settlements
AEMO Functional Matrix ID | AEMO WorkStream | AEMO 5MS Programme: Function | Available for Participant testing | Functional Testing Considerations
R1 | Retail | MDFF NEM12 at any data interval via FTP | 2019-12-01 | Once implemented, no future functional change. Valid for 5, 15 & 30 minute intervals.
R2 | Retail | B2M MTRD MDFF NEM12 at any data interval via MSATS Browser 'B2B Browser > Upload File' pg | 2019-12-01 | Once implemented, no future functional change. Valid for 5, 15 & 30 minute intervals.
R3 | Retail | MDFF NEM13 via FTP | 2020-06-15 | None.
R4 | Retail | B2M MTRD MDFF NEM13 via MSATS Browser 'B2B Browser > Upload File' pg | 2020-06-15 | None.
R5 | Retail | MDMT MDMF Interval and Basic meter data files | 2020-06-15 | None.
R6 | Retail | API Push Functionality for B2M MTRD and MDMT, CATS, NMID | 2020-06-15 | AEMO will update a NEM Participants Push/Pull API functionality on request. This will be available until 31st August 2020 when Participants can directly update Push/Pull functionality via MSATS Browser
R7 | Retail | MSATS Browser 'Metering Data > Data Search' pg | 2020-06-15 | Once implemented, no future functional change. Valid for 5, 15 & 30 minute intervals.
R8 | Retail | MSATS Browser 'B2B Browser > Transforms and Protocols' pg | 2020-08-31 | None.
R9 | Retail | aseXML Schema r39 available | 2020-06-15 | AEMO will update a NEM Participants aseXML schema functionality on request. This will be validate until the 31st August 2020 when Participants can directly update aseXML schema via MSATS Browser.
R9 | Retail | aseXML Schema r39 p1 available | 2021-01-25 | Schema updated to reflect p1 update
R10 | Retail | MSATS Browser 'Participants > Participant Schema' pg | 2020-08-31 | None.
R11 | Retail | MSATS Browser 'B2B Browser > B2B Hub Queue' pg | 2020-08-31 | None.
R12 | Retail | MSATS Browser 'Reports and Alerts > Queue Monitoring' pg | 2020-08-31 | None.
R13 | Retail | Retirement of RM reports: RM7, RM8, RM10, RM12, RM14, RM15, RM18, RM19, SDD and SDR | 2020-08-31 | The retired RM reports will not be visible in the MSATS report menus. AEMO will generate a rejection for a retired RM report where requested (API/FTP).
R14 | Retail | CATS report changes : C1, C4, C7, C10, C11 | 2020-08-31 | None.
R15 | Retail | API Pull Functionality for B2M MTRD and MDMT, CATS, NMID | 2020-08-31 | None.
R16 | Retail | CATS CR changes to support new NMI classification codes | 2020-08-31 | None.
R17 | Retail | New Standing Data - Meter Installation Type Codes (MITC), Datastream Type 'N' | 2020-08-31 | There will be no new MITC's in MSATS until LNSP's create them. DataStreamType = 'N' values should be used upon creation of new CNDS records.
R18 | Retail | MSATS NMI discovery Display of TNI2 and Vic TUoS | 2020-08-31 | None.
R19 | Retail | MSATS NMI Master/Summary display of TNI2 and VIC TUoS | 2020-08-31 | None.
R20 | Retail | MSATS Browser 'Settlement Data' pg | 2020-08-31 | None.
R21 | Retail | New RM Report Requests: RM37, RM38, RM39 | 2020-08-31 | New RM reports will not be automatically pushed to Participants. Update to aseXML is required for the new RM Reports.
R22 | Retail | Historic Settlement Runs @ 30 minutes | 2020-08-31 | Participants will be able to verify existing NEM Settlement Runs.
R23 | Retail | Settlement Run @ 30 minutes | 2020-09-17 | AEMO will generate a new 30-minute NEM Settlement Run.
R24 | Retail | Settlement Run @ 5 Minutes | 2020-11-20 | AEMO will generate a new 5-minute NEM Settlement run.
R25 | Retail | Existing Meter Data Reports: RM9, RM11, RM13, RM26 | 2020-08-31 | Existing and new meter data will be reported in the existing RM reports (reflecting the interval length received by AEMO).
R26 | Retail | Existing Settlements Reports @30-min: RM16, RM17, RM20, RM21, RM22, RM25 | 2020-08-31 | Regardless of the granularity of the interval length received by AEMO, the data will be represented in 30 minute intervals.
R27 | Retail | Existing Settlements Reports @5-min: RM16, RM17, RM20, RM21, RM22, RM26 | 2020-10-30 | Regardless of the granularity of the interval length received by AEMO, the data will be represented in 5 minute intervals.
R28 | Retail | New UFE Reports: RM43, RM46 | 2020-10-30 | - Manufactured meter reads will be used in the calculation of these RM reports - New RM reports will not be automatically pushed to Participants. Update to aseXML is required for the new RM Reports.
R29 | Retail | Access to MSATS Browser via Markets Portal | 2020-08-31 | None.
R30 | Retail | B2B Transaction (SORD, CUST, MTRD etc) exchange supported between Participants | 2020-08-31 | None.
R31 | Retail | Rejection logic for MDMT for Interval Meters | 2020-10-30 | AEMO will reject MDMT files sent after this date where the IntervalReadDate is greater than this date
R35 | Retail | RM 30 Report | 2021-01-31 | None.
R36 | Retail | Standing Data Synchronisation MSATS - MDM | 2021-02-15 | Supports full Standing Data sysnchornisation CATS - eMDM
D1 | Dispatch | 5MS Bidding Service (API, FTP, JSON Format) | 2020-05-15 | End State deployed
D2 | Dispatch | Bid submission using API | 2019-11-29 | End State deployed
D3 | Dispatch | Bid submission using FTP | 2019-11-29 | End State deployed
D4 | Dispatch | Bid submission using Bid Web Portal | 2019-11-29 | End State deployed
D5 | Dispatch | Acknowledgement of submitted Bid | 2019-11-29 | End State deployed
D6 | Dispatch | Request Bid Reports through data-interchange/data model | 2019-11-29 | End State deployed
D7 | Dispatch | Dispatch, 5min Pre-Dispatch, Pre-Dispatch, and DS PASA using 5min Bids | 2019-11-29 | End State deployed
D19 | Dispatch | Full Data Model (5.0) | 2020-05-15 | End State deployed
D20 | Dispatch | NEM Reports | 2020-05-15 | None.
D23 | Dispatch | Rolling Sum Price Report | 2020-05-15 | AEMO will source from Production
S1 | Settlement | 30 and 5 minute reallocations Web UI | 2019-11-01 | None.
S2 | Settlement | Reallocation APIs | 2019-11-01 | None.
S4 | Settlement | Settlements and billing @ 30-min | 2020-03-16 | AEMO will use manufactured data in the creation of NEM Settlement Invoices. Generation of NEM Settlement invoices will not use prices derived from the 5MS Staging Dispatch solution
S5 | Settlement | Prelim, Final, and Revision Settlements | 2020-03-16 | AEMO will use manufactured data in the creation of NEM Settlement Invoices.
S6 | Settlement | Invoicing (Tax Invoice, RCTI, Adjustment Note, etc) | 2020-03-16 | AEMO will use manufactured data in the creation of NEM Settlement Invoices.
S7 | Settlement | Reconciliation reports (SR, SS, etc) | 2020-03-16 | AEMO will use manufactured data in the creation of NEM Settlement Invoices.
S8 | Settlement | NEM Reports | 2020-03-16 | AEMO will use manufactured data in the creation of NEM Settlement Invoices.
S9 | Settlement | Data Interchange | 2020-03-16 | AEMO will use manufactured data in the creation of NEM Settlement Invoices.
S10 | Settlement | Settlements Direct (Production version, no API’s) | 2020-03-16 | AEMO will use manufactured data in the creation of NEM Settlement Invoices.
S11 | Settlement | Prudential and settlement estimation @ 5-min | 2020-03-16 | None.
S12 | Settlement | Transition Settlement Statements (30 & 5-min) | 2020-07-08 | This state will reflect the transition week (i.e. mid week market start for 5MS). AEMO used manufactured data in the creation of NEM Settlement Invoices.
S14 | Settlement | NEM Prudential's Dashboard | 2020-05-15 | AEMO will use manufactured data in the creation of NEM Settlement Invoices.
S15 | Settlement | NEM Prudential Forecast Dashboard @5-min (Web UI) | 2020-05-15 | None.
S16 | Settlement | SCADA Data MDFF file @ 5 Min | 2020-06-30 | Test files supplied in both 15 and 5 minute formats

## Staging_GS
AEMO 5MS Functional Deployment Matrix, Version 1.4
Environment: 5MS Staging Environment Settlement: Global Settlement Date of MSATS data refresh: 30th July, 2020 AEMO Work Streams: Retail, Dispatch, Settlements
AEMO Functional Matrix ID | AEMO WorkStream | AEMO 5MS Programme: Function | Available for Participant testing | Functional Testing Considerations
R1 | Retail | MDFF NEM12 at any data interval via FTP | To be advised | To be advised
R2 | Retail | B2M MTRD MDFF NEM12 at any data interval via MSATS Browser 'B2B Browser > Upload File' pg | To be advised | To be advised
R3 | Retail | MDFF NEM13 via FTP | To be advised | To be advised
R4 | Retail | B2M MTRD MDFF NEM13 via MSATS Browser 'B2B Browser > Upload File' pg | To be advised | To be advised
R5 | Retail | MDMT MDMF Interval and Basic meter data files | To be advised | To be advised
R6 | Retail | API Push Functionality for B2M MTRD and MDMT, CATS, NMID | To be advised | To be advised
R7 | Retail | MSATS Browser 'Metering Data > Data Search' pg | To be advised | To be advised
R8 | Retail | MSATS Browser 'B2B Browser > Transforms and Protocols' pg | To be advised | To be advised
R9 | Retail | aseXML Schema r39 available | To be advised | To be advised
R10 | Retail | MSATS Browser 'Participants > Participant Schema' pg | To be advised | To be advised
R11 | Retail | MSATS Browser 'B2B Browser > B2B Hub Queue' pg | To be advised | To be advised
R12 | Retail | MSATS Browser 'Reports and Alerts > Queue Monitoring' pg | To be advised | To be advised
R13 | Retail | Retirement of RM reports: RM7, RM8, RM10, RM12, RM14, RM15, RM18, RM19, SDD and SDR | To be advised | To be advised
R14 | Retail | CATS report changes : C1, C4, C7, C10, C11 | To be advised | To be advised
R15 | Retail | API Pull Functionality for B2M MTRD and MDMT, CATS, NMID | To be advised | To be advised
R16 | Retail | CATS CR changes to support new NMI classification codes | To be advised | To be advised
R17 | Retail | New Standing Data - Meter Installation Type Codes (MITC), Datastream Type 'N' | To be advised | To be advised
R18 | Retail | MSATS NMI discovery Display of TNI2 and Vic TUoS | To be advised | To be advised
R19 | Retail | MSATS NMI Master/Summary display of TNI2 and VIC TUoS | To be advised | To be advised
R20 | Retail | MSATS Browser 'Settlement Data' pg | To be advised | To be advised
R21 | Retail | New RM Report Requests: RM37, RM38, RM39 | To be advised | To be advised
R22 | Retail | Historic Settlement Runs @ 30 minutes | To be advised | To be advised
R24 | Retail | Settlement Run @ 5 Minutes | To be advised | To be advised
R25 | Retail | Existing Meter Data Reports: RM9, RM11, RM13, RM26 | To be advised | To be advised
R26 | Retail | Existing Settlements Reports @30-min: RM16, RM17, RM20, RM21, RM22, RM25 | To be advised | To be advised
R27 | Retail | Existing Settlements Reports @5-min: RM16, RM17, RM20, RM21, RM22, RM26 | To be advised | To be advised
R28 | Retail | New UFE Reports: RM43, RM46 | To be advised | To be advised
R29 | Retail | Access to MSATS Browser via Markets Portal | To be advised | To be advised
R30 | Retail | B2B Transaction (SORD, CUST, MTRD etc) exchange supported between Participants | To be advised | To be advised
R31 | Retail | Rejection logic for MDMT for Interval Meters | To be advised | To be advised
R32 | Retail | CR rejection logic for CNDS Suffix and Type and Transfer Rejection by NMI Class. | To be advised | To be advised
R33 | Retail | CR Rejection Logic - LR not GLOPOOL and remove Objection and Notification for LR | To be advised | To be advised
R34 | Retail | GS Settlement post LR update | To be advised | To be advised
R35 | Retail | RM 30 Report | To be advised | To be advised
S1 | Settlement | 30 and 5 minute reallocations Web UI | To be advised | To be advised
S2 | Settlement | Reallocation APIs | To be advised | To be advised
S4 | Settlement | Settlements and billing @ 30-min | To be advised | To be advised
S5 | Settlement | Prelim, Final, and Revision Settlements | To be advised | To be advised
S6 | Settlement | Invoicing (Tax Invoice, RCTI, Adjustment Note, etc) | To be advised | To be advised
S7 | Settlement | Reconciliation reports (SR, SS, etc) | To be advised | To be advised
S8 | Settlement | NEM Reports | To be advised | To be advised
S9 | Settlement | Data Interchange | To be advised | To be advised
S10 | Settlement | Settlements Direct (Production version, no API’s) | To be advised | To be advised
S11 | Settlement | Prudential and settlement estimation @ 30-min | To be advised | To be advised
S12 | Settlement | Transition Settlement Statements (30 & 5-min) | To be advised | To be advised
S13 | Settlement | Settlement Statements @ GS (Financial UFE) | To be advised | To be advised
S14 | Settlement | NEM Prudentials Dashboard | To be advised | To be advised
S15 | Settlement | NEM Prudential Forecast Dashboard @5-min (Web UI) | To be advised | To be advised

## PreProduction
AEMO 5MS Functional Deployment Matrix, Version 1.4
Environment: AEMO PreProduction Environment Settlement: 30, 5 and Global Settlement Date of MSATS data refresh: 10/12/20 AEMO Work Streams: Retail, Dispatch, Settlements
AEMO Functional Matrix ID | AEMO WorkStream | AEMO 5MS Programme: Function | Industry Test |  | Market Trials - 5MS |  | Market Trials - GS
|  |  | Function included in Industry Testing? | Functional Testing Considerations (Industry Test) | Function included in Market Trials - 5MS? | Functional Testing Considerations (Market Trials - 5MS) | Function included in Market Trials - GS? | Functional Testing Considerations (Market Trials - GS)
D1 | Dispatch | 5MS Bidding Service (API, FTP, JSON Format) | 2020-11-29 | In transition state | 2021-07-05 | None. | N/A | N/A
D2 | Dispatch | Bid submission using API | 2020-11-29 | In transition state | 2021-07-05 | None. | N/A | N/A
D3 | Dispatch | Bid submission using FTP | 2020-11-29 | In transition state | 2021-07-05 | None. | N/A | N/A
D4 | Dispatch | Bid submission using Bid Web Portal | 2020-11-29 | In transition state | 2021-07-05 | None. | N/A | N/A
D5 | Dispatch | Acknowledgement of submitted Bid | 2020-11-29 | In transition state | 2021-07-05 | None. | N/A | N/A
D6 | Dispatch | Request Bid Reports through data-interchange/data model | 2020-11-29 | In transition state | 2021-07-05 | None. | N/A | N/A
D7 | Dispatch | Dispatch, 5min Pre-Dispatch, Pre-Dispatch, and DS PASA using 5min Bids | 2020-11-29 | In transition state | 2021-07-05 | None. | N/A | N/A
D19 | Dispatch | Full Data Model (5.0) | 2020-11-29 | In transition state | 2021-07-05 | None. | N/A | N/A
D20 | Dispatch | NEM Reports | 2020-11-29 | In transition state | 2021-07-05 | None. | N/A | N/A
D23 | Dispatch | Rolling Sum Price Report | 2020-11-29 | In transition state | 2021-07-05 | None. | N/A | N/A
R1 | Retail | MDFF NEM12 at any data interval via FTP | 2021-04-19 | Once implemented, no future functional change. Valid for 5, 15 & 30 minute intervals. | 2021-07-05 | None. | 2022-02-01 | None.
R2 | Retail | B2M MTRD MDFF NEM12 at any data interval via MSATS Browser 'B2B Browser > Upload File' pg | 2021-04-19 | Once implemented, no future functional change. Valid for 5, 15 & 30 minute intervals. | 2021-07-05 | None. | 2022-02-01 | None.
R3 | Retail | MDFF NEM13 via FTP | 2021-04-19 | None. | 2021-07-05 | None. | 2022-02-01 | None.
R4 | Retail | B2M MTRD MDFF NEM13 via MSATS Browser 'B2B Browser > Upload File' pg | 2021-04-19 | None. | 2021-07-05 | None. | 2022-02-01 | None.
R5 | Retail | MDMT MDMF Interval and Basic meter data files | 2021-04-19 | None. | 2021-07-05 | None. | 2022-02-01 | None.
R6 | Retail | API Push Functionality for B2M MTRD and MDMT, CATS, NMID | 2021-04-19 | AEMO will update a NEM Participants Push/Pull API functionality on request. This will be available until 31st August 2020 when Participants can directly update Push/Pull functionality via MSATS Browser | 2021-07-05 | None. | 2022-02-01 | None.
R7 | Retail | MSATS Browser 'Metering Data > Data Search' pg | 2021-04-19 | Once implemented, no future functional change. Valid for 5, 15 & 30 minute intervals. | 2021-07-05 | None. | 2022-02-01 | None.
R8 | Retail | MSATS Browser 'B2B Browser > Transforms and Protocols' pg | 2021-04-19 | None. | 2021-07-05 | None. | 2022-02-01 | None.
R9 | Retail | aseXML Schema r39 p1 available | 2021-04-19 | None. | 2021-07-05 | None. | 2022-02-01 | None.
R10 | Retail | MSATS Browser 'Participants > Participant Schema' pg | 2021-04-19 | None. | 2021-07-05 | None. | 2022-02-01 | None.
R11 | Retail | MSATS Browser 'B2B Browser > B2B Hub Queue' pg | 2021-04-19 | None. | 2021-07-05 | None. | 2022-02-01 | None.
R12 | Retail | MSATS Browser 'Reports and Alerts > Queue Monitoring' pg | 2021-04-19 | None. | 2021-07-05 | None. | 2022-02-01 | None.
R13 | Retail | Retirement of RM reports: RM7, RM8, RM10, RM12, RM14, RM15, RM18, RM19, SDD and SDR | 2021-04-19 | The retired RM reports will not be visible in the MSATS report menus. AEMO will generate a rejection for a retired RM report where requested (API/FTP). | 2021-07-05 | None. | 2022-02-01 | None.
R14 | Retail | CATS report changes : C1, C4, C7, C10, C11 | 2021-04-19 | None. | 2021-07-05 | None. | 2022-02-01 | None.
R15 | Retail | API Pull Functionality for B2M MTRD and MDMT, CATS, NMID | 2021-04-19 | None. | 2021-07-05 | None. | 2022-02-01 | None.
R16 | Retail | CATS CR changes to support new NMI classification codes | 2021-04-19 | None. | 2021-07-05 | None. | 2022-02-01 | None.
R17 | Retail | New Standing Data - Meter Installation Type Codes (MITC), Datastream Type 'N' | 2021-04-19 | There will be no new MITC's in MSATS until LNSP's create them. DataStreamType = 'N' values should be used upon creation of new CNDS records. | 2021-07-05 | None. | 2022-02-01 | None.
R18 | Retail | MSATS NMI discovery Display of TNI2 and Vic TUoS | 2021-04-19 | None. | 2021-07-05 | None. | 2022-02-01 | None.
R19 | Retail | MSATS NMI Master/Summary display of TNI2 and VIC TUoS | 2021-04-19 | None. | 2021-07-05 | None. | 2022-02-01 | None.
R20 | Retail | MSATS Browser 'Settlement Data' pg | 2021-04-19 | None. | 2021-07-05 | None. | 2022-02-01 | None.
R21 | Retail | New RM Report Requests: RM37, RM38, RM39 | 2021-04-19 | New RM reports will not be automatically pushed to Participants. Update to aseXML is required for the new RM Reports. | 2021-07-05 | None. | 2022-02-01 | None.
R22 | Retail | Historic Settlement Runs @ 30 minutes | 2021-04-19 | Participants will be able to verify existing NEM Settlement Runs. | 2021-07-05 | None. | N/A | N/A
R23 | Retail | Settlement Run @ 30 minutes | 2021-04-19 | First NEM Settlement run will be executed on TBC | 2021-07-05 | None. | N/A | N/A
R24 | Retail | Settlement Run @ 5 Minutes | N/A | N/A | 2021-07-05 | First NEM Settlement run will be executed on TBC | 2022-02-01 | None.
R25 | Retail | Existing Meter Data Reports: RM9, RM11, RM13, RM26 | 2021-04-19 | Existing and new meter data will be reported in the existing RM reports (reflecting the interval length received by AEMO). | 2021-07-05 | None. | 2022-02-01 | None.
R26 | Retail | Existing Settlements Reports @30-min: RM16, RM17, RM20, RM21, RM22, RM25 | 2021-04-19 | Regardless of the granularity of the interval length received by AEMO, the data will be represented in 30 minute intervals. | 2021-07-05 | None. | 2022-02-01 | None.
R27 | Retail | Existing Settlements Reports @5-min: RM16, RM17, RM20, RM21, RM22, RM26 | N/A | N/A | 2021-07-05 | None. | 2022-02-01 | None.
R28 | Retail | New UFE Reports: RM43, RM46 | N/A | N/A | 2021-07-05 | None. | 2022-02-01 | None.
R29 | Retail | Access to MSATS Browser via Markets Portal | 2021-04-19 | None. | 2021-07-05 | None. | 2022-02-01 | None.
R30 | Retail | B2B Transaction (SORD, CUST, MTRD etc) exchange supported between Participants | N/A | N/A | 2021-07-05 | None. | 2022-02-01 | None.
R31 | Retail | Rejection logic for MDMT for Interval Meters | N/A | N/A | 2021-07-05 | None. | 2022-02-01 | None.
R32 | Retail | CR rejection logic for CNDS Suffix and Type and Transfer Rejection by NMI Class. | N/A | N/A | N/A | N/A | 2022-02-01 | None.
R33 | Retail | CR Rejection Logic - LR not GLOPOOL and remove Objection and Notification for LR | N/A | N/A | N/A | N/A | 2022-02-01 | None.
R34 | Retail | GS Settlement post LR update | N/A | N/A | N/A | N/A | 2022-02-01 | None.
R35 | Retail | RM 30 Report | N/A | N/A | 2021-07-05 | None. | 2022-02-01 | None.
S1 | Settlement | 30 and 5 minute reallocations Web UI | 2020-03-01 | None. | 2021-07-05 | None. | 2022-02-01 | None.
S2 | Settlement | Reallocation APIs | 2020-03-01 | None. | 2021-07-05 | None. | 2022-02-01 | None.
S4 | Settlement | Settlements and billing @ 30-min | 2021-03-22 | AEMO will use manufactured data in the creation of NEM Settlement Invoices. | 2021-07-05 | None. | N/A | N/A
S5 | Settlement | Prelim, Final, and Revision Settlements | 2021-03-22 | AEMO will use manufactured data in the creation of NEM Settlement Invoices. | 2021-07-05 | None. | 2022-02-01 | None.
S6 | Settlement | Invoicing (Tax Invoice, RCTI, Adjustment Note, etc) | 2021-03-22 | AEMO will use manufactured data in the creation of NEM Settlement Invoices. | 2021-07-05 | None. | 2022-02-01 | None.
S7 | Settlement | Reconciliation reports (SR, SS, etc) | 2021-03-22 | AEMO will use manufactured data in the creation of NEM Settlement Invoices. | 2021-07-05 | None. | 2022-02-01 | None.
S8 | Settlement | NEM Reports | 2021-03-22 | AEMO will use manufactured data in the creation of NEM Settlement Invoices. | 2021-07-05 | None. | 2022-02-01 | None.
S9 | Settlement | Data Interchange | 2021-03-22 | AEMO will use manufactured data in the creation of NEM Settlement Invoices. | 2021-07-05 | None. | 2022-02-01 | None.
S10 | Settlement | Settlements Direct (Production version, no API’s) | 2021-03-22 | None. | 2021-07-05 | None. | 2022-02-01 | None.
S11 | Settlement | Prudential and settlement estimation @ 30-min | 2021-03-22 | Production data copied for Prudential processing. | 2021-07-05 | None. | 2022-02-01 | None.
S12 | Settlement | Transition Settlement Statements (30 & 5-min) | N/A | N/A | 2021-07-05 | None. | 2022-02-01 | None.
S13 | Settlement | Settlement Statements @ GS (Financial UFE) | N/A | N/A | N/A | N/A | 2022-02-01 | None.
S14 | Settlement | NEM Prudentials Dashboard | 2021-03-22 | AEMO will use manufactured data in the creation of NEM Settlement Invoices. | 2021-07-05 | None. | 2022-02-01 | None.
S15 | Settlement | NEM Prudential Forecast Dashboard @5-min (Web UI) | N/A | N/A | 2021-07-05 | None. | 2022-02-01 | None.
S16 | Settlement | SCADA Data MDFF file @ 5 Min | tbc | Test files supplied in both 15 and 5 minute formats | N/A | N/A | N/A | N/A

## Q&A
AEMO 5MS Functional Deployment Matrix Q&A
Q&A Ref. # | Date raised | Status | AEMO Functional Matrix ID | Question/Clarification | AEMO Response