## Slide 1: Five-Minute Settlement & Global Settlement Program
Stakeholder Information Session 3, 26 June 2019
Join Webex meeting (click to follow link) MEETING NUMBER (ACCESS CODE): 575 845 533
MEETING PASSWRD: F4X29742
DIAL IN: 1800 468 102 / 02 9037 0069
ACCESS CODE: 575 845 533
MEETING PASSWORD: 349 297 42

## Slide 2: Welcome and Introduction
Monica Morona

## Slide 3: 5MS & GS Team
AEMO 5MS & GS Program contacts:
  Sonja Nigmann, Senior Program Manager
  Peter Carruthers, Business Advocate
  Graeme Windley, Program Manager
  Chris Muffett, Business Lead
  Emily Brodie, Procedures Lead
  Sammy Wainrit, Systems Lead
  Greg Minney, Readiness Lead
  Monica Morona, Stakeholder Lead
5MS webpage: http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Five-Minute-Settlement

## Slide 4: Questions & Feedback
Questions for Information Session accepted via:
WebEx comments
5ms@aemo.com.au
Detailed questions and inquiries:
5ms@aemo.com.au
Engagement feedback:
5ms@aemo.com.au

## Slide 5: Agenda
NO | Time | AGENDA ITEM | Responsible
1 | 1:00pm – 1:10pm | Welcome and introduction | Monica Morona (AEMO)
2 | 1:10pm – 1:20pm | 5 Minute Settlement (5MS) rule overview and update | Chris Muffett (AEMO)
3 | 1:20pm – 1:30pm | Global Settlement (GS) rule overview and update | Emily Brodie (AEMO)
4 | 1:30pm – 1:45pm | AEMO’s 5MS Implementation Plan and Program Update | Graeme Windley (AEMO)
5 | 1:45pm – 1:55pm | Procedures changes consultation and workstream finalisation | Emily Brodie (AEMO)
6 | 1:55pm – 2:10pm | Developing against technical specifications – Systems workstream update | Hamish McNeish (AEMO)
7 | 2:10pm – 2:20pm | Moving towards market trials, transition and reporting – Readiness Workstream update | Greg Minney (AEMO)
8 | 2:20pm – 2:30pm | What does this mean for industry? | Chris Muffett (AEMO)
9 | 2:30pm – 2:40pm | How can you engage? | Monica Morona (AEMO)
10 | 2:40pm – 3:00pm | Questions | Monica Morona (AEMO)
11 | 3:00pm | Meeting close | Monica Morona (AEMO)

## Slide 6: 5MS rule overview and update
Chris Muffett

## Slide 7: Background – current NEM dispatch and settlement arrangements
Settlement prices (spot prices) are calculated on a 30 minute basis – the average of 6 x 5 minute dispatch prices
  one high dispatch price in a 30 minute trading interval raises the spot price (and vice versa)
Different time periods for dispatch and settlement were adopted due to limitations in metering and data processing when the NEM started (1998).
Technology is now available which makes 5 minute settlement possible.

## Slide 8: 30-minute settlement
The AEMC:
  found evidence of ‘price distortions’ occurring across the NEM, with the trend most pronounced in Queensland and South Australia
  expected that these distortions would get worse in the future

## Slide 9: AEMC decision
In November 2017, the AEMC made a final rule change altering the settlement period to 5 minutes, aligning with dispatch period
The industry “go live” is 1 July 2021
Purpose of rule change is to:
  remove the anomaly that exists between the 5 minute and 30 minute periods, which has been identified as a contributing factor to disorderly bidding
  provide a clearer price signal for investment in fast response technology, including batteries and demand response
Key areas affected:
  Metering
  Settlement calculation
  Dispatch and market information

## Slide 10: What is required to implement 5MS?
From 1 July 2021, following processes need to change to 5 minute basis:
  Bidding and offering into the NEM
  Settlement
  Intervention pricing
  Calculation of trading amounts and the cumulative price threshold
This means that AEMO and market participants will need to:
  upgrade metering to provide 5 minute data (where required)
  upgrade IT systems to store and process 5 minute data
  review/update existing contract terms and conditions
AEMO also has to update its procedures by December 2019

## Slide 11: GS rule overview and update
Emily Brodie

## Slide 12: Global settlement recap
On 6 December 2018, the AEMC finalised a rule to implement Global Settlement (GS)
GS is an alternative methodology for settling electricity within a distribution area. It will replace settlement-by-difference. GS will:
  remove any inequity between retailers
  provide visibility of the unaccounted for energy (UFE) within distribution areas
More information is provided in the Global Settlement fact sheet: http://www.aemo.com.au/-/media/Files/Electricity/NEM/5MS/Program-Information/2018/5MS_What-is-global-settlement.pdf

## Slide 13: Settlements by Difference vs Global Settlements

## Slide 14: Global settlement implementation timeline
1 December 2019
AEMO procedures updated for both 5MS and GS
1 July 2021
5MS begins
AEMO starts publishing UFE data (‘soft start’)
6 February 2022
GS begins
1 March 2022
AEMO’s first annual report on UFE trends
New procedure required
[NER 3.15.5(d) and 11.112.5]
New annual report
[NER 3.15.5B] and new reporting guidelines [NER 3.15.5B(d) and 11.112.6]

## Slide 15: Key areas affected by global settlement
GS is being implemented in parallel with 5MS
Some market procedures – these are being consulted on as part of the metering and settlements packages
AEMO and participants’ IT systems – changes across both retail and wholesale systems
Additional data:
  NSPs/MDPs required to provide information on non-contestable unmetered loads
  MDPs required to provide metering data for all connection points
AEMO will begin publishing UFE from 1 July 2021:
  no financial impact to retailers from UFE allocation from 1 July 2021 to 5 February 2022
  UFE allocation will be financial from 6 February 2022

## Slide 16: AEMO’s 5MS & GS Implementation Plan and Program Update
Graeme Windley

## Slide 17: Program Scope (IT Focus)
Dispatch
Settlements
Function
Manages demand forecasting and the dispatch price every 5-minutes (and aggregates spot price every 30 minutes). Ensures electricity demand is met.
Function
Manages the calculation of financial liabilities and credits between market participants daily and settles all trade in the NEM on a weekly basis.
Metering
Function
Manages receipt and storage of market data (metering and standing data). Metering prepares data for market settlement and enables market reporting.
Infrastructure / External Web Development / Internal webMethods Integration
Market Procedures, Stakeholder engagement and market/industry readiness
Process Mapping, Change and Training, Cutover and Transition
Program Management
Scope of change
Increase daily bidding intervals from 48 to 288.
New data structures required to receive, use and store five-minute bids and offers.
Changes required to calculate the floor price and price cap.
AEMO to publish five-minute data.
Scope of change
Enable receipt of metering data every 5 minutes.
Enable management of >2 trillion data points by 2028.
Change profiling algorithms to derive 5 minute energy data.
Enable energy allocation to be at 5, 15 and 30 minute intervals.
Scope of change
Enable settlement on 5 min granularity, 5 min price, and Marginal Loss Factors (MLF)
Settlement estimations will calculate energy transactions per 5 min period.
Additional calculations (i.e. market ancillary services, FACS), to be calculated with 5-minute data.
Solution Path
Enhance Legacy Systems
Solution Path
Enhance Legacy Systems
Solution Path
Build New Solution using Strategic Technologies
IT Workstreams
Remainder 5MS & GS Program

## Slide 18: 5MS Program Timeline – Level 1 Milestones
2018 |  |  | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  |  | 2022 |  |  |  |  |  |  |  |  |  |  | 
OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUJ | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Production (5min bids only)
Today
REGULATORY
Transition (30min & 5min bids)
SYSTEMS
DEVELOPMENT
GS Go Live 6-2-22
5MS Go Live 1-7-21
5MS / GS – Procedure, Guideline & Document updates
5MS Staging
AEMO Publishes 5MS & GS Procedures
IEC recommendation on B2B Procedures
Pre-Production
READINESS
Proc Publish
1-12-19
New Metering
Go Live
1-12-22
AEMO System Development & Test - RETAIL
MDM & PAE Go Live 1-11-20
5MS Rule Amendment Window (Technical Changes)
Requirements & High Level Design
5MS & UFE Publishing Go Live
GS Industry Go Live
Drafting Amendments submitted to AEMC
New Metering to be 5MS Compliant Date
Market Readiness Strategy
Market Readiness Strategy published by AEMO
5MS Market Trials commence
5MS Market Trials conclude
Metering Accreditation Complete
Market Trial: 5MS
Market Trial: 5MS
Market Trial: 5MS
All AEMO Internal System Development Commenced
5MS Staging Environment Live
All AEMO Internal System Development Completed
INDUSTRY ENVIRONMENTS
AEMO UAT
AEMO System Development & Test - DISPATCH
AEMO System Development & Test - SETTLEMENTS
AEMO SIT

## Slide 19: 5MS & GS Implementation Approach
AEMO has developed and implemented a Milestone Management Framework
Key elements of the framework:
  Defined milestones with associated dates
  Reporting process
  Change management and impact assessment
Milestones
  Level 1 milestones: key milestones that apply to the overall Program
  Level 2 milestones: milestones by workstream that show key dates relevant for participants
  Defined in Microsoft Project, available for sharing with participants

## Slide 20: Program Update
Overall
  Level 1 and Level 2 Milestones baselined, available for reporting
  Level 3 milestones with industry impact also distributed via MPP
Procedures Workstream
  Overall Green, several individual documents delays, however tracking ahead of schedule to complete all documentation by September.
  Currently three consultations out for review.
Metering Workstream
  AEMO Internal – Proof of Concept accepted for the new Metering Data Management and Profiling (MDM & PAE) solution, build begun.
  Procedures Metering Package 2 has been delayed due to definition of GS and UFE discussions in the market.
  MDM File Format and Load Process (Metering Data) consultation submissions just closed. MSATS Tech Spec to be published 28 June.
Dispatch Workstream
  AEMO Internal - Internal work on track, including industry web Bidding interface. System Testing has begun for developed work packages.
  Technical details for Negative Residue Management due for draft distribution 28 June – final draft Dispatch technical distribution.
Settlements Workstream
  AEMO Internal work on track, System Testing begun for developed work packages.
  All HL Impact Assessments to industry; Draft Tech Spec’s by 31 Oct 2019
Readiness Workstream
  First Readiness Working Group set for Thursday 27 June
  AEMO to take an inclusive approach to defining industry cutover activities

## Slide 21: Procedures Changes Consultation and Workstream Finalisation
Emily Brodie

## Slide 22: Procedures - packaging
Approximately 70 AEMO documents are directly affected by 5MS and GS
Around 20 of these are ‘rules consultation’ procedures, usually requiring 2 rounds of formal consultation
Work packages have been progressively considered by the Procedures Working Group:
  AEMO provides an impact assessment for each procedure and the proposed consultation approach for review and discussion
  Focus groups have been used to provide input into procedure development
  Procedure changes are then subject to consultation
Metering | Settlements | Dispatch | Operations
Metering data Metrology, MSATS procedures & service levels Miscellaneous | SRA Estimation Reallocations Prudentials TNSP Miscellaneous | Bids/Offers Spot market Pricing Miscellaneous | No packages – progressive release

## Slide 23: Procedures prioritisation
*no rules consultation required
TIMING
Started and on track
Started late
Overdue
Complete
CONTENT
No Issues
Issues
Sever Issues
 | Pre-consultation |  | Consultation |  |  | 
5 MINUTE SETTLEMENT PROCEDURES TRACKING | TIMING |  |  |  |  | CONTENT
 | HLIA | PWG Engagement | Consultation paper | Draft documents | Final documents | Package content
METERING |  |  |  |  |  | 
1. Metering - Metering Data & Metrology | Jul-18 | Jul-18 | Sep-18 | Jan-19 | Mar-19 | 
2. Metering - MSATS and SLPs | Jul-18 | Dec-18 & Mar-19 | Apr-19 | Aug-19 | Sep-19 | 
3. Metering - Miscellaneous* | Jul-18 | Feb-19 | n/a | Jun-19 | Aug-19 | 
B2B Procedures - B2B file size | n/a | Feb-19 | n/a | n/a | n/a | 
SETTLEMENTS |  |  |  |  |  | 
SRA | Jun-18 | Jul-18 | n/a | Jul-18 | Aug-18 | 
SRA round #2 | Jun-18 | Feb-19 | Mar-19 | Jun-19 | Aug-19 | 
TNSP | Feb-19 | Feb-19 | n/a | Apr-19 | Jun-19 | 
Estimation | Aug-18 | Aug-18 | Nov-18 | Feb-19 | Apr-19 | 
Reallocations | Dec-18 | Dec-18 | n/a | Dec-18 | Feb-19 | 
Miscellaneous | Oct-18 | Oct-18 | Dec-18 | Mar-19 | May-19 | 
Prudentials | Aug-18 | Sep-18 | Apr-19 | Jun-19 | Aug-19 | 
DISPATCH |  |  |  |  |  | 
2. Dispatch - Spot market - Rules consultation | Sep-18 | Oct 18 (ongoing) | Jan-19 | Jun-19 | Aug-19 | 
2. Dispatch - Spot market - For comment* | Sep-18 | Oct 18 (ongoing) | n/a | Jul-19 | Aug-19 | 
3. Dispatch - Pricing - Rules consultation | Aug-18 | Aug 18 (ongoing) | Aug-18 | Sep-18 | Nov-18 | 
3. Dispatch - Pricing - For comment* | Aug-18 | Aug 18 (ongoing) | n/a | May-19 | Jun-19 | 
4. Dispatch - Miscellaneous* | Jan-19 | Feb-19 | n/a | May-19 | Jun-19 | 
POWER SYSTEM OPS |  |  |  |  |  | 
1. Operations - Miscellaneous* | TBA | Apr 19 (ongoing) | n/a | n/a | Oct-19 | 

## Slide 24: Approach to transitioning 5MS/GS procedures workstream
Stage 1: active engagement through PWG on managing 5MS procedure changes (July 2018 to August 2019)
Stage 2: transitioning to BAU through structured and supported engagement on procedural issues that arise from 5MS/GS implementation e.g. during industry testing and market trials
Stage 3: BAU – AEMO teams run procedure changes
 | Timeframe | Approach
Stage 1 | up to August 2019 | PWG meetings are scheduled
Stage 2 | from August 2019 to 2021 | 5MS procedure changes are managed by those AEMO teams responsible for the relevant procedures. Stakeholder engagement will include discussion or consultation through 5MS forums where appropriate. 5MS program maintains and coordinates a procedures actions log.
Stage 3 | 2021 onwards | BAU - procedure changes are managed through those AEMO teams responsible for the relevant procedures.

## Slide 25: Ongoing Consultations
5MS Metering Package 2: Final Report and Procedures scheduled for publication on 30 September 2019
5MS Metering Package 3: AEMO will be publishing these documents shortly for comments only
5MS Settlements Package – Auction Participation Agreement: Final report and procedures scheduled for publication on 5 August 2019
5MS Settlements Package – Prudentials - Credit Limit Procedures: Final report and procedures scheduled for publication on 16 August 2019
5MS Dispatch Package – Pricing and Misc. Procedures: Final procedures will be published July 2019
5MS Dispatch Package – Spot Market Operations Timetable: Final report and procedures scheduled for publication on 16 August 2019
Notes: 5MS Metering package 2
This consultation is a co-consultation taking into consideration 5MS and Global Settlement items as well as a number of Issues and Change Forms (ICFs)
This package includes more procedures than package 1 and is materially more complex
5MS Metering package 3
AEMO will consider comments received and then publish the final versions to the AEMO website

## Slide 26: Upcoming Consultation
More information will be provided through the PWG on the upcoming consultations:
Metering Procedures Package 3
Dispatch Procedures Package 2, 4 & 5
Power System Operations Procedures (details to be provided on website)
https://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Five-Minute-Settlement/Procedures-Workstream

## Slide 27: Developing against technical specifications – Systems Workstream Update
Hamish McNeish

## Slide 28: NEM Retail System Change Heatmap
B2M / B2B Interfaces
CATS / MDM Processes
MSATS Browser / Reports
MDMT
CATS Standing Data
B2M aseXML schema
NMID
CATS
B2B Transactions
B2B aseXML schema
Meter Data screens
RM21/27
CR Processing
RM11,12,13,14,16
RM17,18,19,20,22
VIC TUoS
Profiling
Energy Allocation
Estimation / Substitution
Meter Data Validation
RM28,30,31,32
RM33
RM7,8,9,10
RM15,29
C2,3,6,7,9,10
C11,12,13
SDR
C1,4
MSATS B2M APIs

## Slide 29: NEM Wholesale System Change Heatmap
DISPATCH
SETTLEMENT
POWER SYSTEM
Bids/Offers
Dispatch
Predispatch (P5/P30s)
ST PASA
Settlement 5MS Calc.
Settlement GS Calc.
Causer Pays Factors
Data Model
SRA
MT PASA / EAAP
Demand Forecasting
Data Model
Generator Recall
Data Model
RERT
Administered Pricing
Suspension Pricing
Negative Residue Management
Wind/Solar Availability
Reallocations
Estimation and Prudentials
VAR/MW Dispatch
Constraints
Spot Price
Registration
IRSR Calc.

## Slide 30: Technical Specifications
Full list published on the AEMO 5MS Webpage
https://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Five-Minute-Settlement/Systems-Workstream/Systems-Technical-Documents
Support vendor/participant systems design, development and testing

## Slide 31: Technical Specifications
Technical Document | Description | DRAFT | FINAL
Meter Data File Format (MDFF) B2B and B2M Meter Data Format | Changes to support 5-minute meter data | 25 Jan 19 | 30 Apr 19
MDM File Format and Load Process Processing/loading meter data into AEMOs MDM | Changes to support loading and processing MDFF | 20 May 19 | 31 Jul 19
MSATS 5MS Technical Specification B2M via API | Changes to introduce APIs for existing B2M messages | 31 May 19 | 30 Sep 19
MSATS 5MS Technical Specification MSATS browser and RM reports | Changes in MSATS MDM functionality for 5-minute meter data | 28 Jun 19 | 30 Aug 19
Retail/Metering

## Slide 32: Technical Specifications (2)
Technical Document | Description | DRAFT | FINAL
EMMS 5MS Technical Specification Bidding Format and submitting Dispatch/Pre-dispatch/PASA | Changes related to bidding shifting to 5-minute intervals | 28 Dec 18 | 2 Apr 19
EMMS 5MS Technical Specification Bidding Web UI/APIs/Upload Mandatory Restrictions Pricing and Miscellaneous | Changes to support Web Bidding interface, and changes related to pricing shift to 5-minutes | 28 Jun 19 | 31 Jul 19
Dispatch and Operations

## Slide 33: Technical Specifications (3)
Technical Content | Description | DRAFT | FINAL
EMMS 5MS Technical Specification Reallocations | Changes to support reallocations at 5-minute resolution | 31 Jul 19 | 31 Oct 19
EMMS 5MS Technical Specification Settlements and Billing | Changes to support Settlements at 5-minutes and Global Settlement | 28 Jun 19 | 27 Dec 19
EMMS 5MS Technical Specification Prudentials and Estimation | Changes required due to changes in Settlement and Billing | 30 Oct 19 | 31 Jan 20
Settlements

## Slide 34: Testing Environments
For 5MS the following environments will be available:
  5MS Staging
  Provided to support vendors/participants testing systems
  AEMO will progressively release into this environment
  Release schedule is outlined in the SWG Meeting Packs
  AEMO’s first release (bidding and dispatch) is 29 Nov 19
  Pre-Production
  Will provide the to-be production state
  Provided to support vendors/participants testing and controlled changes
  Used for Industry Testing (not coordinated) and Market Trials (coordinated)

## Slide 35: 5MS Architecture Overview
Systems uplift (application, integration, data, infrastructure and security) to meet the
  5MS and GS Rule Change requirements
  Non-functional requirements arising primarily due to increase in the volume of data (current and future volumes) and enriched data (e.g. MDFF data)
Implement modern data exchange protocols (e.g. RESTful APIs) and formats (e.g. JSON) for the new functionalities and current functionalities where there are significant changes
Provide support for legacy interfaces to support transition / contingency
Provide an accompanying API where a significant change to a web application occurs
Modern data exchange protocols over Internet

## Slide 36: 5MS Architecture On a Page

## Slide 37: Vendor/Participant Considerations
1. Review the 5MS systems High-Level Impact Assessment
Determine areas of impact to your systems
Use this information as an input to requirements and design artefacts
2. Review and provide feedback on DRAFT Technical Specifications
Technical Specifications are released by email on the AEMO artefacts
Use this information as an input to design documents
Feedback is 2 weeks from publication
3. Design and Develop based on FINAL Technical Specifications
Plan based on AEMOs dates for FINAL technical specifications
Use this information as an input to design documents
Carryout internal tests against this technical specification
4. Plan Testing using the 5MS Staging Environment
Plan testing activities based on AEMO dates of releases into 5MS Staging
Carry out integration testing against 5MS Staging

## Slide 38: Moving towards market trial, transition and reporting – Readiness workstream update
Greg Minney

## Slide 39: 5MS Program Timeline – Readiness Workstream
2018 |  |  | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  |  | 2022 |  |  |  |  |  |  |  |  |  |  | 
OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUJ | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Production (5min bids only)
Today
REGULATORY
Transition (30min & 5min bids)
SYSTEMS
DEVELOPMENT
GS Go Live 6-2-22
5MS Go Live 1-7-21
5MS / GS – Procedure, Guideline & Document updates
5MS Staging
AEMO Publishes 5MS & GS Procedures
IEC recommendation on B2B Procedures
Pre-Production
READINESS
Proc Publish
1-12-19
New Metering
Go Live
1-12-22
AEMO System Development & Test
MDM & PAE Go Live 1-11-20
5MS Rule Amendment Window (Technical Changes)
Requirements & High Level Design
5MS & UFE Publishing Go Live
GS Industry Go Live
Drafting Amendments submitted to AEMC
New Metering to be 5MS Compliant Date
Market Readiness Strategy
Market Readiness Strategy published by AEMO
5MS Market Trials commence
5MS Market Trials conclude
Metering Accreditation Complete
Market Trial: 5MS
Market Trial: 5MS
Market Trial: 5MS
All AEMO Internal System Development Commenced
5MS Staging Environment Live
All AEMO Internal System Development Completed
INDUSTRY ENVIRONMENTS
AEMO UAT

## Slide 40: 5MS/GS Market Readiness Workstream Scope
Establishment of objective market readiness criteria,
Regular reporting by impacted participants
Analysis and assessment of reported results
Readiness issue and risk assessments
Readiness Reporting and Management
Industry Testing and Market Trials
Transition and Cutover
Metering Accreditation Updates
Planning, execution and management of Market / Industry test activities
Environment support and availability
Market Transition Strategy which details the steps, activities and responsibilities in moving from current state to future state
Planning and monitoring of participant and AEMO transition activities
Systems cutover planning and execution - including industry co-ordination
Identification of timing and scope of accreditation requirements
Accreditation Update approach

## Slide 41: Readiness Working Group
Main stakeholder forum for direct industry input into the planning and execution of readiness activities
The RWG will:
  Bring to the table individual participant views and issues
  Help coordinate, assist and prepare for the transition and cutover to 5MS and GS
  Engage with and provide expertise to AEMO on 5MS and GS market readiness activities
Engaging early and often in the 5MS/GS market readiness work will ensure the timely identification of any potential readiness issues, including potential resolution options
All deliverables from the Readiness Workstream will be available on the 5MS Site

## Slide 42: Indicative timelines
Item | Engagement Commences | Draft Paper Released | Final Paper Released
Market Readiness Strategy | June 19 | 30 August 19 | 29 Nov 19
Industry Test Strategy | June 19 | 30 August 19 | 31 Oct 19
Transition & Go-Live Strategy | July 19 | 30 Sept 19 | 31 Jan 20
Market Trial Strategy | August 19 | 29 Nov 19 | 28 Feb 20
Metering Service Provider Accreditation Update Plan | August 19 | 29 Nov 19 | 31 Mar 20
Industry Readiness Reporting Plan | Sept 19 | 29 Nov 19 | 31 Jan 20
NOTE: Deliverable dates are currently draft/proposed dates

## Slide 43: What does this mean for industry?
Chris Muffett

## Slide 44: Key milestones for the industry
1 July 2021
Five-Minute Settlement begins
AEMO starts publishing UFE data (‘soft start’)
6 February 2022
Global Settlement has financial impact
1 December 2022
Deadline for conversion of 5-minute capable meters

## Slide 45: Preparations leading up to 1 July 2021
Participants | Five-Minute Settlement | Global Settlement
Generators (including SGAs) | Systems and processes in place to: Submit 5-minute offers (scheduled and semi-scheduled) Receive 5-minute metering data (in addition to existing data) Receive 5-minute granularity settlement reports | 
Retailers | Systems and processes in place to: Receive 5-minute metering data (in addition to existing data) Receive 5-minute granularity settlement reports | Systems and processes in place to: Receive UFE for each local area Receive UFE allocation data (although no financial impact)
Network operators | Systems and processes in place to: Receive 5-minute metering data (in addition to existing data) | Provide information on non-contestable unmetered loads (including NMIs, profiling, etc) Assist with the clarification of cross-boundary and bulk supply points
Metering Coordinators | Engage with FRMPs and metering providers on the configuration/replacement of meters to 5-minute | 
Metering Providers | Configure/replace meters to 5-minute as arranged by Metering Coordinators (e.g. Type 1-3) | 
Metering Data Providers | Systems and processes in place to: Provide 5-minute metering data in MDFF to AEMO Provide 5-minute metering data via B2B | Systems and processes in place to provide metering data for all distribution connection points
Large customers | Systems and processes in place to receive 5-minute metering data and settlement reports (wholesale customers) Engage with their retailer on any requirement/impact of 5-minute metering (e.g. Type 1-3) | Engage with their retailer on any requirement/impact from UFE

## Slide 46: Preparations post 1 July 2021
Leading up to 6 February 2022:
Leading up to 1 December 2022:
Participants | Global Settlement
Retailers | Systems and processes in place to receive and reconcile UFE allocation data (with financial impact)
Network operators, metering coordinators and meter data providers | Assist with the resolution of any connection point or metering issues identified as part of UFE publication
Large customers | Any changes to contractual arrangements as a result of UFE allocation
Participants | Global Settlement
Retailers | Engage with metering coordinators on the conversion of 5-minute capable meters installed since 1 December 2018
Metering Coordinators, Metering Providers and Meter Data Providers | Facilitate the conversion of 5-minute capable meters installed since 1 December 2018

## Slide 47: How can you engage?
Monica Morona

## Slide 48: Where can you find more information?
AEMOs website provides background information, and factsheets
https://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Five-Minute-Settlement
Details of the Procedures, Systems and Readiness Workstreams:
  Including Procedures information
  Technical Specifications and documents
  Consultation timeframes

## Slide 49: Website Update – Ongoing Project

## Slide 50: Working Groups and Forums

## Slide 51: Forward Calendar & Engagement
Meetings and forum dates:
http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Five-Minute-Settlement

## Slide 52: 5MS & GS Mailing List
One point of contact – 5ms@aemo.com.au
5MS & GS have mailing lists for:
  General information
  Consultation activities
  Each of the workstreams:
    Procedures
    Systems
    Readiness
Contact us to be included on any of the above mailing lists