## Version control
VERSION CONTROL
|  | RWG | 5MS/GS Readiness working group
VERSION | RELEASE DATE | CHANGES
0.1 | 2020-07-14 |  | Draft released to the 5MS DFG and RWG for comment
1 | 2020-08-28 |  | Final published

## 5-min bidding phases
5-MINUTE BIDDING PHASES

## Bidding transition plan
5MS BIDDING TRANSITION PLAN |  |  | TRANSITION PERIOD = from when AEMO begins accepting 5-min bids to 5MS start |  |  | 5MS commencement date is 1 October 2021
# | Phase | TRANSITION ACTIVITY | TRANSITION ACTIVITY OBJECTIVE | ASSUMPTIONS/COMMENTS | RESPONSIBILITY | DEPENDENCIES | ACTIVITY TRANSITION START DATE | ACTIVITY TRANSITION END DATE | RULE TIMING
BTA# | Describes the phases that support the transition to 5-min bidding | Describes the Bidding transition activity | Outlines the objective of the transition activity | Lists any assumptions or comments related to the activity | Assigns leadership and responsibility of the activity to a specific participant type | Lists any dependencies related to the activity | Lists the transition start date for this activity. When no transition start date is specified for an activity, participants may commence the transition at any time prior to the transition end date for that activity. | Lists the transition end date of this activity. It is expected that all relevant participants have completed the activity by this date. | Lists the commencement date of the 5MS rule requirement that the activity supports
BTA1 | Production go-live | Deploy 5-min bidding capability in production | Enable 5-min bidding transition period for industry | AEMO plans to accept 5-min bids from midday, 1 Apr 21 Bid validation will require each 5-min bid within each half hour to be identical, giving them the same profile as 30-min bids, independent of the trading day to which the bid applies. AEMO will use the latest submitted Offer/Bid regardless of origin (either 30-minute or 5-minute) for the DUID, Service, Trading Date. Participants may choose to transition from 30-minute to 5-minute at any time within the Transition period and AEMO will use the appropriate submission. AEMO’s systems can accommodate Participants reverting back to 30-minute Offers/Bids, however AEMO suspects this might cause confusion and discourages this in Production. | AEMO | BTA9 | 2021-04-01 | 2021-04-01 | 2021-10-01
BTA2 | Transition | 5-min bids submitted (in JSON format) during the transition period | Provide participants the option of submitting 5-min bids ahead of 5MS start. | Bids for each 5-min within each half hour must be identical, independent of the trading day to which the bid applies. | Scheduled and semi-scheduled generators, scheduled loads and MNSPs | BTA1 | 2021-04-01 | 2021-09-30 | n/a
BTA3 | Transition | 30-min bids can continue through transition period | Provide participants the option of continuing to submit 30-min bids until 5MS start. | 30-min bids will be stored as usual, but will also be converted to and stored as a corresponding 5-min bid. This is independent of the trading day to which the bid applies. | Scheduled and semi-scheduled generators, scheduled loads and MNSPs |  | 2021-04-01 | 2021-09-30 | n/a
BTA4 | 5MS Start | 5-min bids submitted (in JSON format) from 5MS start | Enable 5-min bidding in accordance with the 5MS rule | Bids for each 5-min within each half hour do not have to be identical, allowing 5-min profiling of bids. | Scheduled and semi-scheduled generators, scheduled loads and MNSPs | BTA1 | 2021-10-01 | n/a | 2021-10-01
BTA5 | 5MS Start | AEMO rejects 30-min bids from 5MS start | Prevent 30-min bidding in accordance with 5MS rule | Participants submitting 30-min bids will receive messages explaining that 30-min bidding is no longer allowed. | AEMO |  | 2021-10-01 | n/a | 2021-10-01
BTA6 | Preparation | Monitor for valid 5-min bids before the start of the transition period | Support AEMO's and participants system implementations | All latest valid bids must be available in 5-min format at the start of the transition period. Very few participants submit bids more than two weeks in advance. This means that almost all latest valid bids will be in 5-min format at the start of the transition. However, some participants have already submitted bids beyond 1 Apr 21; and a few participants' latest valid bids are years old. | AEMO |  | Underway | 2020-11-28 | n/a
BTA7 | Preparation | Request updated 30-min bids from relevant participants | Support AEMO's and participants system implementations | From the monitoring in BTA6 AEMO will request updated 30-min bids to populate the 5-min bidding tables under BTA3. | AEMO | BTA6 | 2020-08-01 | 2020-11-28 | n/a
BTA8 | Preparation | Submit valid 30-min bid | Support AEMO's and participants system implementations | Participants may respond to an AEMO request under BTA6 to update their 30-min bids. | Scheduled and semi-scheduled generators, scheduled loads and MNSPs | BTA7 | 2020-08-01 | 2020-11-28 | n/a
BTA9 | Preparation | Manual translation of 30-min bid into 5-min bid if no updated 30-min bid submitted in accordance with BTA8 | Support AEMO's 5MS implementation in accordance with 5MS transitional rule |  | AEMO | BTA6 | 2020-12-01 | 2021-03-31 | 2021-10-01