## Version
VERSION CONTROL
|  |  | RWG | 5MS/GS Readiness working group
| VERSION | RELEASE DATE | CHANGES
| 0.1 | 2019-12-20 |  | Draft released to the 5MS/GS RWG and CFG for comment
| 0.2 | 2020-02-28 |  | Second draft released to the 5MS/GS RWG and CFG for comment containing additional sectionon minimum criteria for commencing 5MS and GS.
| 1 | 2020-06-05 |  | Final document published, considers feedback from RWG and CFG

## Readiness Contingency Scenarios
5MS GS INDUSTRY READINESS CONTINGENCY PLAN | [6 empty] | 2020-06-05
Contingency Scenario Ref | Industry Risk Ref | Contingency Scenario | Scenario Description | Scenario Category | Priority (H/M/L) | Likelihood (H/M/L) | Impacted Stakeholders | Triggers | Monitoring Mechanism | Response | Comments
C1 | R14, R15, R16, R17 | Minimum criteria not met for 5MS/GS commencements | Minimum criteria (defined in Industry readiness contingency plan word document) not met for 5MS/GS commencements resulting in critical impact to NEM operations and/or material risk of market or power system failure | Readiness | H | L | AEMO, Impacted Participants | The following triggers may indicate that minimum criteria for 5MS/GS commencements may not be met: - Readiness reporting results, 7-8 months in advance of the commencement dates - Insufficient participants in industry testing/market trials - Unfavourable industry testing/market trial results | Industry Readiness Reporting, Industry testing and Market trials | - Perform impact assessment, confirming risk of fundamental market failure and recommend preferred contingency response based on the physical and commercial market requirements - Where necessary, escalate issue and recommend actions to the PCF or EF - Submit rule change to AEMC (6 month process) where no other alternative approach exists | Making a rule change request: https://www.aemc.gov.au/our-work/changing-energy-rules-unique-process/making-rule-change-request A rule change request was lodged with AEMC on Thursday, 9 April 2020 seeking a 12-month deferral of both 5MS and GS. This contingency scenario continues to be relevant, for either the current commencement dates or any future change to the commencement date.
C2 | R14, R15, R16 | Essential meter(s) not fully compliant at 5MS rule commencement | Essential meter(s) installation and reconfiguration not fully compliant at 5MS rule commencement | Readiness | H | M | AEMO, Impacted Participants | Industry Readiness Reporting shows that applicable MTP activities are showing trends of running late resulting in a number of Essential meters not being fully compliant at 5MS Rule commencement | Industry Readiness Reporting | - MDPs to provide 5 minute subs until affected meters are compliant or - MDPs do not send through reads and AEMO profiled supported substitutes until affected meters are compliant - Escalate issue, recommend actions and seek guidance from the PCF and EF as appropriate
C3 | R14, R15, R16, R17, R19 | Essential meter(s) metering data delivery issues | MDP(s) not providing 5-min data for Essential meter(s) as required at 5MS commencement resulting in short term financial volatility | Readiness | H | M | AEMO, Impacted Participants | Ongoing monitoring of Industry Readiness Reporting shows that applicable MTP activities are running late resulting in 5min metering data not being provided for a number of Essential meters at 5MS Rule commencement MDP not suitably accredited by the defined dates outlined in the MSP Accreditation Update Plan | Industry Readiness Reporting (of Metering Transition Plan activities) | - Response dependent on the underlying issues (consider duration and materiality) - MDP to confirm rectification plan - BAU MDP processes, including manually loading data into MSATS or finding alternative pathways to MSATS using different sites - AEMO to generate subs at time of Settlement until issue resolved (BAU process) - AEMO and Participants to provide support as required (alternative mechanism to provide data) - Escalate issue, recommend actions and seek guidance from the PCF and EF as appropriate - As a last resort, MC to transfer NMIs to alternative MDP
C4 | R14, R15, R16, R19 | Metering Service Provider Participant(s) not suitably accredited at Rule commencement | MDP(s) or MP(s) accreditation not suitable at 5MS commencement | Readiness | H | L | AEMO, Impacted Participants | Ongoing monitoring of Industry Readiness Reporting shows that applicable MTP activities are running late resulting in an MDP or MP not being accredited at 5MS Rule commencement | Industry Readiness Reporting (of Metering Transition Plan activities) | - MC to transfer NMIs to accredited MDPs/MPs - AEMO and Participants to provide support as required - Escalate issue, recommend actions and seek guidance from the PCF and EF as appropriate | Trigger for type 4 and 4A and VIC AMI new and replacement metering requirements treated as BAU process Trigger for non-contestable unmetered loads is also treated as BAU process
C5 | R14 | MSATS standing data not fully available at GS Rule commencement | Metering and MSATS standing data not fully available/updated at GS rule commencement (post revision 2) - leading to material settlement difference | Readiness | M | L | AEMO, Impacted Participants | Ongoing Industry Readiness Reporting shows that applicable MTP activities are running late resulting in MSATS standing data not being fully available prior to R2 post GS Rule commencement BAU standing data monitoring mechanisms between AEMO and participants UFE publication data from 5MS commcement indicates MSATS standing data is not fully available | Industry Readiness Reporting, Monitoring of UFE publication data after 5MS commencement and BAU standing data monitoring mechanisms | - Monitor standing data issues and execute updates ASAP - AEMO to provide support as required | A similar scenario of MSATS standing data not fully available at 5MS commencement will not affect operation of the NEM. Therefore no contingency response is expected for this scenario.
C6 | R17, R19 | Failure of B2B and/or B2M to process required volumes | Failure of B2B and/or B2M capability to process transaction volumes from 1 July 2021 | Production | H | L | AEMO, Impacted Participants | Production monitoring activities identify that transaction volumes are not being processed as required | AEMO and Participant BAU Monitoring | - Under standard operating processes, AEMO would raise an incident and then follow its incident management process. Market notifications would occur as appropriate.
C7 | R20 | AEMO MDM platform deployment delayed | Criteria not met to proceed with the deployment of the AEMO MDM Platform | Readiness | H | L | AEMO, Impacted Participants | AEMO milestones states that deployment/cutover has/will been delayed | Program Milestones and Industry Readiness Reporting | - Perform impact assessment and recommend preferred response e.g. alternative timings, assessment needs to consider materiality and duration of the delay and flow on consequences to participants being able to meet minimum criteria for 5MS/GS commencements and broader market - Implementing this contingency response could trigger other contingency scenarios (e.g. C1, C25) | - Outcome of assessment would be different if delay is pre 1/7/21 or post rule commencement
C8 | R20 | AEMO Settlements platform deployment delayed | Criteria not met to proceed with the deployment of the AEMO settlements platform | Readiness | H | L | AEMO, Impacted Participants | AEMO milestones states that deployment/cutover has been delayed | Program Milestones and Industry Readiness Reporting | - Perform impact assessment and recommend preferred response e.g. alternative timings, assessment needs to consider materiality and duration of the delay and flow on consequences to participants being able to meet minimum criteria for 5MS/GS commencements and broader market - Implementing this contingency response could trigger other contingency scenarios (e.g. C1, C25) | - Outcome of assessment would be different if delay is pre 1/7/21 or post rule commencement
C9 | R20 | AEMO Bidding and dispatch platform deployment delayed | Criteria not met to proceed with the deployment of the AEMO bidding and dispatch platform | Readiness | H | L | AEMO, Impacted Participants | AEMO milestones states that deployment/cutover has been delayed | Program Milestones and Industry Readiness Reporting | Perform impact assessment and recommend preferred response e.g. alternative timings, assessment needs to consider materiality and duration of the delay and flow on consequences to participants being able to meet minimum criteria for 5MS/GS commencements and broader market - Implementing this contingency response could trigger other contingency scenarios (e.g. C1, C25) | - Outcome of assessment would be different if delay is pre 1/7/21 or post rule commencement
C10 | R20 | AEMO MDM platform cutover failure | Cutover process and production validations not successfully completed for MDM platform deployment as required by Cutover plan. | Implementation | H | L | AEMO, Impacted Participants | AEMO milestones states that deployment/cutover has been delayed | Cutover plan | - Roll back release - Perform impact assessment and recommend preferred response e.g. alternative timings, assessment needs to consider materiality and duration of the delay and flow on consequences to participants being able to meet minimum criteria for 5MS/GS commencements and broader market. - Allow adequate time for testing.
C11 | R20 | AEMO Settlements platform cutover failure | Cutover process and production validations not successfully completed for settlements platform deployment | Implementation | H | L | AEMO, Impacted Participants | AEMO milestones states that deployment/cutover has been delayed | Cutover plan | - Roll back release - Perform impact assessment and recommend preferred response e.g. alternative timings, assessment needs to consider materiality and duration of the delay and flow on consequences to participants being able to meet minimmum criteria for 5MS/GS commencements and broader market. - Allow adequate time for testing.
C12 | R20 | AEMO Bidding and dispatch platform cutover failure | Cutover process and production validations not successfully completed for bidding and dispatch platform deployment | Implementation | H | L | AEMO, Impacted Participants | AEMO milestones states that deployment/cutover has been delayed | Cutover plan | - Roll back release - Perform impact assessment and recommend preferred response e.g. alternative timings, assessment needs to consider materiality and duration of the delay and flow on consequences to participants being able to meet minimmum criteria for 5MS/GS commencements and broader market. - Allow adequate time for testing.
C13 | R21 | AEMO MDM platform issues in production | Missing or broken MDM functionality in production | Production | M | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and participant BAU monitoring | - Under standard operating processes, AEMO would raise an incident and then follow its incident management process. Market notifications would occur as appropriate.
C14 | R21 | AEMO Settlements platform issues in production | Missing or broken settlements functionality in production | Production | M | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and participant BAU monitoring | - Under standard operating processes, AEMO would raise an incident and then follow its incident management process. Market notifications would occur as appropriate. Existing procedures would be applied as appropriate e.g. Settlement Estimations Policy, Settlement Revisions Policy | NEM settlements procedures and guides at: https://aemo.com.au/energy-systems/electricity/national-electricity-market-nem/market-operations/settlements-and-payments/settlements/procedures-and-guides
C15 | R21 | AEMO Bidding and dispatch platform issues in production | Missing or broken bidding or dispatch functionality in production | Production | M | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and participant BAU monitoring | - Under standard operating processes, AEMO would raise an incident and then follow its incident management process. Market notifications would occur as appropriate. If market suspension is required, the market suspension procedures would be applied. | Guide to Market Suspension in the NEM and associated procedures at: https://aemo.com.au/en/energy-systems/electricity/emergency-management/guide-to-market-suspension-in-the-nem
C16 | R21 | 5 minute bids not being accepted by AEMO | 5-minute bids from participants not able to be accepted by AEMO participants on bidding platform or web platform | Production | H | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and Participant BAU Monitoring | - During the transition window, if 5 min bids cannot be accepted, but 30 min bids can, AEMO may require participants to provide 30 minute bids. - If AEMO cannot receive 5 or 30 minute bids, the Market suspension procedures will be invoked | Guide to Market Suspension in the NEM and associated procedures at: https://aemo.com.au/en/energy-systems/electricity/emergency-management/guide-to-market-suspension-in-the-nem
C17 | R21 | Settlement invoice not being generated | Settlement invoices not being generated from rule commencement | Production | H | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and Participant BAU Monitoring | - Under standard operating processes, AEMO would raise an incident and then follow its incident management process. Market notifications would occur as appropriate. Existing procedures would be applied as appropriate e.g. Settlement Estimations Policy, Settlement Revisions Policy | NEM settlements procedures and guides at: https://aemo.com.au/energy-systems/electricity/national-electricity-market-nem/market-operations/settlements-and-payments/settlements/procedures-and-guides
C18 | R21 | Miscalculations of dispatch instructions | Miscalculations of dispatch instructions after dispatch platform upgrade | Production | H | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and Participant BAU Monitoring | - Under standard operating processes, AEMO would raise an incident and then follow its incident management process. Market notifications would occur as appropriate. If market suspension is required, the market suspension procedures would be applied. If settlement adjustments ar required, existing procedures would be applied as appropriate e.g. Settlement revisions policy | Guide to Market Suspension in the NEM and associated procedures at: https://aemo.com.au/en/energy-systems/electricity/emergency-management/guide-to-market-suspension-in-the-nem
C19 | R21 | Settlement invoices inaccuracies | Settlement invoices calculated after settlement platform upgrade reveal inaccuracies in calculation | Production | H | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and Participant BAU Monitoring | - Under standard operating processes, AEMO would raise an incident and then follow its incident management process. Market notifications would occur as appropriate. Existing procedures would be applied as appropriate e.g. Settlement Estimations Policy, Settlement Revisions Policy | NEM settlements procedures and guides at: https://aemo.com.au/energy-systems/electricity/national-electricity-market-nem/market-operations/settlements-and-payments/settlements/procedures-and-guides
C20 | R22 | AEMO MDM platform production failure | System / hardware failure of AEMO's MDM platform post implementation | Production | H | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and Participant BAU Monitoring | - Under standard operating processes, AEMO would raise an incident and then follow its incident management process. Market notifications would occur as appropriate.
C21 | R22 | AEMO Settlements platform production failure | System / hardware failure of AEMO's settlements platform post implementation | Production | H | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and Participant BAU Monitoring | - Under standard operating processes, AEMO would raise an incident and then follow its incident management process. Market notifications would occur as appropriate. Existing procedures would be applied as appropriate e.g. Settlement Estimations Policy, Settlement Revisions Policy | NEM settlements procedures and guides at: https://aemo.com.au/energy-systems/electricity/national-electricity-market-nem/market-operations/settlements-and-payments/settlements/procedures-and-guides
C22 | R22 | AEMO Bidding and dispatch platform production failure | System / hardware failure of AEMO's bidding and dispatch platform post implementation | Production | H | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and Participant BAU Monitoring | - Under standard operating processes, AEMO would raise an incident and then follow its incident management process. Market notifications would occur as appropriate. If market suspension is required, the market suspension procedures would be applied. | Guide to Market Suspension in the NEM and associated procedures at: https://aemo.com.au/en/energy-systems/electricity/emergency-management/guide-to-market-suspension-in-the-nem
C23 | R23 | Major event at scheduled system deployment | Major event (e.g. natural disaster, load shedding) occurs at time of scheduled system deployment | Implementation | H | L | AEMO, AEMC, All Participants | Major event occurs at time of system deployment | Cutover Plan and Escalation Process | - Perform impact assessment and recommend preferred response e.g. alternative timings, assessment needs to consider materiality and duration of the delay and flow on consequences to participants being able to meet minimum criteria for 5MS/GS commencements and broader market
C24 | R24 | Too few participants to complete Market Trials | Too few participants, or differentiation in participant types, to complete Market Trials | Implementation | H | L | AEMO, Impacted Participants | AEMO milestones states that Market Trials are at risk | Industry Readiness Reporting | - Escalate to PCF and Executive Forum - Reschedule Market Trial with available participants - Participants to consider bilateral testing
C25 | R11 | AEMO 'not ready' to operate | AEMO 'not ready' to operate within market conditions at rule commencement resulting in fundamental impact to ongoing NEM operations | Readiness | H | L | AEMO, Impacted Participants | Critical AEMO Milestones missed and not considered recoverable prior to rule commencement when assessed major checkpoint | Program Milestones and Industry Readiness Reporting | Establishment of extent of delay and industry consultation on appropriate response. Confirmation that impact of delay will result in fundamental market failure Development of Rule Change Proposal for AEMC consideration (AEMO).
C26 | R21 | Miscalculations of pre-dispatch and STPASA | Miscalculations of pre-dispatch and STPASA after dispatch platform upgrade | Production | M | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and Participant BAU Monitoring | - Under standard operating processes, AEMO would raise an incident and then follow its incident management process. Market notifications would occur as appropriate.

## Readiness Risk Contingencies
Industry Risk Ref | Risk Title | Risk Description | Contingency Scenario Ref | Contingency Scenario | Scenario Description | Scenario Category | Priority (H/M/L) | Likelihood (H/M/L) | Impacted Stakeholders | Triggers | Monitoring Mechanism | Response | Comments
R11 | The AEMO internal project is not ready for 5MS Go Live | AEMO may not be ready to deliver the full extent of the 5MS deliverables by Go Live, results in failure of Go Live for 5MS and GS Program | C25 | AEMO 'not ready' to operate | AEMO 'not ready' to operate within market conditions at rule commencement resulting in fundamental impact to ongoing NEM operations | Readiness | H | L | AEMO, Impacted Participants | Critical AEMO Milestones missed and not considered recoverable prior to rule commencement when assessed major checkpoint | Program Milestones and Industry Readiness Reporting | Establishment of extent of delay and industry consultation on appropriate response. Confirmation that impact of delay will result in fundamental market failure Development of Rule Change Proposal for AEMC consideration (AEMO).
R14 | Metering implementation activities affecting participant business functions during transitional period | Expectations and interpretation of transitional activities to implement metering procedure requirements may result in some participants being unable to effectively deliver business functions | C1 | Minimum criteria not met for 5MS/GS commencements | Minimum criteria (defined in Industry readiness contingency plan word document) not met for 5MS/GS commencements resulting in critical impact to NEM operations and/or material risk of market or power system failure | Readiness | H | M | AEMO, Impacted Participants | The following triggers may indicate that minimum criteria for 5MS/GS commencements may not be met: - Readiness reporting results, 7-8 months in advance of the commencement dates - Insufficient participants in industry testing/market trials - Unfavourable industry testing/market trial results | Industry Readiness Reporting | - MDPs to provide 5 minute subs until affected meters are compliant or - MDPs do not send through reads and AEMO profiled supported substitutes until affected meters are compliant - Escalate issue, recommend actions and seek guidance from the PCF and EF as appropriate
|  |  | C2 | Essential meter(s) not fully compliant at 5MS commencement | Essential meter(s) installation and reconfiguration not fully compliant at 5MS commencement | Readiness | H | M | AEMO, Impacted Participants | Final round of Industry Readiness Reporting (May 2021) shows that applicable MTP activities are running late resulting in a number of Essential meters not being fully compliant at 5MS Rule commencement | Industry Readiness Reporting | - MDPs to provide 5 minute subs until affected meters are compliant or - MDPs do not send through reads and AEMO profiled supported substitutes until affected meters are complaint - Escalate issue, recommend actions and seek guidance from the PCF and EF as appropriate
|  |  | C3 | 5-min Essential meter(s) metering data delivery issues | MDP(s) not providing 5-minute data for Essential meter(s) as required at 5MS commencement resulting in short term financial volatility | Readiness | H | M | AEMO, Impacted Participants | Ongoing monitoring of Industry Readiness Reporting shows that applicable MTP activities are running late resulting in 5min metering data not being provided for a number of Essential meters at 5MS Rule commencement MDP not suitably accredited by the defined dates outlined in the MSP Accreditation Update Plan | Industry Readiness Reporting (of Metering Transition Plan activities) | - Response dependent on the underlying issues (consider duration and materiality) - MDP to confirm rectification plan - BAU MDP processes, including manually loading data into MSATS or finding alternative pathways to MSATS using different sites - AEMO to generate subs at time of Settlement until issue resolved (BAU process) - AEMO and Participants to provide support as required (alternative mechanism to provide data) - Escalate issue, recommend actions and seek guidance from the PCF and EF as appropriate - As a last resort, MC to transfer NMIs to alternative MDP
|  |  | C4 | Metering Service Provider Participant(s) not suitably accredited at Rule commencement | MDP(s) or MP(s) accreditation not suitable at 5MS rule commencement | Readiness | H | L | AEMO, Impacted Participants | Ongoing monitoring of Industry Readiness Reporting shows that applicable MTP activities are running late resulting in an MDP or MP not being accredited at 5MS Rule commencement | Industry Readiness Reporting (of Metering Transition Plan activities) | - MC to transfer NMIs to accredited MDPs/MPs - AEMO and Participants to provide support as required - Escalate issue, recommend actions and seek guidance from the PCF and EF as appropriate | Trigger for type 4 and 4A and VIC AMI new and replacement metering requirements treated as BAU process Trigger for non-contestable unmetered loads is also treated as BAU process
|  |  | C5 | MSATS standing data not fully available at GS Rule commencement | Metering and MSATS standing data not fully available/updated at GS rule commencement (post revision 2) - leading to material settlement difference | Readiness | M | L | AEMO, Impacted Participants | Ongoing Industry Readiness Reporting shows that applicable MTP activities are running late resulting in MSATS standing data not being fully available prior to R2 post GS Rule commencement BAU standing data monitoring mechanisms between AEMO and participants UFE publication data from 5MS commencement indicates MSATS standing data is not fully available | Industry Readiness Reporting, Monitoring of UFE publication data after 5MS commencement and BAU standing data monitoring mechanisms | - Monitor standing data issues and execute updates ASAP - AEMO to provide support as required | A similar scenario of MSATS standing data not fully available at 5MS commencement will not affect operation of the NEM. Therefore no contingency response is expected for this scenario.
R15 | Potential impacts from AEMO accreditation resource and timing constraints | Resource and timing constraints for AEMO may result in delays to accreditation updates in timeframe required for transition activity | C1 | Minimum criteria not met for 5MS/GS commencements | Minimum criteria (defined in Industry readiness contingency plan word document) not met for 5MS/GS commencements resulting in critical impact to NEM operations and/or material risk of market or power system failure | Readiness | H | L | AEMO, Impacted Participants | The following triggers may indicate that minimum criteria for 5MS/GS commencements may not be met: - Readiness reporting results, 7-8 months in advance of the commencement dates - Insufficient participants in industry testing/market trials - Unfavourable industry testing/market trial results | Industry Readiness Reporting, Industry testing and Market trials | - Perform impact assessment, confirming risk of fundamental market failure and recommend preferred contingency response based on the physical and commercial market requirements - Where necessary, escalate issue and recommend actions to the PCF or EF - Submit rule change to AEMC (6 month process) where no other alternative approach exists
|  |  | C2 | Essential meter(s) not fully compliant at 5MS commencement | Essential meter(s) installation and reconfiguration not fully compliant at 5MS commencement | Readiness | H | M | AEMO, Impacted Participants | Final round of Industry Readiness Reporting (May 2021) shows that applicable MTP activities are running late resulting in a number of Essential meters not being fully compliant at 5MS Rule commencement | Industry Readiness Reporting | - MDPs to provide 5 minute subs until affected meters are compliant or - MDPs do not send through reads and AEMO profiled supported substitutes until affected meters are complaint - Escalate issue, recommend actions and seek guidance from the PCF and EF as appropriate
|  |  | C3 | 5-min Essential meter(s) metering data delivery issues | MDP(s) not providing 5-min data for Essential meter(s) as required at 5MS commencement resulting in short term financial volatility | Readiness | H | M | AEMO, Impacted Participants | Ongoing monitoring of Industry Readiness Reporting shows that applicable MTP activities are running late resulting in 5min metering data not being provided for a number of Essential meters at 5MS Rule commencement MDP not suitably accredited by the defined dates outlined in the MSP Accreditation Update Plan | Industry Readiness Reporting (of Metering Transition Plan activities) | - Response dependent on the underlying issues (consider duration and materiality) - MDP to confirm rectification plan - BAU MDP processes, including manually loading data into MSATS or finding alternative pathways to MSATS using different sites - AEMO to generate subs at time of Settlement until issue resolved (BAU process) - AEMO and Participants to provide support as required (alternative mechanism to provide data) - Escalate issue, recommend actions and seek guidance from the PCF and EF as appropriate - As a last resort, MC to transfer NMIs to alternative MDP
|  |  | C4 | Metering Service Provider Participant(s) not suitably accredited at Rule commencement | MDP(s) or MP(s) accreditation not suitable at 5MS rule commencement | Readiness | H | L | AEMO, Impacted Participants | Ongoing monitoring of Industry Readiness Reporting shows that applicable MTP activities are running late resulting in an MDP or MP not being accredited at 5MS Rule commencement | Industry Readiness Reporting (of Metering Transition Plan activities) | - MC to transfer NMIs to accredited MDPs/MPs - AEMO and Participants to provide support as required - Escalate issue, recommend actions and seek guidance from the PCF and EF as appropriate | Trigger for type 4 and 4A and VIC AMI new and replacement metering requirements treated as BAU process Trigger for non-contestable unmetered loads is also treated as BAU process
R16 | Potential impacts from MSP accreditation resource and timing constraints | Resource and timing constraints for MSP participants may result in delays to accreditation updates in timeframe required for transition activity | C1 | Minimum criteria not met for 5MS/GS commencements | Minimum criteria (defined in Industry readiness contingency plan word document) not met for 5MS/GS commencements resulting in critical impact to NEM operations and/or material risk of market or power system failure | Readiness | H | L | AEMO, Impacted Participants | The following triggers may indicate that minimum criteria for 5MS/GS commencements may not be met: - Readiness reporting results, 7-8 months in advance of the commencement dates - Insufficient participants in industry testing/market trials - Unfavourable industry testing/market trial results | Industry Readiness Reporting, Industry testing and Market trials | - Perform impact assessment, confirming risk of fundamental market failure and recommend preferred contingency response based on the physical and commercial market requirements - Where necessary, escalate issue and recommend actions to the PCF or EF - Submit rule change to AEMC (6 month process) where no other alternative approach exists
|  |  | C2 | Essential meter(s) not fully compliant at 5MS commencement | Essential meter(s) installation and reconfiguration not fully compliant at 5MS commencement | Readiness | H | M | AEMO, Impacted Participants | Final round of Industry Readiness Reporting (May 2021) shows that applicable MTP activities are running late resulting in a number of essential meters not being fully compliant at 5MS Rule commencement | Industry Readiness Reporting | - MDPs to provide 5 minute subs until affected meters are compliant or - MDPs do not send through reads and AEMO profiled supported substitutes until affected meters are complaint - Escalate issue, recommend actions and seek guidance from the PCF and EF as appropriate
|  |  | C3 | 5-min Essential meter(s) metering data delivery issues | MDP(s) not providing 5-minute data for Essential meter(s) as required at 5MS commencement resulting in short term financial volatility | Readiness | H | M | AEMO, Impacted Participants | Ongoing monitoring of Industry Readiness Reporting shows that applicable MTP activities are running late resulting in 5min metering data not being provided for a number of essential meters at 5MS Rule commencement MDP not suitably accredited by the defined dates outlined in the MSP Accreditation Update Plan | Industry Readiness Reporting (of Metering Transition Plan activities) | - Response dependent on the underlying issues (consider duration and materiality) - MDP to confirm rectification plan - BAU MDP processes, including manually loading data into MSATS or finding alternative pathways to MSATS using different sites - AEMO to generate subs at time of Settlement until issue resolved (BAU process) - AEMO and Participants to provide support as required (alternative mechanism to provide data) - Escalate issue, recommend actions and seek guidance from the PCF and EF as appropriate - As a last resort, MC to transfer NMIs to alternative MDP
|  |  | C4 | Metering Service Provider Participant(s) not suitably accredited at Rule commencement | MDP(s) or MP(s) accreditation not suitable at 5MS rule commencement | Readiness | H | L | AEMO, Impacted Participants | Ongoing monitoring of Industry Readiness Reporting shows that applicable MTP activities are running late resulting in an MDP or MP not being accredited at 5MS Rule commencement | Industry Readiness Reporting (of Metering Transition Plan activities) | - MC to transfer NMIs to accredited MDPs/MPs - AEMO and Participants to provide support as required - Escalate issue, recommend actions and seek guidance from the PCF and EF as appropriate | Trigger for type 4 and 4A and VIC AMI new and replacement metering requirements treated as BAU process Trigger for non-contestable unmetered loads is also treated as BAU process
R17 | Industry 'big bang' approach | Potential for a number of Metering and/or Retail participants to go-live on 1 July 2021, sending 5MS compliant flows for the first time on that day, may result in an increase of the potential of multiple failures across B2M and B2B networks. | C1 | Minimum criteria not met for 5MS/GS commencements | Minimum criteria (defined in Industry readiness contingency plan word document) not met for 5MS/GS commencements resulting in critical impact to NEM operations and/or material risk of market or power system failure | Readiness | H | L | AEMO, Impacted Participants | The following triggers may indicate that minimum criteria for 5MS/GS commencements may not be met: - Readiness reporting results, 7-8 months in advance of the commencement dates - Insufficient participants in industry testing/market trials - Unfavourable industry testing/market trial results | Industry Readiness Reporting, Industry testing and Market trials | - Perform impact assessment, confirming risk of fundamental market failure and recommend preferred contingency response based on the physical and commercial market requirements - Where necessary, escalate issue and recommend actions to the PCF or EF - Submit rule change to AEMC (6 month process) where no other alternative approach exists
|  |  | C3 | 5-min Essential meter(s) metering data delivery issues | MDP(s) not providing 5-minute data for Essential meter(s) as required at 5MS commencement resulting in short term financial volatility | Readiness | H | M | AEMO, Impacted Participants | Ongoing monitoring of Industry Readiness Reporting shows that applicable MTP activities are running late resulting in 5min metering data not being provided for a number of essential meters at 5MS Rule commencement MDP not suitably accredited by the defined dates outlined in the MSP Accreditation Update Plan | Industry Readiness Reporting (of Metering Transition Plan activities) | - Response dependent on the underlying issues (consider duration and materiality) - MDP to confirm rectification plan - BAU MDP processes, including manually loading data into MSATS or finding alternative pathways to MSATS using different sites - AEMO to generate subs at time of Settlement until issue resolved (BAU process) - AEMO and Participants to provide support as required (alternative mechanism to provide data) - Escalate issue, recommend actions and seek guidance from the PCF and EF as appropriate - As a last resort, MC to transfer NMIs to alternative MDP
|  |  | C6 | Failure of B2B and/or B2M to process required volumes | Failure of B2B and/or B2M capability to process transaction volumes from 1 July 2021 | Production | H | L | AEMO, Impacted Participants | Production monitoring activities identify that transaction volumes are not being processed as required | AEMO and Participant BAU Monitoring | - Follow existing BAU contingency processes and procedures
R19 | Risk of a critical mass of participants not being ‘ready’ at identified critical path milestones | Critical mass of participants fail to meet expected industry Readiness critical path milestones, including not having adequate systems to undertake market trials and testing, resulting in failure to be ready for go-live. | C3 | 5min Essential meter(s) metering data delivery issues | MDP(s) not providing 5-min data for Essential meter(s) as required at 5MS commencement resulting in short term financial volatility | Readiness | H | M | AEMO, Impacted Participants | Ongoing monitoring of Industry Readiness Reporting shows that applicable MTP activities are running late resulting in 5min metering data not being provided for a number of essential meters at 5MS Rule commencement MDP not suitably accredited by the defined dates outlined in the MSP Accreditation Update Plan | Industry Readiness Reporting (of Metering Transition Plan activities) | - Response dependent on the underlying issues (consider duration and materiality) - MDP to confirm rectification plan - BAU MDP processes, including manually loading data into MSATS or finding alternative pathways to MSATS using different sites - AEMO to generate subs at time of Settlement until issue resolved (BAU process) - AEMO and Participants to provide support as required (alternative mechanism to provide data) - Escalate issue, recommend actions and seek guidance from the PCF and EF as appropriate - As a last resort, MC to transfer NMIs to alternative MDP
|  |  | C4 | Metering Service Provider Participant(s) not suitably accredited at Rule commencement | MDP(s) or MP(s) accreditation not suitable at 5MS rule commencement | Readiness | H | L | AEMO, Impacted Participants | Ongoing monitoring of Industry Readiness Reporting shows that applicable MTP activities are running late resulting in an MDP or MP not being accredited at 5MS Rule commencement | Industry Readiness Reporting (of Metering Transition Plan activities) | - MC to transfer NMIs to accredited MDPs/MPs - AEMO and Participants to provide support as required - Escalate issue, recommend actions and seek guidance from the PCF and EF as appropriate | Trigger for type 4 and 4A and VIC AMI new and replacement metering requirements treated as BAU process Trigger for non-contestable unmetered loads is also treated as BAU process
|  |  | C5 | MSATS standing data not fully available at GS Rule commencement | Metering and MSATS standing data not fully available/updated at GS rule commencement (post revision 2) - leading to material settlement difference | Readiness | M | L | AEMO, Impacted Participants | Ongoing Industry Readiness Reporting shows that applicable MTP activities are running late resulting in MSATS standing data not being fully available prior to R2 post GS Rule commencement BAU standing data monitoring mechanisms between AEMO and participants UFE publication data from 5MS commencement indicates MSATS standing data is not fully available | Industry Readiness Reporting, Monitoring of UFE publication data after 5MS commencement and BAU standing data monitoring mechanisms | - Monitor standing data issues and execute updates ASAP - AEMO to provide support as required | A similar scenario of MSATS standing data not fully available at 5MS commencement will not affect operation of the NEM. Therefore no contingency response is expected for this scenario.
|  |  | C6 | Failure of B2B and/or B2M to process required volumes | Failure of B2B and/or B2M capability to process transaction volumes from 1 July 2021 | Production | H | L | AEMO, Impacted Participants | Production monitoring activities identify that transaction volumes are not being processed as required | AEMO and Participant BAU Monitoring | - Follow existing BAU contingency processes and procedures
R20 | Risk of cutover failure | Participant impact of AEMO systems not going live as scheduled within the planned cutover window (e.g. MDM cutover) | C7 | AEMO MDM platform deployment delayed | Criteria not met to proceed with the deployment of the AEMO MDM Platform | Readiness | H | L | AEMO, Impacted Participants | AEMO milestones states that deployment/cutover has/will been delayed | Program Milestones and Industry Readiness Reporting | - Perform impact assessment and recommend preferred response e.g. alternative timings, assessment needs to consider materiality and duration of the delay and flow on consequences to participants being able to meet minimum criteria for 5MS/GS commencements and broader market - Implementing this contingency response could trigger other contingency scenarios (e.g. C1, C25)
|  |  | C8 | AEMO Settlements platform deployment delayed | Criteria not met to proceed with the deployment of the AEMO settlements platform | Readiness | H | L | AEMO, Impacted Participants | AEMO milestones states that deployment/cutover has been delayed | Program Milestones and Industry Readiness Reporting | - Perform impact assessment and recommend preferred response e.g. alternative timings, assessment needs to consider materiality and duration of the delay and flow on consequences to participants being able to meet minimum criteria for 5MS/GS commencements and broader market - Implementing this contingency response could trigger other contingency scenarios (e.g. C1, C25)
|  |  | C9 | AEMO Bidding and dispatch platform deployment delayed | Criteria not met to proceed with the deployment of the AEMO dispatch platform | Readiness | H | L | AEMO, Impacted Participants | AEMO milestones states that deployment/cutover has been delayed | Program Milestones and Industry Readiness Reporting | - Perform impact assessment and recommend preferred response e.g. alternative timings, assessment needs to consider materiality and duration of the delay and flow on consequences to participants being able to meet minimum criteria for 5MS/GS commencements and broader market - Implementing this contingency response could trigger other contingency scenarios (e.g. C1, C25)
|  |  | C10 | AEMO MDM platform cutover failure | Cutover process and production validations not successfully completed for MDM platform deployment as required by Cutover plan. | Implementation | H | L | AEMO, Impacted Participants | AEMO milestones states that deployment/cutover has been delayed | Cutover plan | - Roll back release - Perform impact assessment and recommend preferred response e.g. alternative timings, assessment needs to consider materiality and duration of the delay and flow on consequences to participants being able to meet minimmum criteria for 5MS/GS commencements and broader market. - Allow adequate time for testing.
|  |  | C11 | AEMO Settlements platform cutover failure | Cutover process and production validations not successfully completed for settlements platform deployment | Implementation | H | L | AEMO, Impacted Participants | AEMO milestones states that deployment/cutover has been delayed | Cutover plan | - Roll back release - Perform impact assessment and recommend preferred response e.g. alternative timings, assessment needs to consider materiality and duration of the delay and flow on consequences to participants being able to meet minimmum criteria for 5MS/GS commencements and broader market. - Allow adequate time for testing.
|  |  | C12 | AEMO Bidding and dispatch platform cutover failure | Cutover process and production validations not successfully completed for dispatch platform deployment | Implementation | H | L | AEMO, Impacted Participants | AEMO milestones states that deployment/cutover has been delayed | Cutover plan | - Roll back release - Perform impact assessment and recommend preferred response e.g. alternative timings, assessment needs to consider materiality and duration of the delay and flow on consequences to participants being able to meet minimmum criteria for 5MS/GS commencements and broader market. - Allow adequate time for testing.
R21 | Risk of degraded operational performance at go-live | Risk of degraded operational performance at go-live | C13 | AEMO MDM platform issues in production | Missing or broken MDM functionality in production | Production | M | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and participant BAU monitoring | - Follow existing BAU defect processes, market notifications, including workarounds
|  |  | C14 | AEMO Settlements platform issues in production | Missing or broken settlements functionality in production | Production | M | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and participant BAU monitoring | - Follow existing BAU defect processes, market notifications, including workarounds
|  |  | C15 | AEMO Bidding and dispatch platform issues in production | Missing or broken dispatch functionality in production | Production | M | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and participant BAU monitoring | - Follow existing BAU defect processes, market notifications, including workarounds
|  |  | C16 | 5 minute bids not being accepted by AEMO | 5-minute bids from participants not able to be accepted by AEMO participants on bidding platform or web platform | Production | H | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and Participant BAU Monitoring | - Implement Market suspension procedures if AEMO is unable to operate the spot market in accordance with the provision of the NER
|  |  | C17 | Settlement invoice not being generated | Settlement invoices not being generated from rule commencement | Production | H | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and Participant BAU Monitoring | - Follow existing BAU contingency processes and procedures - An incident would be raised and then incident mgt process would be followed e.g. market notifications
|  |  | C18 | Miscalculations of dispatch instructions | Miscalculations of dispatch instructions after dispatch platform upgrade | Production | H | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and Participant BAU Monitoring | - Implement Market suspension procedures if AEMO is unable to operate the spot market in accordance with the provision of the NER - An incident would be raised and then incident mgt process would be followed e.g. market notifications
|  |  | C19 | Settlement invoices inaccuracies | Settlement invoices calculated after settlement platform upgrade reveal inaccuracies in calculation | Production | H | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and Participant BAU Monitoring | - Follow existing BAU contingency processes and procedures including settlements estimation - An incident would be raised and then incident mgt process would be followed e.g. market notifications
|  |  | C26 | Miscalculations of pre-dispatch and STPASA | Miscalculations of pre-dispatch and STPASA after dispatch platform upgrade | Production | M | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and Participant BAU Monitoring | - Follow existing BAU contingency processes and procedures - An incident would be raised and then incident mgt process would be followed e.g. market notifications
R22 | Introduction of 5MS capability and architecture increases risk of system unavailability post cutover | There is a risk that subsequent to the deployment or upgrade the market system becomes unavailable for an extended period due to malfunction | C20 | AEMO MDM platform production failure | System / hardware failure of AEMO's MDM platform post implementation | Production | H | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and Participant BAU Monitoring | - Follow existing BAU contingency processes and procedures including settlements estimation - An incident would be raised and then incident mgt process would be followed e.g. market notifications
|  |  | C21 | AEMO Settlements platform production failure | System / hardware failure of AEMO's settlements platform post implementation | Production | H | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and Participant BAU Monitoring | - Follow existing BAU contingency processes and procedures including settlements estimation - An incident would be raised and then incident mgt process would be followed e.g. market notifications
|  |  | C22 | AEMO Bidding and dispatch platform production failure | System / hardware failure of AEMO's dispatch platform post implementation | Production | H | L | AEMO, Impacted Participants | Issues identified in Production | AEMO and Participant BAU Monitoring | - Implement Market suspension procedures if market is down for greater than 30 mins - An incident would be raised and then incident mgt process would be followed e.g. market notifications
R23 | Major event occurs at cutover | Risk that a major market event (e.g. load shedding) occurs at timeframe scheduled for go-live resulting in increased risk or impact to planned activity | C23 | Major event at scheduled system deployment | Major event (e.g. natural disaster, load shedding) occurs at time of scheduled system deployment | Implementation | H | L | AEMO, AEMC, All Participants | Major event occurs at time of system deployment | Cutover Plan and Escalation Process | - Perform impact assessment and recommend preferred response e.g. alternative timings, assessment needs to consider materiality and duration of the delay and flow on consequences to the critical mass of Participants and broader market
R24 | Not enough participants for Market Trials | Risk that there is not enough critical mass of participants, or differentiation in participant types, to complete Market Trials | C24 | Not enough critical mass of participants to complete Market Trials | Not enough critical mass of participants, or differentiation in participant types, to complete Market Trials | Implementation | H | L | AEMO, Impacted Participants | AEMO milestones states that Market Trials are at risk | Industry Readiness Reporting | - Escalate to PCF and Executive Forum - Reschedule Market Trial with available participants - Participants to consider bilateral testing

## Sheet1 (hidden)
H
M
L