## Guide
Description of Metering transition plan elements
Metering transition plan element (MTP tab columns) | Purpose
CATEGORY | High level groupings for metering transition activities
SID | Indicates the unique sub-category ID
SUB-CATEGORY | Groups a set of related metering transition activities (e.g. Type 7 metering installations) within a category
AID | Indicates the unique activity ID
ACTIVITY | Describes the Metering transition activity
ASSUMPTIONS | Lists any assumptions related to the activity
RESPONSIBILITY | Assigns leadership and responsibility of the metering transition activity to a specific participant type
DEPENDENCIES | Lists any dependencies related to the activity
VOLUME/SIZE CONSIDERATIONS | Provides an indication of volume/size implications of the activity
DIRECTLY AFFECTED PARTIES | Lists out parties that are directly involved in executing the activity
TRANSITION START DATE | Lists the transition start date for this activity. When no transition start date is specified for an activity, participants may commence the transition at any time prior to the transition end date for that activity.
TRANSITION END DATE | Lists the transition end date of this activity. It is expected that all relevant participants have completed the activity by this date.
RULE / PROCEDURE TIMING | Lists the commencement date of the 5MS or GS rule requirement that the activity supports
TRANSITION OBJECTIVE / OUTCOME | Outlines the objective of the transition activity
COMMENTS (by AEMO or from TFG) | Lists any comments made by AEMO or the TFG
NMI classification code changes to support UFE calculation by 1 July 2021
NMI Classification Code | Description
BULK | Connection point where a transmission network connects to a distribution network (also termed 'Bulk Supply Point’)
DWHOLSAL | Distribution network connection point where energy is directly purchased from the spot market by a Market Customer
NCONUML | Non-contestable unmetered load
NREG | Connection point associated with a non-registered embedded generator, i.e. a generating unit that is not classified by a Market Generator, but may be classified by a Small Generation Aggregator as a market generating unit.
WHOLESAL | Transmission network connection point where energy is directly purchased from the spot market by a Market Customer
XBOUNDRY | Connection point where a distribution network connects to another to distribution network

## Version
VERSION CONTROL
|  |  | RWG | 5MS/GS Readiness working group
|  |  | TFG | 5MS/GS Transition focus group
| VERSION | RELEASE DATE | CHANGES
| 0.1 | 2019-11-29 |  | Draft released to the 5MS/GS RWG and TFGfor comment
| 1 | 2020-02-07 |  | Final document published, considers feedback from RWG and TFG
| 1.1 | 2020-03-10 | S12 | Clarifications to activity (A31), responsibilities, directly affected parties, transition start and end dates
|  |  | A120A | Additional activity to clarify details of VIC TUOS metering data delivery to AEMO
New column ("Approach") added at the request of the TFG
|  |  | A32 A37 A42 A47 A53 A59 A65 A71 A84 A88 | Approach to determining agreements added
|  |  | A52 A58 A64 A70 A76 | Approach to roll-out plans added
|  |  | A116 | Approach to updating LR and FRMP to GLOPOOL for existing NMIs added
|  |  | A117 | Approach to activating tier 1 basic datastreams added
| 1.2 | 2020-03-26 | A36 A40 A45 A51 A57 A63 A69 A75 A81 | Updated Register level datastreams transition start date to align to the transition start date of AEMO being able to receive MDFF (1 Feb 2021)
|  |  | S21 | Removed SC as is now considered non-applicable
|  |  | S40 A36a A40a A45a A57a A63a A69a A75a A81a | Removed S40 and added associated activity at the Meter Type level instead
|  |  | A98a | Added 'Provide AEMO indicative NCUL NMI list' to S27
|  |  | S27a | Added subcategory regarding SAPN's conversion of the one 'SASCALE' NMI to individual controlled load NMIs
|  |  | A54 A56 A60 A62 A66 A68 | Updated Transition End Date to 30 Nov 2022 to better align to 5MS Rule requirements
| 1.3 | 2020-04-01 | A30 A35 A36 A40 A41 A45 A46 A50 A51 A56 A57 A62 A63 A68 A69 A74 A75 A86 A92 A94 A95 A96 A97 A99 A100 A101 A104 A105 A119 A120 | Updates as a consequence of the MDM go-live date shfting to 9 March 2020
|  |  | A36a A40a A45a | Update to Transition End Date to align to the Procedure effective date
| 1.4 | 2020-05-01 | A83a A89a | Activity added: “RegisterID to Suffix alignment” for Type 7 and NCONUML installations Activity added: Provide AEMO with NMI lists associated with each NCONUML profile/algorithm
| 1.5 | 2020-07-01 | Various | Updated to reflect AEMC 3mth deferral of 5MS and GS Commencement Dates New activities added to confirm requirement to proivde progress and updates re the installation and reconfiguration of meters rollout plans every 2mths New activities added to confirm requirement to proivde progress and updates to 5min meter data delivery rollout plans every 3mths CATS Notification comments added to the 'VOLUME/SIZE CONSIDERATIONS' column
| 1.6 | 2020-12-01 | Various | Updates to various activity 'Comments', including: the completion of the delivery of initial rollout plans from MP/MCs and MDPs, outcomes of the Metering ICF consultation final detrmination re RegisterID to Suffix requirements and clarification of DNSP and ENM update requirements re NREG NCC
| 1.7 | 2021-01-01 | Various | Updates include: - Changes to various activities transition start and end dates due to the change in AEMO's Retail Solution go-live date - Changes to activity decriptions and comments as approved by the RWG - Activities being marked as Completed as the transiton end dates have lapsed
| 1.9 | 2021-05-01 | Various | Updates include: - Additional activities added (A95a, A97a, A97b and A97c)) supporting cross boundary supplies - Activities being marked as Completed as the transiton end dates have lapsed - Transition Start Dates changed, as required, to reflect AEMO's new Retail solution go-live date of 21 June 2021

## MTP
5MS & GS METERING TRANSITION PLAN |  |  |  | 2021-05-01
CATEGORY | SID | SUB-CATEGORY | AID | ACTIVITY | APPROACH | ASSUMPTIONS | RESPONSIBILITY | DEPENDENCIES | VOLUME/SIZE CONSIDERATIONS | DIRECTLY AFFECTED PARTIES | TRANSITION START DATE | TRANSITION END DATE | RULE / PROCEDURE TIMING | TRANSITION OBJECTIVE / OUTCOME | COMMENTS (by AEMO or from TFG)
METER INSTALLATION AND RECONFIGURATION
| S01 | BULK/Wholesale Meters | A1 | Identify which meters need replacing or reconfiguring (specify any sites that are deemed high risk due to no access or any other risk that may not enable reconfiguration/risk and provide associated treatment) |  |  | MP |  |  | MC | At the discretion of the Participant | 2020-03-31 | N/A | Wholesale meters requiring replacement or reconfiguration identified | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A2 | Initial assessment of whether data storage exemptions may be required |  |  | MP |  |  | AEMO | At the discretion of the Participant | 2020-03-31 | N/A | Initial assessment of potential data storage exemptions completed | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A3 | Provide visibility of approach / timeframe for required meter replacement or reconfiguration |  |  | MC |  |  | AEMO, MP | At the discretion of the Participant | 2020-03-31 | N/A | Approach and timeframes visible to AEMO | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A3a | Provide progress and amendments to forward plans to AEMO every 2mths |  |  | MC |  |  | AEMO, MP | 2020-08-15 | 2021-09-30 |  | Approach and timeframes visible to AEMO | Rollout plans to include all type 1-3, subset of 4, type 7 and Cross Boundary meters (Known) meters
|  |  | A4 | Install or reconfigure meters as required |  |  | MP | S41 |  | MC, MDP, AEMO | At the discretion of the Participant | 2021-07-31 | By 1 Oct 2021 | Wholesale meters 5min compliant
|  |  | A4a | Update Meter Read Type code with RWDA |  |  | MP |  | Generation of CR3xxx transactions to update Meter Read Type code Inclusion in overall CATS Notification Strategy required | AEMO, MDP | 2021-05-01 | 2021-07-31 | By 1 Oct 2021 | To communicate which meters are 5min capable | New activity added (v1.5)
|  |  | A5 | Apply for data storage exemptions as required |  |  | MP |  |  | AEMO | At the discretion of the Participant | 2021-07-31 | By 1 Oct 2021 | Data storage exemptions submitted and assessed
| S02 | Type 1-3 meters | A6 | Identify which meters need replacing or reconfiguring (specify any sites that are deemed high risk due to no access or any other risk that may not enable reconfiguration/risk and provide associated treatment) |  |  | MP |  |  | MC | At the discretion of the Participant | 2020-03-31 | N/A | Type 1-3 meters requiring replacement or reconfiguration identified | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A7 | Initial assessment of whether data storage exemptions may be required |  |  | MP |  |  | AEMO | At the discretion of the Participant | 2020-03-31 | N/A | Initial assessment of potential data storage exemptions completed | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A8 | Provide visibility of approach / timeframe for required meter replacement or reconfiguration |  |  | MC |  |  | AEMO, MP | At the discretion of the Participant | 2020-03-31 | N/A | Approach and timeframes visible to AEMO | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A8a | Provide progress and amendments to forward plans to AEMO every 2mths |  |  | MC |  |  | AEMO, MP | 2020-08-15 | 2021-09-30 |  | Approach and timeframes visible to AEMO | Rollout plans to include all type 1-3, subset of 4, type 7 and Cross Boundary meters (Known) meters
|  |  | A9 | Install or reconfigure meters as required |  |  | MP | S41 |  | MC, MDP, AEMO | At the discretion of the Participant | 2021-07-31 | By 1 Oct 2021 | Type 1-3 meters 5min compliant
|  |  | A9a | Update Meter Read Type code with RWDA |  |  | MP |  | Generation of CR3xxx transactions to update Meter Read Type code Inclusion in overall CATS Notification Strategy required | AEMO, MDP | 2021-05-01 | 2021-07-31 | By 1 Oct 2021 | To communicate which meters are 5min capable | New activity added (v1.5)
|  |  | A10 | Apply for data storage exemptions as required |  |  | MP |  |  | AEMO | At the discretion of the Participant | 2021-07-31 | By 1 Oct 2021 | Data storage exemptions submitted and assessed
| S03 | Subset of type 4 meters - TNI, Market Generator or SGA | A11 | Identify which meters need replacing or reconfiguring (specify any sites that are deemed high risk due to no access or any other risk that may not enable reconfiguration/risk and provide associated treatment) |  |  | MP |  |  | MC, SGA | At the discretion of the Participant | 2020-03-31 | N/A | Subset of type 4 meters requiring replacement or reconfiguration identified | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A12 | Initial assessment of whether data storage exemptions may be required |  |  | MP |  |  | AEMO | At the discretion of the Participant | 2020-03-31 | N/A | Initial assessment of potential data storage exemptions completed | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A13 | Provide visibility of approach / timeframe for required meter replacement or reconfiguration |  |  | MC |  |  | AEMO, MP | At the discretion of the Participant | 2020-03-31 | N/A | Approach and timeframes visible to AEMO | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A13a | Provide progress and amendments to forward plans to AEMO every 2mths |  |  | MC |  |  | AEMO, MP | 2020-08-15 | 2021-09-30 |  | Approach and timeframes visible to AEMO | Rollout plans to include all type 1-3, subset of 4, type 7 and Cross Boundary meters (Known) meters
|  |  | A14 | Install or reconfigure meters as required |  |  | MP | S41 |  | MC, MDP, AEMO | At the discretion of the Participant | 2021-07-31 | By 1 Oct 2021 | Subset of type 4 meters 5min compliant
|  |  | A14a | Update Meter Read Type code with RWDA |  |  | MP |  | Generation of CR3xxx transactions to update Meter Read Type code Inclusion in overall CATS Notification Strategy required | AEMO, MDP | 2021-05-01 | 2021-07-31 | By 1 Oct 2021 | To communicate which meters are 5min capable | New activity added (v1.5)
|  |  | A15 | Apply for data storage exemptions as required |  |  | MP |  |  | AEMO | At the discretion of the Participant | 2021-07-31 | By 1 Oct 2021 | Data storage exemptions submitted and assessed
| S04 | Cross Boundary meters (Known) | A16 | Identify which meters need replacing or reconfiguring (specify any sites that are deemed high risk due to no access or any other risk that may not enable reconfiguration/risk and provide associated treatment) |  |  | MP |  |  | MC, MP, LNSP | At the discretion of the Participant | 2020-03-31 | N/A | Cross boundary meters which need to be installed, replaced or reconfigured identified
|  |  | A17 | Determine and engage Metering Coordinator (after Global Settlement market commencement on 1 May 2022) |  |  | LNSP |  |  | MC, LNSP | At the discretion of the Participant | 2021-09-30 | By 1 Oct 2021 | Ensure that a MC is appointed for cross boundary NMIs after Global Settlements commencement
|  |  | A18 | Initial assessment of whether data storage exemptions may be required |  |  | MP |  |  | AEMO | At the discretion of the Participant | 2020-03-31 | N/A | Initial assessment of potential data storage exemptions completed | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A19 | Provide visibility of approach / timeframe for required meter replacement or reconfiguration |  |  | MC |  |  | AEMO, MP | At the discretion of the Participant | 2020-03-31 | N/A | Approach and timeframes visible to AEMO | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A19a | Provide progress and amendments to forward plans to AEMO every 2mths |  |  | MC |  |  | AEMO, MP | 2020-08-15 | 2021-09-30 |  | Approach and timeframes visible to AEMO | Rollout plans to include all type 1-3, subset of 4, type 7 and Cross Boundary meters (Known) meters
|  |  | A20 | Install or reconfigure meters as required |  |  | MP | S41 |  | MC, MDP, AEMO | At the discretion of the Participant | 2021-07-31 | By 1 Oct 2021 | All applicable cross boundary meters 5min compliant
|  |  | A20a | Update Meter Read Type code with RWDA |  |  | MP |  | Generation of CR3xxx transactions to update Meter Read Type code Inclusion in overall CATS Notification Strategy required | AEMO, MDP | 2021-05-01 | 2021-07-31 | By 1 Oct 2021 | To communicate which meters are 5min capable | New activity added (v1.5)
|  |  | A21 | Apply for data storage exemptions as required |  |  | MP |  |  | AEMO | At the discretion of the Participant | 2021-07-31 | By 1 Oct 2021 | Data storage exemptions submitted and assessed
| S05 | Cross Boundary meters (Unknown) | A22 | Identify which meters need to be installed, replaced or reconfigured |  |  | MP |  |  | MC, MP, LNSP | At the discretion of the Participant | 2020-06-30 | N/A | Cross boundary meters which need to be installed, replaced or reconfigured identified | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A23 | Provide visibility of approach / timeframe for required meter replacement or reconfiguration |  |  | MC |  |  | AEMO, MP | At the discretion of the Participant | 2021-03-31 | N/A | Approach and timeframes visible to AEMO
|  |  | A24 | Install or reconfigure meters as required |  |  | MP | S41 |  | MC, MDP, AEMO | At the discretion of the Participant | 2021-09-30 | By 1 Oct 2021 | All applicable cross boundary meters 5min compliant
| S06 | New and replacement Type 4 | A25 | Install 5-minute capable meters as required (BAU) |  |  | MP | S41, S42 |  | MP, MDP, Retailer LNSP, Affected Customer, AEMO | 2018-12-01 | N/A | From 1 Dec 2018
|  |  | A25a | Update Meter Read Type code with RWDA |  |  | MP |  | Generation of CR3xxx transactions to update Meter Read Type code Inclusion in overall CATS Notification Strategy required | AEMO, MDP | 2021-10-01 | 2022-11-30 | By 1 Oct 2021 | To communicate which meters are 5min capable | Transition period approved by AEMO Feb 2021 to allow Tranche 2 meters to be updated from 1 Oct 2021 to 30 Nov 2022
| S07 | New and replacement Type 4A | A26 | Install 5-minute capable meters as required (BAU) |  |  | MP | S41, S42 |  | MP, MDP, Retailer NSP, Affected Customer, AEMO | 2019-12-01 | N/A | From 1 Dec 2019
|  |  | A26a | Update Meter Read Type code with RWDA |  |  | MP |  | Generation of CR3xxx transactions to update Meter Read Type code Inclusion in overall CATS Notification Strategy required | AEMO, MDP | 2021-10-01 | 2022-11-30 | By 1 Oct 2021 | To communicate which meters are 5min capable | Transition period approved by AEMO Feb 2021 to allow Tranche 2 meters to be updated from 1 Oct 2021 to 30 Nov 2022
| S08 | New and replacement VIC AMI meters | A27 | Install 5-minute capable meters as required (BAU) |  |  | MP | S41, S42 |  | MP, MDP, Retailer NSP, Affected Customer, AEMO | 2018-12-01 | N/A | From 1 Dec 2018
|  |  | A27a | Update Meter Read Type code with RWDA |  |  | MP |  | Generation of CR3xxx transactions to update Meter Read Type code Inclusion in overall CATS Notification Strategy required | AEMO, MDP | 2021-10-01 | 2022-11-30 | By 1 Oct 2021 | To communicate which meters are 5min capable | Transition period approved by AEMO Feb 2021 to allow Tranche 2 meters to be updated from 1 Oct 2021 to 30 Nov 2022
| S09 | New and replacement SAMPLE Meters | A28 | Install 5-minute capable meters as required (BAU) |  |  | MP | S41, S42 |  | MP, MDP, Retailer NSP, Affected Customer, AEMO | 2018-12-01 | N/A | From 1 Dec 2018
|  |  | A28a | Update Meter Read Type code with RWDA |  |  | MP |  | Generation of CR3xxx transactions to update Meter Read Type code Inclusion in overall CATS Notification Strategy required | AEMO, MDP | 2021-10-01 | 2022-11-30 | By 1 Oct 2021 | To communicate which meters are 5min capable | Transition period approved by AEMO Feb 2021 to allow Tranche 2 meters to be updated from 1 Oct 2021 to 30 Nov 2022
| S11 | SCADA Data | A30 | Creation of 5 minute metering data based on SCADA data |  |  | AEMO |  |  | AEMO, MDP | 2021-04-01 | 2021-10-01 | By 1 Oct 2021
| S12 | Special Site | A31 | For any registered ‘Special Site’ (as defined in the ‘Special Sites and Technology Related conditions within the National Electricity Market Version 1.2) or any Logical NMI, update and distribute algorithms adjusted for introduction of 5 minute interval length to AEMO, FRMP and LNSP for approval. |  |  | MC | n/a |  | FRMP, LNSP, AEMO, MP, MDP | At the discretion of participant | 2021-08-31 | By 1 Oct 2021 | For any Registered ‘Special Site’, MDPs accurately deliver approved and adjusted meter data with consideration to meter data recorded in 5 minute intervals
METER DATA DELIVERY
| S13 | BULK/Wholesale Meters | A32 | Agreement to allow the delivery of 5min metering data pre 1 Oct 2021 between NSP, Retailer, MDP and AEMO | Participants to seek Legal advice as required in relation to NER 7.10.5. Participants to engage other Participants early to discuss the potential delivery of 5-min metering data pre-1 Oct 2021. Participants to advise AEMO when they believe they will deliver or receive 5-min metering data. |  | MDP | S01, S43 |  | NSP, FRMP, LR, MDP, MP, AEMO | At the discretion of the Applicable Participants | 2021-05-31 | By 1 Oct 2021 | Applicable agreements in place to enable MDPs to deliver 5min metering data to Participants to support five-minute settlement | MP to provide confirmation of which meters can be included in an agreement Should a NMI churn to a Retailer who does not have an agreement to receive 5min data, an agreement would need to be established or the MDP must deliver 30min data.
|  |  | A32a | Provide datastream conversion plans to convert Net datastreams to register level to AEMO every 2mths |  |  | MDP |  |  | AEMO, MP | 2021-03-01 | 2021-09-30 |  | Approach and timeframes visible to AEMO | Conversion plans to include all type 1-3, subset of 4, type 7 and Cross Boundary meters (Known) datastreams
|  |  | A33 | 5min metering data delivered to Participants (B2B) |  |  | MDP | S01, S43 |  | NSP, FRMP, LR, MDP, AEMO | Subject to the terms of the Agreement | 31-Aug-21 (subject to the terms of the Agreement) | By 1 Oct 2021 | MDPs delivering 5min metering data to Participants to support five-minute settlement | Where a sub-multiple agreement is not in place, the MDP must be able to aggregate 5min reads to 30min up until the commencement of 5MS.
|  |  | A35 | 5min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVarh)) energy metering data as applicable) |  |  | MDP | S01, S43 |  | AEMO, MDP | 2021-06-21 | 31-Aug-21 (subject to the terms of the Agreement) | By 1 Oct 2021 | MDPs delivering 5min metering data to AEMO to support five-minute settlement | No formal agreements between AEMO and MDPs required, MDPs can send through 5min metering data from the transition start date at their convenience.
|  |  | A36 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table |  |  | MDP | S01 | Generation of CR4xxx transactions to transition from Net to Register Level Datastream Inclusion in overall CATS Notification Strategy required | AEMO, NSP | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 | Register level datastreams active in CNDS table as per AEMO procedures | Participants need to be in a position to receive and process the new Datastream Type code of 'N' to support this activity (note – as the Datastream type code already exists in the supported aseXML schemas, no upgrade to r39 is required). Some Participants questioned if all Participants would be ready by the 9-Mar-2021 Transition Start Date.
|  |  | A36a | Complete data cleanse to ensure, the RegisterID matches the content of the ‘Suffix’ within the CATS_REGISTER_IDENTIFIER table. E.g. ‘E1’, ‘B1’, ‘Q1’, ‘K1’, etc. |  |  | MP |  | Generation of CR3xxx transactions to align values Inclusion in overall CATS Notification Strategy required | AEMO, MDP | At the discretion of the Participant | 2021-08-31 | By 1 Oct 2021 | To ensure compliance with the Standing Data for MSATS procedure | As per the Metering ICF Final Determination, published Dec 2020, ‘The RegisterID is used to identify a data source that is obtained from the meter. A single meter may provide multiple data sources. If the RegisterID has a value as per the ‘Datastream Suffix for Interval Metering Data’ section of the NMI Procedure, then it must be the same as the Suffix field in the CATS_REGISTER_IDENTIFIER table.’
| S14 | Type 1-3, subset of 4 | A37 | Agreement to allow the delivery of 5min metering data pre 1 Oct 2021 between NSP, Retailer, MDP and AEMO | Participants to seek Legal advice as required in relation to NER 7.10.5. Participants to engage other Participants early to discuss the potential delivery of 5-min metering data pre-1 Oct 2021. Participants to advise AEMO when they believe they will deliver or receive 5-min metering data. |  | MDP | S02, S03, S43 |  | NSP, FRMP, LR, MDP, AEMO | At the discretion of the Applicable Participants | 2021-05-31 | By 1 Oct 2021 | Applicable agreements in place to enable MDPs to deliver 5min metering data to Participants to support five-minute settlement | MP to provide confirmation of which meters can be included in an agreement Should a NMI churn to a Retailer who does not have an agreement to receive 5min data, an agreement would need to be established or the MDP must deliver 30min data.
|  |  | A37a | Provide datastream conversion plans to convert Net datastreams to register level to AEMO every 2mths |  |  | MDP |  |  | AEMO, MP | 2021-03-01 | 2021-09-30 |  | Approach and timeframes visible to AEMO | Conversion plans to include all type 1-3, subset of 4, type 7 and Cross Boundary meters (Known) datastreams
|  |  | A38 | 5min metering data delivered to Participants (B2B) |  |  | MDP | S02, S03, S43 |  | NSP, FRMP, LR, MDP, AEMO | Subject to the terms of the Agreement | 31-Aug-21 (subject to the terms of the Agreement) | By 1 Oct 2021 | MDPs delivering 5min metering data to Participants to support five-minute settlement | Where a sub-multiple agreement is not in place, the MDP must be able to aggregate 5min reads to 30min up until the commencement of 5MS.
|  |  | A40 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table |  |  | MDP | S02, S03 | Generation of CR4xxx transactions to transition from Net to Register Level Datastream Inclusion in overall CATS Notification Strategy required | NSP, FRMP, LR, MDP, AEMO | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 | Register level datastreams active in CNDS table as per AEMO procedures | Participants need to be in a position to receive and process the new Datastream Type code of 'N' to support this activity (note – as the Datastream type code already exists in the supported aseXML schemas, no upgrade to r39 is required). Some Participants questioned if all Participants would be ready by the 9-Mar-2021 Transition Start Date.
|  |  | A40a | Complete data cleanse to ensure, the RegisterID matches the content of the ‘Suffix’ within the CATS_REGISTER_IDENTIFIER table. E.g. ‘E1’, ‘B1’, ‘Q1’, ‘K1’, etc. |  |  | MP |  | Generation of CR3xxx transactions to align values Inclusion in overall CATS Notification Strategy required | AEMO, MDP | At the discretion of the Participant | 2021-08-31 | By 1 Oct 2021 | To ensure compliance with the Standing Data for MSATS procedure | As per the Metering ICF Final Determination, published Dec 2020, ‘The RegisterID is used to identify a data source that is obtained from the meter. A single meter may provide multiple data sources. If the RegisterID has a value as per the ‘Datastream Suffix for Interval Metering Data’ section of the NMI Procedure, then it must be the same as the Suffix field in the CATS_REGISTER_IDENTIFIER table.’
|  |  | A41 | 5min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVarh)) energy metering data as applicable) |  |  | MDP | S02, S03, S43 |  | AEMO, MDP | 2021-06-21 | 31-Aug-21 (subject to the terms of the Agreement) | By 1 Oct 2021 | MDPs delivering 5min metering data to AEMO to support five-minute settlement | No formal agreements between AEMO and MDPs required, MDPs can send through 5min metering data from the transition start date at their convenience.
| S15 | Cross Boundary meters (Known) | A42 | Agreement to allow the delivery of 5min metering data pre 1 Oct 2021 between NSP, Retailer, MDP and AEMO | Participants to seek Legal advice as required in relation to NER 7.10.5. Participants to engage other Participants early to discuss the potential delivery of 5-min metering data pre-1 Oct 2021. Participants to advise AEMO when they believe they will deliver or receive 5-min metering data. |  | MDP | S04, S43 |  | NSP, FRMP, LR, MDP, AEMO | At the discretion of the Applicable Participants | 2021-05-31 | By 1 Oct 2021 | Applicable agreements in place to enable MDPs to deliver 5min metering data to Participants to support five-minute settlement | MP to provide confirmation of which meters can be included in an agreement Should a NMI churn to a Retailer who does not have an agreement to receive 5min data, an agreement would need to be established or the MDP must deliver 30min data.
|  |  | A42a | Provide datastream conversion plans to convert Net datastreams to register level to AEMO every 2mths |  |  | MDP |  |  | AEMO, MP | 2021-03-01 | 2021-09-30 |  | Approach and timeframes visible to AEMO | Conversion plans to include all type 1-3, subset of 4, type 7 and Cross Boundary meters (Known) datastreams
|  |  | A43 | 5min metering data delivered to Participants (B2B) |  |  | MDP | S04, S43 |  | NSP, FRMP, LR, MDP, AEMO | Subject to the terms of the Agreement | 31-Aug-21 (subject to the terms of the Agreement) | By 1 Oct 2021 | MDPs delivering metering data to support Global Settlement Calculations | Where a sub-multiple agreement is not in place, the MDP must be able to aggregate 5min reads to 30min up until the commencement of 5MS.
|  |  | A45 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table |  |  | MDP | S04 | Generation of CR4xxx transactions to transition from Net to Register Level Datastream Inclusion in overall CATS Notification Strategy required | NSP, FRMP, LR, MDP, AEMO | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 | Register level datastreams active in CNDS table as per AEMO procedures | Participants need to be in a position to receive and process the new Datastream Type code of 'N' to support this activity (note – as the Datastream type code already exists in the supported aseXML schemas, no upgrade to r39 is required). Some Participants questioned if all Participants would be ready by the 9-Mar-2021 Transition Start Date.
|  |  | A45a | Complete data cleanse to ensure, the RegisterID matches the content of the ‘Suffix’ within the CATS_REGISTER_IDENTIFIER table. E.g. ‘E1’, ‘B1’, ‘Q1’, ‘K1’, etc. |  |  | MP |  | Generation of CR3xxx transactions to align values Inclusion in overall CATS Notification Strategy required | AEMO, MDP | At the discretion of the Participant | 2021-08-31 | By 1 Oct 2021 | To ensure compliance with the Standing Data for MSATS procedure | As per the Metering ICF Final Determination, published Dec 2020, ‘The RegisterID is used to identify a data source that is obtained from the meter. A single meter may provide multiple data sources. If the RegisterID has a value as per the ‘Datastream Suffix for Interval Metering Data’ section of the NMI Procedure, then it must be the same as the Suffix field in the CATS_REGISTER_IDENTIFIER table.’
|  |  | A46 | 5min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVarh)) energy metering data as applicable) |  |  | MDP | S04, S43 |  | AEMO, MDP | 2021-06-21 | 31-Aug-21 (subject to the terms of the Agreement) | By 1 Oct 2021 | MDPs delivering metering data to support Global Settlement Calculations | No formal agreements between AEMO and MDPs required, MDPs can send through 5min metering data from the transition start date at their convenience.
| S16 | Cross Boundary meters (Unknown) | A47 | Agreement to allow the delivery of 5min metering data pre 1 Oct 2021 between NSP, Retailer, MDP and AEMO | Participants to seek Legal advice as required in relation to NER 7.10.5. Participants to engage other Participants early to discuss the potential delivery of 5-min metering data pre-1 Oct 2021. Participants to advise AEMO when they believe they will deliver or receive 5-min metering data. |  | MDP | S05, S43 |  | NSP, FRMP, LR, MDP, AEMO | At the discretion of the Applicable Participants | 2021-05-31 | By 1 Oct 2021 | Applicable agreements in place to enable MDPs to deliver 5min metering data to Participants to support five-minute settlement | MP to provide confirmation of which meters can be included in an agreement. Should a NMI churn to a Retailer who does not have an agreement to receive 5min data, an agreement would need to be established or the MDP must deliver 30min data.
|  |  | A48 | 5min metering data delivered to Participants (B2B) |  |  | MDP | S05, S43 |  | NSP, FRMP, LR, MDP, AEMO | Subject to the terms of the Agreement | 31-Aug-21 (subject to the terms of the Agreement) | By 1 Oct 2021 | MDPs delivering metering data to support Global Settlement Calculations | Where a sub-multiple agreement is not in place, the MDP must be able to aggregate 5min reads to 30min up until the commencement of 5MS.
|  |  | A50 | 5min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVarh)) energy metering data as applicable) |  |  | MDP | S05, S43 |  | AEMO, MDP | 2021-06-21 | 31-Aug-21 (subject to the terms of the Agreement) | By 1 Oct 2021 | MDPs delivering metering data to support Global Settlement Calculations | No formal agreements between AEMO and MDPs required, MDPs can send through 5min metering data from the transition start date at their convenience.
|  |  | A51 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table |  |  | MDP | S05 | Generation of CR4xxx transactions due to transition from Net to Register Level Datastream Inclusion in overall CATS Notification Strategy required | NSP, FRMP, LR, MDP, AEMO | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 | Register level datastreams active in CNDS table as per AEMO procedures | Participants need to be in a position to receive and process the new Datastream Type code of 'N' to support this activity (note – as the Datastream type code already exists in the supported aseXML schemas, no upgrade to r39 is required). Some Participants questioned if all Participants would be ready by the 9-Mar-2021 Transition Start Date.
| S17 | New and replacement Type 4 | A52 | Provide forward plan to AEMO and industry | Each MDP Rollout plan is to include: transition window, volumes, ramp rates and overall approach e.g. jurisdictional, distribution area, Retailer. |  | MDP |  |  | NSP, FRMP, LR, MDP, AEMO | At the discretion of the Participant | 2020-09-01 | N/A | Approach and timeframes visible to affected parties | Complete
|  |  | A52a | Provide progress and amendments to forward plans to AEMO and industry every 2mths | Each MDP Rollout plan is to include: transition window, volumes, ramp rates and overall approach e.g. jurisdictional, distribution area, Retailer. |  | MDP |  |  | NSP, FRMP, LR, MDP, AEMO | 2020-12-01 | 2022-11-30 | N/A | Approach and timeframes visible to affected parties | New activity added (v1.5)
|  |  | A52b | Provide datastream conversion plans to convert Net datastreams to register level to AEMO every 2mths |  |  | MDP |  |  | AEMO, MP | 2021-03-01 | 2022-11-30 |  | Approach and timeframes visible to AEMO
|  |  | A53 | Agreement to allow the delivery of 5min metering data pre 1 Oct 2021 between NSP, Retailer, MDP and AEMO | Participants to seek Legal advice as required in relation to NER 7.10.5. Participants to engage other Participants early to discuss the potential delivery of 5-min metering data pre-1 Oct 2021. Participants to advise AEMO when they believe they will deliver or receive 5-min metering data. |  | MDP | S06, S43 | CATS Notification Mgt to be considered as part of the Agreements | NSP, FRMP, LR, MDP, AEMO | At the discretion of the Applicable Participants | 2021-05-31 | By 1 Dec 2022 | Applicable agreements in place to enable MDPs to deliver 5min metering data to Participants to support five-minute settlement | MP to provide confirmation of which meters can be included in an agreement. Should a NMI churn to a Retailer who does not have an agreement to receive 5min data, an agreement would need to be established or the MDP must deliver 30min data.
|  |  | A54 | 5min metering data delivered to Participants (B2B) |  |  | MDP | S06, S43, S44 |  | NSP, FRMP, LR, MDP, AEMO | Subject to the terms of the Agreement | 2022-11-30 | By 1 Dec 2022 | MDPs delivering 5min metering data to Participants to support five-minute settlement | Where a sub-multiple agreement is not in place, the MDP must be able to aggregate 5min reads to 30min up until the commencement of 5MS.
|  |  | A56 | 5min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVarh)) energy metering data as applicable) |  |  | MDP | S06, S43, S44 |  | AEMO, MDP | 2021-06-21 | 2022-11-30 | By 1 Dec 2022 | MDPs delivering 5min metering data to Participants to support five-minute settlement | No formal agreements between AEMO and MDPs required, MDPs can send through 5min metering data from the transition start date at their convenience.
|  |  | A57 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table |  |  | MDP | S06 | Generation of CR4xxx transactions due to transition from Net to Register Level Datastream Inclusion in overall CATS Notification Strategy required | NSP, FRMP, LR, MDP, AEMO | 2021-06-21 | 2022-11-30 | By 1 Dec 2022 | Register level datastreams active in CNDS table as per AEMO procedures | Participants need to be in a position to receive and process the new Datastream Type code of 'N' to support this activity (note – as the Datastream type code already exists in the supported aseXML schemas, no upgrade to r39 is required). Some Participants questioned if all Participants would be ready by the 9-Mar-2021 Transition Start Date.
|  |  | A57a | Complete data cleanse to ensure, the RegisterID matches the content of the ‘Suffix’ within the CATS_REGISTER_IDENTIFIER table. E.g. ‘E1’, ‘B1’, ‘Q1’, ‘K1’, etc. |  |  | MP |  | Generation of CR3xxx transactions to align values Inclusion in overall CATS Notification Strategy required | AEMO, MDP | At the discretion of the Participant | 2022-01-15 | 2022-02-06 | To ensure compliance with the Standing Data for MSATS procedure | As per the Metering ICF Final Determination, published Dec 2020, ‘The RegisterID is used to identify a data source that is obtained from the meter. A single meter may provide multiple data sources. If the RegisterID has a value as per the ‘Datastream Suffix for Interval Metering Data’ section of the NMI Procedure, then it must be the same as the Suffix field in the CATS_REGISTER_IDENTIFIER table.’
| S18 | New and replacement Type 4A | A58 | Provide forward plan to AEMO and industry | Each MDP Rollout plan is to include: transition window, volumes, ramp rates and overall approach e.g. jurisdictional, distribution area, Retailer. |  | MDP |  |  | NSP, FRMP, LR, MDP, AEMO | At the discretion of the Participant | 2020-09-01 | N/A | Approach and timeframes visible to affected parties | Complete
|  |  | A58a | Provide progress and amendments to forward plans to AEMO and industry every 2mths | Each MDP Rollout plan is to include: transition window, volumes, ramp rates and overall approach e.g. jurisdictional, distribution area, Retailer. |  | MDP |  |  | NSP, FRMP, LR, MDP, AEMO | 2020-12-01 | 2022-11-30 | N/A | Approach and timeframes visible to affected parties | New activity added (v1.5)
|  |  | A58b | Provide datastream conversion plans to convert Net datastreams to register level to AEMO every 2mths |  |  | MDP |  |  | AEMO, MP | 2021-03-01 | 2022-11-30 |  | Approach and timeframes visible to AEMO
|  |  | A59 | Agreement to allow the delivery of 5min metering data pre 1 Oct 2021 between NSP, Retailer, MDP and AEMO | Participants to seek Legal advice as required in relation to NER 7.10.5. Participants to engage other Participants early to discuss the potential delivery of 5-min metering data pre-1 Oct 2021. Participants to advise AEMO when they believe they will deliver or receive 5-min metering data. |  | MDP | S07, S43 | CATS Notification Mgt to be considered as part of the Agreements | NSP, FRMP, LR, MDP, AEMO | At the discretion of the Applicable Participants | 2021-05-31 | By 1 Dec 2022 | Applicable agreements in place to enable MDPs to deliver 5min metering data to Participants to support five-minute settlement | MP to provide confirmation of which meters can be included in an agreement
|  |  | A60 | 5min metering data delivered to Participants (B2B) |  |  | MDP | S07, S43, S44 |  | NSP, FRMP, LR, MDP, AEMO | Subject to the terms of the Agreement | 2022-11-30 | By 1 Dec 2022 | MDPs delivering 5min metering data to Participants to support five-minute settlement | Where a sub-multiple agreement is not in place, the MDP must be able to aggregate 5min reads to 30min up until the commencement of 5MS.
|  |  | A62 | 5min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVarh)) energy metering data as applicable) |  |  | MDP | S07, S43, S44 |  | AEMO, MDP | 2021-06-21 | 2022-11-30 | By 1 Dec 2022 | MDPs delivering 5min metering data to Participants to support five-minute settlement | No formal agreements between AEMO and MDPs required, MDPs can send through 5min metering data from the transition start date at their convenience.
|  |  | A63 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table |  |  | MDP | S07 | Generation of CR4xxx transactions due to transition from Net to Register Level Datastream Inclusion in overall CATS Notification Strategy required | NSP, FRMP, LR, MDP, AEMO | 2021-06-21 | 2022-11-30 | By 1 Dec 2022 | Register level datastreams active in CNDS table as per AEMO procedures | Participants need to be in a position to receive and process the new Datastream Type code of 'N' to support this activity (note – as the Datastream type code already exists in the supported aseXML schemas, no upgrade to r39 is required). Some Participants questioned if all Participants would be ready by the 9-Mar-2021 Transition Start Date.
|  |  | A63a | Complete data cleanse to ensure, the RegisterID matches the content of the ‘Suffix’ within the CATS_REGISTER_IDENTIFIER table. E.g. ‘E1’, ‘B1’, ‘Q1’, ‘K1’, etc. |  |  | MP |  | Generation of CR3xxx transactions to align values Inclusion in overall CATS Notification Strategy required | AEMO, MDP | At the discretion of the Participant | 2022-01-15 | 2022-02-06 | To ensure compliance with the Standing Data for MSATS procedure | As per the Metering ICF Final Determination, published Dec 2020, ‘The RegisterID is used to identify a data source that is obtained from the meter. A single meter may provide multiple data sources. If the RegisterID has a value as per the ‘Datastream Suffix for Interval Metering Data’ section of the NMI Procedure, then it must be the same as the Suffix field in the CATS_REGISTER_IDENTIFIER table.’
| S19 | New and replacement VIC AMI meters | A64 | Provide forward plan to AEMO and industry | Each MDP Rollout plan is to include: transition window, volumes, ramp rates and overall approach e.g. jurisdictional, distribution area, Retailer. |  | MDP |  |  | AEMO, FRMP, LNSP | At the discretion of the Participant | 2020-09-01 | N/A | Approach and timeframes visible to affected parties | Complete
|  |  | A64a | Provide progress and amendments to forward plans to AEMO and industry every 2mths | Each MDP Rollout plan is to include: transition window, volumes, ramp rates and overall approach e.g. jurisdictional, distribution area, Retailer. |  | MDP |  |  | NSP, FRMP, LR, MDP, AEMO | 2020-12-01 | 2022-11-30 | N/A | Approach and timeframes visible to affected parties | New activity added (v1.5)
|  |  | A64b | Provide datastream conversion plans to convert Net datastreams to register level to AEMO every 2mths |  |  | MDP |  |  | AEMO, MP | 2021-03-01 | 2022-11-30 |  | Approach and timeframes visible to AEMO
|  |  | A65 | Agreement to allow the delivery of 5min metering data pre 1 Oct 2021 between NSP, Retailer, MDP and AEMO | Participants to seek Legal advice as required in relation to NER 7.10.5. Participants to engage other Participants early to discuss the potential delivery of 5-min metering data pre-1 Oct 2021. Participants to advise AEMO when they believe they will deliver or receive 5-min metering data. |  | MDP | S08, S43 | CATS Notification Mgt to be considered as part of the Agreements | NSP, FRMP, LR, MDP, AEMO | At the discretion of the Applicable Participants | 2021-05-31 | By 1 Dec 2022 | Applicable agreements in place to enable MDPs to deliver 5min metering data to Participants to support five-minute settlement | MP to provide confirmation of which meters can be included in an agreement. Should a NMI churn to a Retailer who does not have an agreement to receive 5min data, an agreement would need to be established or the MDP must deliver 30min data.
|  |  | A66 | 5min metering data delivered to Participants (B2B) |  |  | MDP | S08, S43, S44 |  | NSP, FRMP, LR, MDP, AEMO | Subject to the terms of the Agreement | 2022-11-30 | By 1 Dec 2022 | MDPs delivering 5min metering data to Participants to support five-minute settlement | Where a sub-multiple agreement is not in place, the MDP must be able to aggregate 5min reads to 30min up until the commencement of 5MS.
|  |  | A68 | 5min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVarh)) energy metering data as applicable) |  |  | MDP | S08, S43, S44 |  | AEMO, MDP | 2021-06-21 | 2022-11-30 | By 1 Dec 2022 | MDPs delivering 5min metering data to Participants to support five-minute settlement | No formal agreements between AEMO and MDPs required, MDPs can send through 5min metering data from the transition start date at their convenience.
|  |  | A69 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table |  |  | MDP | S08 | Generation of CR4xxx transactions due to transition from Net to Register Level Datastream Inclusion in overall CATS Notification Strategy required | NSP, FRMP, LR, MDP, AEMO | 2021-06-21 | 2022-11-30 | By 1 Dec 2022 | Register level datastreams active in CNDS table as per AEMO procedures | Participants need to be in a position to receive and process the new Datastream Type code of 'N' to support this activity (note – as the Datastream type code already exists in the supported aseXML schemas, no upgrade to r39 is required). Some Participants questioned if all Participants would be ready by the 9-Mar-2021 Transition Start Date.
|  |  | A69a | Complete data cleanse to ensure, the RegisterID matches the content of the ‘Suffix’ within the CATS_REGISTER_IDENTIFIER table. E.g. ‘E1’, ‘B1’, ‘Q1’, ‘K1’, etc. |  |  | MP |  | Generation of CR3xxx transactions to align values Inclusion in overall CATS Notification Strategy required | AEMO, MDP | At the discretion of the Participant | 2022-01-15 | 2022-02-06 | To ensure compliance with the Standing Data for MSATS procedure | As per the Metering ICF Final Determination, published Dec 2020, ‘The RegisterID is used to identify a data source that is obtained from the meter. A single meter may provide multiple data sources. If the RegisterID has a value as per the ‘Datastream Suffix for Interval Metering Data’ section of the NMI Procedure, then it must be the same as the Suffix field in the CATS_REGISTER_IDENTIFIER table.’
| S20 | New and replacement SAMPLE Meters | A70 | Provide forward plan to AEMO and industry | Each MDP Rollout plan is to include: transition window, volumes, ramp rates and overall approach e.g. jurisdictional, distribution area, Retailer. |  | MDP |  |  | AEMO, FRMP, LNSP | At the discretion of the Participant | 2020-09-01 | N/A | Approach and timeframes visible to affected parties | Complete
|  |  | A70a | Provide progress and amendments to forward plans to AEMO and industry every 2mths | Each MDP Rollout plan is to include: transition window, volumes, ramp rates and overall approach e.g. jurisdictional, distribution area, Retailer. |  | MDP |  |  | NSP, FRMP, LR, MDP, AEMO | 2020-12-01 | 2022-11-30 | N/A | Approach and timeframes visible to affected parties | New activity added (v1.5)
|  |  | A70b | Provide datastream conversion plans to convert Net datastreams to register level to AEMO every 2mths |  |  | MDP |  |  | AEMO, MP | 2021-03-01 | 2022-11-30 |  | Approach and timeframes visible to AEMO
|  |  | A71 | Agreement to allow the delivery of 5min metering data pre 1 Oct 2021 between NSP, Retailer, MDP and AEMO | Participants to seek Legal advice as required in relation to NER 7.10.5. Participants to engage other Participants early to discuss the potential delivery of 5-min metering data pre-1 Oct 2021. Participants to advise AEMO when they believe they will deliver or receive 5-min metering data. |  | MDP | S09, S43 | CATS Notification Mgt to be considered as part of the Agreements | NSP, FRMP, LR, MDP, AEMO | At the discretion of the Applicable Participants | 2021-05-31 | By 1 Dec 2022 | Applicable agreements in place to enable MDPs to deliver 5min metering data to Participants to support five-minute settlement | MP to provide confirmation of which meters can be included in an agreement. Should a NMI churn to a Retailer who does not have an agreement to receive 5min data, an agreement would need to be established or the MDP must deliver 30min data.
|  |  | A74 | 5min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVarh)) energy metering data as applicable) |  |  | MDP | S09, S43, S44 |  | AEMO, MDP | 2021-06-21 | 2022-11-30 | By 1 Dec 2022 | MDPs delivering 5min metering data to Participants to support five-minute settlement | No formal agreements between AEMO and MDPs required, MDPs can send through 5min metering data from the transition start date at their convenience.
|  |  | A75 | Create/activate applicable export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table |  |  | MDP | S09 | Generation of CR4xxx transactions due to transition from Net to Register Level Datastream Inclusion in overall CATS Notification Strategy required | NSP, FRMP, LR, MDP, AEMO | 2021-06-21 | 2022-11-30 | By 1 Dec 2022 | Register level datastreams active in CNDS table as per AEMO procedures | Participants need to be in a position to receive and process the new Datastream Type code of 'N' to support this activity (note – as the Datastream type code already exists in the supported aseXML schemas, no upgrade to r39 is required). Some Participants questioned if all Participants would be ready by the 9-Mar-2021 Transition Start Date.
|  |  | A75a | Complete data cleanse to ensure, the RegisterID matches the content of the ‘Suffix’ within the CATS_REGISTER_IDENTIFIER table. E.g. ‘E1’, ‘B1’, ‘Q1’, ‘K1’, etc. |  |  | MP |  | Generation of CR3xxx transactions to align values Inclusion in overall CATS Notification Strategy required | AEMO, MDP | At the discretion of the Participant | 2022-01-15 | 2022-02-06 | To ensure compliance with the Standing Data for MSATS procedure | As per the Metering ICF Final Determination, published Dec 2020, ‘The RegisterID is used to identify a data source that is obtained from the meter. A single meter may provide multiple data sources. If the RegisterID has a value as per the ‘Datastream Suffix for Interval Metering Data’ section of the NMI Procedure, then it must be the same as the Suffix field in the CATS_REGISTER_IDENTIFIER table.’
| S22 | Type 7 metering installations | A82 | 5min metering data delivered to Participants (B2B) |  |  | MDP | S43 |  | FRMP, LNSP | At the discretion of the Applicable Participants | 2021-09-30 | By 1 Oct 2021 | MDPs delivering 5min metering data to Participants to support five-minute settlement
|  |  | A82a | Provide datastream conversion plans to convert Net datastreams to register level to AEMO every 2mths |  |  | MDP |  |  | AEMO, MP | 2021-03-01 | 2021-09-30 |  | Approach and timeframes visible to AEMO | Conversion plans to include all type 1-3, subset of 4, type 7 and Cross Boundary meters (Known) datastreams
|  |  | A83 | Updating Datastreams in MSATs |  |  | MDP |  |  | MDP | At the discretion of the Participant | 2021-08-31 | By 1 Oct 2021
|  |  | A83a | Complete data cleanse to ensure, the RegisterID matches the content of the ‘Suffix’ within the CATS_REGISTER_IDENTIFIER table. E.g. ‘E1’, ‘B1’, ‘Q1’, ‘K1’, etc. |  |  | MP |  | Generation of CR4xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, MDP | At the discretion of the Participant | 2022-01-15 | 2022-02-06 | To ensure compliance with the Standing Data for MSATS procedure | As per the Metering ICF Final Determination, published Dec 2020, ‘The RegisterID is used to identify a data source that is obtained from the meter. A single meter may provide multiple data sources. If the RegisterID has a value as per the ‘Datastream Suffix for Interval Metering Data’ section of the NMI Procedure, then it must be the same as the Suffix field in the CATS_REGISTER_IDENTIFIER table.’
|  |  | A84 | Agreement to allow the delivery of 5min metering data pre 1 Oct 2021 between NSP, Retailer, MDP and AEMO | Participants to seek Legal advice as required in relation to NER 7.10.5. Participants to engage other Participants early to discuss the potential delivery of 5-min metering data pre-1 Oct 2021. Participants to advise AEMO when they believe they will deliver or receive 5-min metering data. |  | MDP |  | CATS Notification Mgt to be considered as part of the Agreements | NSP, FRMP, LR, MDP, AEMO | At the discretion of the Applicable Participants | 2021-05-31 | By 1 Oct 2021 |  | MP to provide confirmation of which meters can be included in an agreement. Should a NMI churn to a Retailer who does not have an agreement to receive 5min data, an agreement would need to be established or the MDP must deliver 30min data.
|  |  | A86 | 5min metering data delivered to AEMO (MDFF) |  |  | MDP | S43 |  | AEMO | 2021-06-21 | 2021-09-30 | By 1 Oct 2021 | MDPs delivering 5min metering data to AEMO to support five-minute settlement | No formal agreements between AEMO and MDPs required, MDPs can send through 5min metering data from the transition start date at their convenience.
| S23 | Non-contestable unmetered loads | A87 | MC must ensure that details of the Inventory Table, calculation methodologies and Agreed Loads are agreed prior to implementation by relevant Registered Participants |  |  | MC |  |  | AEMO, FRMP, LNSP | At the discretion of the Applicable Participants | 2021-03-31 | N/A | MDPs delivering metering data to support Global Settlement and UFE Calculations
|  |  | A88 | Agreement to allow the delivery of 5min metering data pre 1 Oct 2021 between NSP, Retailer, MDP and AEMO | Participants to seek Legal advice as required in relation to NER 7.10.5. Participants to engage other Participants early to discuss the potential delivery of 5-min metering data pre-1 Oct 2021. Participants to advise AEMO when they believe they will deliver or receive 5-min metering data. |  | MDP |  | CATS Notification Mgt to be considered as part of the Agreements | NSP, FRMP, LR, MDP, AEMO | At the discretion of the Applicable Participants | 2021-05-31 | By 1 Oct 2021 |  | MP to provide confirmation of which meters can be included in an agreement
|  |  | A89 | AEMO Metering Business approve MDP NCONUML profiles/algorithms |  |  | AEMO |  |  | AEMO, FRMP, LNSP | At the discretion of AEMO | 2021-05-01 | By 1 Oct 2021 | MDPs delivering metering data to support participant billing of NCUML
|  |  | A89a | Provide AEMO estimated number of NMIs and associated energy volumes for each Unmetered Device category within calculation methodology |  |  | MDP | A89 |  | MDP, AEMO | At the discretion of the Participant | 2021-05-01 | By 1 Oct 2021
|  |  | A90 | 5min metering data delivered to Participants (B2B) |  |  | MDP | S43 |  | FRMP, LNSP | At the discretion of the Applicable Participants | 2021-09-30 | By 1 Oct 2021 | MDPs delivering metering data to support participant billing of NCUML | Where a sub-multiple agreement is not in place, the MDP must be able to aggregate 5min reads to 30min up until the commencement of 5MS.
|  |  | A92 | 5min metering data delivered to AEMO (MDFF) |  |  | MDP | S43 |  | AEMO | 2021-06-21 | 2021-09-30 | By 1 Oct 2021 | MDPs delivering metering data to support Global Settlement Calculations | No formal agreements between AEMO and MDPs required, MDPs can send through 5min metering data from the transition start date at their convenience.
| S24 | Tier 1 basic metering data | A93 | Delivery of tier 1 basic meter metering data (Actuals, Subs and Forward Estimates) to AEMO |  |  | MDP | S43 |  | AEMO | At the discretion of the Participant | 2021-06-30 | By 1 Oct 2021 | MDPs delivering metering data to support Global Settlement Calculations
| S25 | Meter data delivery of 30min and 15min interval reads only in MDFF to AEMO | A94 | Meter data delivery of 15 and 30min interval reads only in MDFF to AEMO |  |  | MDP | S43 |  | AEMO | 2021-06-21 | N/A | By 1 Oct 2021 | MDPs delivering interval data to AEMO via NEM12 MDFF
STANDING DATA MANAGEMENT
| S26 | Cross-boundary supplies | A95 | Create cross-boundary NMIs |  |  | LNSP |  | Generation of CR2xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, MP, MDP, FRMP, LR, LNSP | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021
|  |  | A95a | Provide NMI Create plans to AEMO every 2mths |  |  | LNSP |  |  | AEMO, MP, MDP, FRMP, LR, LNSP | 2021-03-01 | 2021-09-30 | By 1 Oct 2021
|  |  | A95b | Information provided when seeking approval from AEMO, in accordance with section 3.1(c) of the Cross Boundary Supply Guideline, must include evidence of the agreement of the LNSP and NSP2 roles |  |  | LNSP |  |  | AEMO, LNSP, NSP2 | At the discretion of the Participant | 2021-08-31 | By 1 Oct 2021 | To support the NMI re-classification of XBOUNDRY sites | New activity added (v1.8)
|  |  | A96 | Create Datastreams in MSATS |  |  | MDP | S04, S05 | Generation of CR4xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, FRMP, LNSP | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021 | Participants need to be in a position to receive and process the new Datastream Type code of 'N' to support this activity (note – as the Datastream type code already exists in the supported aseXML schemas, no upgrade to r39 is required). Some Participants questioned if all Participants would be ready by the 9-Mar-2021 Transition Start Date.
|  |  | A97 | Create registers in MSATS |  |  | MP | S04, S05 | Generation of CR3xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, FRMP, LNSP | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021
|  |  | A97a | AEMO to provide TNI2 values to LNSPs to support the updating of applicable TNI fields i.e. TNI fields associated to NMIs downstream of a cross boundary NMI |  |  | AEMO |  | Generation of CR2xxx transactions Inclusion in overall CATS Notification Strategy essential | LNSP | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021 | New activity added (v1.8)
|  |  | A97b | LNSPs to update the TNI field, for NMIs downstream of a cross boundary NMI, with the AEMO provided TNI2 value |  |  | LNSP |  | Generation of CR2xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, MP, MDP, FRMP, LR, LNSP | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021 | New activity added (v1.8)
|  |  | A97c | Provisioning of cross boundary information to AEMO to enable the determination of TNI2 values |  |  | LNSP |  |  | AEMO | At the discretion of the Participant | 2021-07-31 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021 | New activity added (v1.8)
| S27 | Non-contestable unmetered loads | A98 | B2BWG to consider potential recommendations to the IEC to better support 1 to many scenarios |  |  | AEMO |  |  | AEMO, MP, MDP, FRMP, LNSP |  | 2019-11-30 | N/A | To support the calculation of UFE from 1 Oct 2021 | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A98a | Provide AEMO indicative NCONUML NMI list |  |  | LNSP |  |  | AEMO | At the discretion of the Participant | 2021-02-28 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021 | Note, request from Origin that the NMI list is provided to the LR in addition to AEMO to assist with any reconciliation work to be undertaken and visibility of NMI’s to be created in the market
|  |  | A99 | Create NCONUML NMIs in MSATS |  | 1 part process i.e. NMIs are to be created when the new NCUL NMI Class Code is available in MSATS | LNSP |  | Generation of CR2xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, MP, MDP, FRMP, LNSP | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021
|  |  | A99a | Provide NMI Create plans to AEMO every 2mths |  |  | LNSP |  |  | AEMO, MP, MDP, FRMP, LNSP | 2021-03-01 | 2021-09-30 | By 1 Oct 2021
|  |  | A100 | Create Datastreams in MSATS |  |  | MDP |  | Generation of CR4xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, MP, FRMP, LNSP | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021 | Participants need to be in a position to receive and process the new Datastream Type code of 'N' to support this activity (note – as the Datastream type code already exists in the supported aseXML schemas, no upgrade to r39 is required). Some Participants questioned if all Participants would be ready by the 9-Mar-2021 Transition Start Date.
|  |  | A101 | Create registers in MSATS |  |  | MP |  | Generation of CR3xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, MDP, FRMP, LNSP | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021
| S27a | Convert 'SASCALE NMI' | A101a | Make existing 'Bulk' NMI extinct in MSATS |  |  | LNSP |  |  | AEMO, MP, MDP, FRMP, LR, LNSP | At the discretion of the Participant | 2021-06-30 | By 1 Oct 2021 | SA PowerNet to transition from x1 (one) NMI in CATS (‘SASCALE’) identifying controlled load to individual CNDS records for first Tier NMI’s with controlled load
|  |  | A101b | Create individual controlled load Datastreams in MSATS |  |  | MDP |  | Generation of CR4xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, FRMP, LNSP | At the discretion of the Participant | 2021-06-30 | By 1 Oct 2021 | As above | Participants need to be in a position to receive and process the new Datastream Type code of 'N' to support this activity (note – as the Datastream type code already exists in the supported aseXML schemas, no upgrade to r39 is required). Some Participants questioned if all Participants would be ready by the 9-Mar-2021 Transition Start Date.
|  |  | A101c | Create individual controlled load Registers in MSATS |  |  | MP |  | Generation of CR3xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, FRMP, LNSP | At the discretion of the Participant | 2021-06-30 | By 1 Oct 2021 | As above
| S28 | New NMI classification codes - BULK | A102 | Ensure capability to receive and process new NMI classification codes |  |  | FRMP |  |  | FRMP, MDP, MP, LR | At the discretion of the Participant | 2021-05-30 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021
|  |  | A103 | Update NMI Class Codes for existing NMIs as required |  |  | TNSP |  | Generation of CR2xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, FRMP | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021
| S29 | New NMI classification codes - NCONUML | A104 | Ensure capability to receive and process new NMI classification codes |  |  | FRMP |  |  | FRMP, MDP, MP, LR | At the discretion of the Participant | 2021-05-30 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021
|  |  | A105 | Update NMI Class Codes for existing NMIs as required |  |  | LNSP |  | Generation of CR2xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, FRMP | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021 | If both parties are ready, AEMO may enable the code in MSATs, however distributors/retailers should only use it when both parties are ready Only between Local Retailer and DB.
| S30 | New NMI classification codes - DWHOLESAL | A106 | Ensure capability to receive and process new NMI classification codes |  |  | FRMP |  |  | FRMP, MDP, MP, LR | At the discretion of the Participant | 2021-05-30 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021
|  |  | A107 | Update NMI Class Codes for existing NMIs as required |  |  | LNSP |  | Generation of CR2xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, FRMP | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021
| S31 | New NMI classification codes - NREG | A108 | Ensure capability to receive and process new NMI classification codes |  |  | FRMP |  |  | FRMP, MDP, MP, LR | At the discretion of the Participant | 2021-05-30 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021
|  |  | A109 | Update NMI Class Codes for existing NMIs as required |  |  | LNSP |  | Generation of CR2xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, FRMP | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021 | Non-registered generation within embedded networks must also be re-classified as NREG. As DNSPs have no visibility of, and no role in the administration of, child connection points within embedded networks, Embedded Network Managers (ENMs) must change the NMI Classification to NREG. DNSPs and ENMs will be able to identify NREG NMIs as detailed below. DNSP identification of all NREG NMIs within distribution networks 1. SGA NMIs – identifiable in MSATS •FRMP = %SGA (DNSP must ensure that SGAs are correctly assigned to generation NMIs) 2. Non-market embedded generators – identifiable in MSATS •LNSP = DNSP Participant ID • NMI Classification = GENERATR • AggFlag = Y • FRMP <> %SGA 3. Non-registered embedded generators that meet the requirements of NER 5A.A.1 and 5A.D.1A – DNSPs have details of these NMIs in their “Register of completed embedded generation projects”. ENM identification of all NREG NMIs within embedded networks 4. SGA NMIs – identifiable in MSATS • FRMP = %SGA (ENM must ensure that SGAs are correctly assigned to generation NMIs) 5. Non-market embedded generators – identifiable in MSATS • LNSP = ENM Participant ID • NMI Classification = GENERATR • AggFlag = Y • FRMP <> %SGA
| S32 | New NMI classification codes - XBOUNDRY | A110 | Ensure capability to receive and process new NMI classification codes |  |  | FRMP |  |  | FRMP, MDP, MP, LR | At the discretion of the Participant | 2021-05-30 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021
|  |  | A111 | Update NMI Class Codes for existing NMIs as required |  |  | LNSP |  | Generation of CR2xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, FRMP | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021
| S33 | New NMI classification codes - GENERATR | A112 | Ensure capability to receive and process new NMI classification codes |  |  | FRMP |  |  | FRMP, MDP, MP, LR | At the discretion of the Participant | 2021-05-30 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021
|  |  | A113 | Update NMI Class Codes for existing NMIs as required |  |  | LNSP |  | Generation of CR2xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, FRMP | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021
| S34 | New NMI classification codes - WHOLESAL | A114 | Ensure capability to receive and process new NMI classification codes |  |  | FRMP |  |  | FRMP, MDP, MP, LR | At the discretion of the Participant | 2021-05-30 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021
|  |  | A115 | Update NMI Class Codes for existing NMIs as required |  |  | TNSP |  | Generation of CR2xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, FRMP | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021 | NMI Discovery impact i.e. not recognised code AEMO to monitor application of certain codes e.g. NREG Can we decouple NMI request vs NMI COM? If market customers are not ready early then the risk profile goes up! AEMO to provide Participants a list of NMIs, including their NMI Classification Code, which they believe needs to be updated for reconciliation/validation purposes.
| S35 | LR and FRMP fields | A116 | Update LR and FRMP to GLOPOOL for existing NMIs as required | AEMO’s proposed approach is for AEMO to perform the updates through a bulk update mechanism and suppress CR notifications. |  | AEMO |  | Generation of significant CR5xxx transactions AEMO to support update via agreed bulk update approach | AEMO and All Participant Types | 2022-05-01 | 2022-05-01 | 2022-05-01 | To remove the financial liability of Retailers for bulk connection points | Updates must be effective 1 May 2022 Consider opt in opt out independent update (shared script rules) options In flight CRs will be included in the updates
| S36 | Tier 1 basic meter datastreams | A117 | Consider new process for activating datastreams | Updates to be managed through BAU CR transactions, potential notification management requirements still to be determined |  | MDP |  |  | AEMO, FRMP, LNSP | At the discretion of the Participant | 2021-06-30 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021
|  |  | A118 | Create/activate tier 1 basic meter datastreams as required |  |  | MDP |  | Generation of CR4xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, FRMP, LNSP | At the discretion of the Participant | 2021-06-30 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021
| S37 | Update Sample meter DataStreamType codes and Profiles | A119 | Ensure all Sample meters have a Datastream type code of 'P' and are attached to a Profile |  |  | MDP |  | Generation of CR4xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, FRMP, LNSP | At the discretion of the Participant | 2021-08-31 | By 1 May 2022 |  | Participants need to be in a position to receive and process the new Datastream Type code of 'N' to support this activity (note – as the Datastream type code already exists in the supported aseXML schemas, no upgrade to r39 is required). Some Participants questioned if all Participants would be ready by the 9-Mar-2021 Transition Start Date.
| S38 | VIC TUOS datastreams | A120 | Update Datastream type codes from 1-4 to 'I' or 'N' as required |  |  | MDP |  | Generation of CR4xxx transactions Inclusion in overall CATS Notification Strategy essential | AEMO, FRMP, LNSP | 2021-06-21 | 2021-08-31 | By 1 Oct 2021 |  | Participants need to be in a position to receive and process the new Datastream Type code of 'N' to support this activity (note – as the Datastream type code already exists in the supported aseXML schemas, no upgrade to r39 is required). Some Participants questioned if all Participants would be ready by the 9-Mar-2021 Transition Start Date.
|  |  | A120A | Ongoing delivery of VIC TUOS metering data to AEMO via MDFF during transition to 5MS |  |  | MDP |  |  | AEMO | Ongoing | Ongoing | N/A | No interruption to delivery of VIC TUOS metering data to AEMO via MDFF during transition to 5MS
| S39 | Meter installation type code in MSATS | A121 | Complete data cleanse of meter installation type code in MSATS |  |  | MP |  |  | AEMO, FRMP, LNSP |  | 2019-11-30 | By 1 Oct 2021 | To support the calculation of UFE from 1 Oct 2021 | Deemed completed, as the transition end date has past
METERING ACCREDITATION UPDATES
| S41 | MP accreditation update (for 1 Oct 2021) | A123 | Assess level of change required for people, process and systems to facilitate 5MS/GS implementation |  |  | MP |  |  | AEMO | At the discretion of the Participant | 2020-02-28 | By 1 Oct 2021 |  | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A124 | Confirm scope/scale of change with AEMO |  |  | MP |  |  | AEMO | At the discretion of the Participant | 2020-06-30 | By 1 Oct 2021 |  | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A125 | If needed, apply for accreditation update |  |  | MP |  |  | AEMO | At the discretion of the Participant | In accordance with Roadmap agreed with AEMO | By 1 Oct 2021
|  |  | A126 | Approve accreditation applications |  |  | AEMO |  |  | AEMO | At the discretion of AEMO | In accordance with Roadmap agreed with AEMO | By 1 Oct 2021
| S42 | MP accreditation update (for 1 Dec 2022) | A127 | Assess level of change required for people, process and systems to facilitate 5MS/GS implementation |  |  | MP |  |  | AEMO | At the discretion of the Participant | 2020-03-31 | By 1 Dec 2022 |  | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A128 | Confirm scope/scale of change with AEMO |  |  | MP |  |  | AEMO | At the discretion of the Participant | 2020-09-30 | By 1 Dec 2022 |  | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A129 | If needed, apply for accreditation update |  |  | MP |  |  | AEMO | At the discretion of the Participant | In accordance with Roadmap agreed with AEMO | By 1 Dec 2022
|  |  | A130 | Approve accreditation applications |  |  | AEMO |  |  | AEMO | At the discretion of AEMO | In accordance with Roadmap agreed with AEMO | By 1 Dec 2022
| S43 | MDP accreditation update (for 1 Oct 2021) | A131 | Assess level of change required for people, process and systems to facilitate 5MS/GS implementation |  |  | MDP |  |  | AEMO | At the discretion of the Participant | 2020-02-28 | By 1 Oct 2021 |  | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A132 | Confirm scope/scale of change with AEMO |  |  | MDP |  |  | AEMO | At the discretion of the Participant | 2020-06-30 | By 1 Oct 2021 |  | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A133 | If needed, apply for accreditation update |  |  | MDP |  |  | AEMO | At the discretion of the Participant | In accordance with Roadmap agreed with AEMO | By 1 Oct 2021
|  |  | A134 | Approve accreditation applications |  |  | AEMO |  |  | AEMO | At the discretion of AEMO | In accordance with Roadmap agreed with AEMO | By 1 Oct 2021
| S44 | MDP accreditation update (for 1 Dec 2022) | A135 | Assess level of change required for people, process and systems to facilitate 5MS/GS implementation |  |  | MDP |  |  | AEMO | At the discretion of the Participant | 2020-03-31 | By 1 Dec 2022 |  | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A136 | Confirm scope/scale of change with AEMO |  |  | MDP |  |  | AEMO | At the discretion of the Participant | 2020-09-30 | By 1 Dec 2022 |  | Deemed completed, as the transition end date has past and no Participants are reporting it as being late
|  |  | A137 | If needed, apply for accreditation update |  |  | MDP |  |  | AEMO | At the discretion of the Participant | In accordance with Roadmap agreed with AEMO | By 1 Dec 2022
|  |  | A138 | Approve accreditation applications |  |  | AEMO |  |  | AEMO | At the discretion of AEMO | In accordance with Roadmap agreed with AEMO | By 1 Dec 2022
Note: All other dependencies not explicitly mentioned in the MTP are assumed to be the responsibility of the "Responsible" party of each activity