## Slide 1: AEM0 Workshop – July 2015

## Slide 2: Power of Choice Implementation
Program plan update and discussion
Work planning (July to November 2015)
Summary of stakeholder feedback to date and issues register
Questions

## Slide 3: Program plan update

## Slide 4: Program plan update
On 2 July 2015, the AEMC provided notice that the date for the final determination for metering competition is to be extended to 26 November 2015.
Notice was also provided on the expected date changes to the delivery of the first set of AEMO and IEC procedure changes and a revised date on which the new rules and procedures would become effective:
      AEMO and IEC Procedures: 1 September 2016
      Metering competition effective date: 1 December 2017
Over the months of May and June, AEMO held a number of workshops and working group meetings to facilitate discussion on:
      The technical analysis of the changes required to procedures based on the draft determination
      Scheduling and planning of the metering competition work alongside other Power of Choice initiatives.

## Slide 5: Program plan update
In summary, the feedback received from stakeholders regarding the schedule presented for the program and specifically for the metering competition change is as follows:
      Align initiatives where possible – simplify procedure, system, procedure change.
      Take into account downtime over Dec/Jan in planning (4-6 week loss to consultation period).
      Build in reasonable time for pre-consultation stakeholder engagement and through the formal consultation process – concern that sufficient time was not allowed for in MC procedure package 1 in particular.
      Differing views on time required for industry system build and when that work could reasonably commence (e.g. after final determination, once all procedures are finalised).
AEMO has developed two schedules for further discussion:
      Based on the timelines from the draft determination (updated)
      An alternate schedule, based on feedback from stakeholders

## Slide 6: Program plan update
Of note, the revised final determination date for metering competition aligns with the target final determination date for the embedded networks rule change – November 2015.
AEMO has considered that as a result of this alignment, timeframes for the delivery of the two initiatives could be aligned.
Other PoC initiatives, such as Shared Market Protocol (SMP) and Multiple Trading Relationships (MTR) are not in scope for this discussion, although it is recognised that the development of SMP in particular will potentially impact on the program for MC and EN.
SMP timeframes are currently being considered in the AEMC SMP advice to the COAG Energy Council – submissions due on draft advice by 23 July 2015

## Slide 7: Program plan update
Work pkg 1a & 1b
Participant System Development
27/11/ 2015
1/09/2016
1/12/2017
Benefits:
      MC and EN alignment – open procedures only once
      Effective date for both changes is 2 years from final determination
      Comprises 15 month period for participant system and process development post procedure change
Challenges:
      Running MC and EN changes in parallel increases complexity of change.
      Only provides for minimum consultation timeframe allowed in rules – risk that complexities of MC and EN will not have full/robust input from stakeholders.
      Dec/Jan holiday period – significant reduction in time for development and consultation.
Standard procedure consultation period - Version 0.2A

## Slide 8: Program plan update
27/11/ 2015
Benefits:
      MC and EN alignment – open procedures only once
      Provides flexibility to accommodate complexities of MC and EN
      Provides additional time for industry to consult on the procedures
      Considers down-time over Dec/Jan
Challenges:
      Running two changes in parallel increases complexity of change
      Effective dates are extended unless:
        12 months or less is sufficient for industry process and system change
        Industry process and system change can commence earlier
Extended procedure consultation period - Version 0.2B
Work pkg 1a & 1b
Participant System Development
14/12/2016
28/2/2018

## Slide 9: Program plan update - Discussion
The AEMC final determination will set the timeframes for procedure development and the rule effective date.
AEMO, the IEC, participants and providers will have to comply with the dates provided in the rules.
Questions and feedback on the alternative timeline:
      Views on the procedure development and consultation timeframe?
      Ability to progress work over the Dec/Jan period?
      When can industry process and system change reasonably commence?
      What timeframe is reasonable for participant and provider process and system change?
      Views on the potential alignment of MC and EN initiatives?

## Slide 10: Work planning For the period July to November ‘15

## Slide 11: Work planning (jul to nov 2015)
The extension to the final determination for metering competition provides an opportunity for AEMO and interested parties to:
      Develop reference materials to assist procedure development and implementation
      Identify issues and gaps
      Initiate development of processes or documents associated with the changes, but not specified in the rule
      Ensure that all relevant parties are made aware of the change process
      Commence procedure drafting
A number of these matters were discussed in specific working group meetings in June.
Noting risk that the final determination may differ to draft – important to understand main items being considered by the AEMC for the final determination.

## Slide 12: Proposed Work Planning (July to November 2015)
Supporting documentation, process and requirements
Topic | Issue
Process mapping | High level process maps for services (current vs. future), highlighting differences in practical operation and communication between roles
Role mapping (and description) | Role mapping – MC/RP, MDP, MP, FRMP, LNSP – highlighting differences from current state. Role description - where role is new or has changed under draft determination
Terminology / glossary of terms | Terminology / glossary of terms – clarifying up front the use of terms (e.g. remote disconnection vs. de-energisation of supply).
Remote disconnection and reconnection | Progress the process work for remote disconnection and reconnections – stakeholder concerns and jurisdictional safety regulator engagement.
Standard installation information and asset removal form / format | Industry feedback confirmed a desire to develop a standard method and form for provision of: location data for rollout of advanced metering, and asset removal data for NSP asset displacement.

## Slide 13: Proposed Work Planning (July to November 2015)
Specific procedure development prior to final determination
Topic | Issue
Minimum Services Specification (MSS) | As the most significant addition to the SLPs, an early start provides the greatest timeframe for development and consultation
Emergency Priority Procedures (EPP) | As a component of the MSS, the EPP has equal priority. AEMO is seeking initial input on the emergency situations and the services that may need to be considered in those situations, in the context of the rule requirement.
NECF – register reading requirement | NECF change requires changes to the MDFF
MSATS Procedures | Major procedure impacted by MC and EN
Service Level Procedures | Major procedures impacted by MC and EN
Ongoing analysis of other PoC initiatives | Impacts to timelines and resources of other PoC initiatives (e.g. Meter Replacement and SMP rule change development)

## Slide 14: Work planning (jul to nov 2015)
At this time AEMO is considering the priority order and approach.
There is an opportunity to use the current AEMO industry working group meeting schedule in the industry calendar through to November 2015.
AEMO could open existing working groups to all interested parties over this period.
Questions:
      Is there value in AEMO progressing work of this nature ahead of the final determination?
      Do the lists cover the key areas where a ‘head-start’ is beneficial?
      Are there any critical matters that are not covered in the points listed?
      Is the suggestion to utilise existing dates for working groups with open invitations the optimal method to engage with stakeholders over this period?

## Slide 15: Summary of feedback and issues register

## Slide 16: Summary of stakeholder feedback
Since constructing the initial power of choice program plan / schedule, AEMO have requested and received significant feedback and comment from stakeholders.
Recently, more in-depth and specific discussions took place at the series of working group sessions held in June.
Consolidated feedback been provided in the meeting pack, with AEMO responses.
General themes were as follows:
      Need for system and process change timeframes to be considered
      Plan to align initiatives where common procedures require change
      Querying the need for changes to the current B2B system
      Questions relating to materials AEMO will provide, how AEMO intends to consult and the utilisation of the existing working group structures.
There was also an amount of commentary on matters related to policy rather than implementation, procedure change and scheduling.

## Slide 17: Issues for MC implementaiton
Topic | Issue
Consultation | AEMO stakeholder engagement strategy for consultation on procedures to be confirmed
Data cleansing request from COAG | Include the data cleansing activity into the program once approach determined.
Jurisdictional matters | Obtain clarity on approach to Metrology Procedure drafting regarding tables of difference, harmonisation, etc.
Meter churn | Assess the impact of the Meter Replacement rule change
Procedure changes | Ensure references to RP are assessed for context when amending to MC
Sample metering | Ensure that the management of sample metering is considered in the Metrology procedure review
Remote disconnection & reconnection | Determine requirements and method to progress discussions on operation of remote reconnection and remote disconnection service.
Program management | AEMO to confirm PM for the PoC program.
NECF 2 | Consider the inclusion of changes required to the MDFF for NECF2.
Type 4A requirements | Include requirements for contestable “MRIM” installations (e.g. NSRDs)

## Slide 18: Implementation – next steps
Additional items may be added to the issues register as AEMO assesses feedback to the notes from the June working group meetings.
AEMO will assess the feedback provided at this forum and develop program for the period to November 2015.
AEMO will continue to utilise the Retail Market Consultative Forum (RMCF) as the vehicle for communicating with stakeholders.
The RMCF attendance and circulation list is open to all interested parties.
Questions regarding:
      RMCF?
      Issues register?

## Slide 19: Power of choice implementaiton
Questions?