## Slide 1: Power of choice - Implementation Program Industry Testing Phase 3 – Market Trial WORKBOOK
12 May 2017
Presented BY AEMO

## Slide 2: Phase Three Market Trial Testing Cycle 1
Thank you to everyone who provided feedback.
Cycle 1 tests are based on top 20 business scenarios.
  Multiplied by the number of potential retail participants 20 tests * 30 retailers
  Multiplied by Vic (not adopting all changers) and non Vic (adopting all changes)
  Scenarios are based on BAU existing data - i.e. non churn go live status
  The base scenarios are also executed on the basis of churn (MC not the LNSP) for 30 potential retailers
  23 C&I scenarios identified multiplied by 30 potential retailers, again multiplied by Vic and Non Vic
Total number of scenarios for potential execution 3068.
  Each scenario has a minimum of two test cases
  Each scenario has a lapsed execution time of between 2 – 5 days
  Participants not involved in an action directly related to a scenario will still receive notifications if they are a ‘current’ participant and may want/need to check the status of the NMI in there system when scenario is complete

## Slide 3: Next Steps- Phase Three Market Trial Testing
Next Steps
  Registration - to enable all parties to be ready for the start of phase 3 registrations are required by 16 June 2017
  As each retail participant registers, they will be allocated a series of tests and asked to nominate the scenarios they intend to conduct.
  Each Participant who is responsible for the first test case in the scenario needs to define the participant ID they intend to use and draft the tests (based on the process they intend to follow) they would execute to achieve the scenario outcome.
  On the 19 June 2017 a list of all participants registered will be sent to allow retailers to work with registered LNSP’s and or MC’s etc, to define the remaining tests in the scenario. As the tests are defined the Participant ID for the test should also be updated.
  This task is required to be completed and submitted to POC by 04 July 2017 to allow for a review of the number of test cases per participant will then be conducted to ensure everyone has capacity to execute and based on this scenarios can be added or moved into a subsequent test cycle.
Once capacity is understood scenario (04 July 2017) scenarios will be reviewed for cycle 2 and cycle 3.