## Slide 1: Power of choice - Implementation Program EN/MC Industry Testing – Lessons Learned
5 July 2017
Presented BY AEMO

## Slide 2: Timeline - Phase One En/mc Industry Testing
Observation:
  A number of tests were executed directly in MSATS and highlighted that not all companies are aware of or have access to participant Ids for all the roles their companies use.
Recommendation:
  All participants confirm they can sign on to MSATS for their respective companies participant IDs before execution starts.
Observation:
  A number of scenarios required cancelation and restart due to incorrect generation in MSATS which slowed over all execution.
Recommendation:
  Basic Training on how to use MSATS to reduce the amount of rework and assist with identification of valid data.

## Slide 3: Timeline - Phase One En/mc Industry Testing
Observation:
  Searching for test cases in the instance where the participant was not the owner was found to be time consuming and prone to mistakes.
Recommendation:
  A review of test lab to provide easier visibility for participants will be undertaken and options put forward to the next ITWG. Also worth noting would be a walk through of scenarios by all parties involved prior to execution starting.
Observation:
The daily meetings were prompt and effective but only had a small number of participants attending, there was some concern that these would not be practical on a larger scale.
Recommendation:
  Organise smaller groups for the daily testing meetings based on paring would increase efficiency.