## Slide 1: Power of choice - Implementation Program Industry Testing Phase 3 – Market Trial
5 July 2017
Presented BY AEMO

## Slide 2: Timeline - Phase Three Market Trial Testing
Market Trial Test Plan
  AEMO to present draft test plan 29/05/2017
  Receive feedback until 14/06/2017
  Final plan 23/6/2017
Test Scenarios – Cycle 1
  AEMO to create test scenarios for workbook from 22/05/2017 until 09/06/2017
  Review and update workbook from 12/06/2017 to 23/06/2017
  Commence Test Scenario Pairing from 26/06/2017 until 30/07/2017
  Publish Paring 4/07/2017
  Review/update test cases for scenario workshop 12/07/2017
  Publish updated test cases to all participants 14/07/2017

## Slide 3: Timeline - Phase Three Market Trial Testing
Test Scenarios – Cycle 2
  AEMO to create test scenarios for workbook from 03/07/2017 until 07/07/2017
  Participant review and update workbook from 10/07/2017 to 14/07/2017
  Commence Test Scenario Pairing from 18/07/2017
  Publish Paring 19/07/2017
  Review/update test cases for scenario workshop 20/07/2017
  Publish updated to test cases to all participants 24/07/2017
Test Scenarios – Cycle 3
  AEMO to create test scenarios for workbook from 10/07/2017 until 14/07/2017
  Review and update workbook from 17/07/2017 to 21/07/2017
  Commence Test Scenario Pairing from 24/07/2017
  Publish Paring 26/07/2017
  Review/update test cases for scenario workshop 03/08/2017
  Publish to all participants 08/08/2017

## Slide 4: Timeline - Phase Three Market Trial Testing
Test Data Preparation
  Identification of data requirements to commence from 03/07/2017 until 04/08/2017
Test Environment Refresh
  Test Environment Data refresh planned from 31/07/2017 until 07/08/2017
  Data Preparation (new roles etc.) from 07/08/2017 to 18/08/2017
HP Quality Centre Preparation
  Prepare HPQC test cases based on workbooks commencing 24/07/2017
  Complete setup of HPQC (Test Lab, new users, assign test cases, data etc.) from 07/08/2017 to 18/08/2017
Phase 3 Test Execution
  Each test cycle will be 3 weeks in duration with a week between each cycle to provide participants to address issues, fix defects and prepare for the next cycle
    Cycle 1 Execution from 21/08/2017 until 08/09/2017
    Cycle2 Execution from 18/09/2017 until 06/10/2017
    Cycle3 Execution from 16/10/2017 until 03/11/2017