## Slide 1: Power of Choice – Program Consultative Forum (Poc-PCF) Meeting pack
25 November 2016
Presented BY Michael ryan

## Slide 2: Agenda slide
Brief Update
Upcoming activities
Processes
Risk Review
Forward Meeting plan

## Slide 3: Brief Update - achievements
General:
Program is on schedule with good industry engagement at the working groups and feedback provided through formal/ informal channels.
Program:
Website updates have been released http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Power-of-Choice
AEMO Procedures
First stage of the Formal Consultation Procedure Cycle completed with 26 Submissions received on 15 November 2016 for Work Package 2 .
B2B Procedures
B2B Initial draft procedures were published on 27 October 2016.
Systems
SWG established and up and running
AEMO has hosted 3 full SWG sessions and 2 focus group meetings since the end of October
Readiness:
AEMO received the first set of participant readiness reports on 14 November and 20 readiness reports received

## Slide 4: AEMO Program Update – upcoming tasks
Program:
EN and MC Package Two submissions received – next draft out for consultation on 13 December.
B2B Procedure submissions due on 2 December.
Continued engagement with SWG on technical capability.
Continued readiness discussions.
AEMO Procedures:
POC-PWG meeting on 20 December to discuss key issues from the Draft Determination.
Draft Determination to be published on 13 December 2016
B2B Procedures:
First stage consultation ends on 2 December 2016
Draft procedures to be published on 23 December 2016
Technical Delivery specification draft to be completed for publication on 23 December 2016
Systems:
SWG will provide feedback to the B2B-WG.
Next focus group session is scheduled for 28 November 2016 and full SWG on 6 December 2016.
AEMO is planning to run through the current solutions and decisions made by the group with the B2B working group on 23 November 2016.
Readiness:
Readiness reporting trial underway November 2016 – Participant feedback is encouraged to update this process.
AEMO is hosting an information session on 28 November 2016 to cover the (4) POC rule changes that are relevant to AEMO’s POC implementation program, as well as overview the POC procedural changes made under Work Package 1 relating to metering.

## Slide 5: Procedure stream update
Work Package 2
15 November - 1st stage submissions closed. 26 submissions were received – click here for a link to all the submissions on AEMO’s website.
13 December - AEMO to publish the Draft Determination and the start of 2nd stage consultation.
20 December - next POC-PWG meeting (via teleconference) to discuss key issues from the Draft Determination.
16 January – 2nd stage submissions close.
28 February – AEMO to publish the Final Determination.
AEMO will release all other Package 2 guidelines and checklists not subject to NER consultation following the publication of the Draft Determination.

## Slide 6: B2B Procedures STREAM UPDATE
IEC and B2B Working Group recommended AEMO to publish initial draft procedures on 27 Oct
First stage consultation ends on 2 December – Draft procedures to be published on 23 December
Technical Delivery specification
  Conducted a B2B WG workshop on 23 Nov to discuss drafting recommendations from Systems Working Group – draft to be completed for publishing on 23 December
Legal Advice to IEC
  IEC have received legal advice and have drafted a Directive for B2B procedure drafting – B2B WG and AEMO will redraft procedures to meet this directive
First Stage Review period
  B2B WG and AEMO have a compressed timeframe to collate and respond to submissions and redraft procedures
  Early Reponses from industry are welcome – we already have 1 response.

## Slide 7: readiness stream update
Industry readiness progress reports
  AEMO received the first set of participant readiness reports on 14 November.
  At least 20 readiness reports received, covering several participant roles and operating across multiple jurisdictions.
  AEMO is currently reviewing the individual reports in order to collate an industry-wide market readiness report.
  Generally speaking, the reports suggest participants’ high-level assessment of the regulatory changes are underway and they are following public consultation processes on procedural changes to further inform their readiness planning.
  The reports will be reviewed by the Readiness Working Group on Monday 28 November at its 1400–1530 AEDT teleconference/webinar meeting.
  The reports will be publically available from AEMO’s website after the Readiness Working Group meeting.
  The reporting template covers 6 broad categories (including 20 detailed sub-categories): Assessment and preparation; Legal, regulatory, contractual and policy; People; Business processes; Market systems; and Transition planning.
  The next set of reports are due to AEMO on 16 January (a consolidated December/January report).
Participant Information Session
  AEMO is hosting an information session on Monday 28 November at 1000–1200 AEDT via teleconference/webinar.
  The information session will overview the (4) POC rule changes that are relevant to AEMO’s POC implementation program, as well as overview the POC procedural changes made under Work Package 1 relating to metering.
  The target audience is program/readiness managers who have not been involved in AEMO’s POC workings groups and consultative processes to date, and are likely to become involved in POC implementation activities in the next year.
  AEMO has invited each Readiness Working Group Member to coordinate attendance on behalf of their organisation.
  The presentation slides will be publically available from AEMO’s website after the session for interested parties.
  The participant information sessions form a six-part information series under the Market Readiness Strategy.

## Slide 8: Watching briefs
Vic Govt. Consultation on Competition in Metering
  Potential alterations to Procedures & systems to accommodate outcomes
Safety regulation
  Draft B2B Procedures provide the framework for jurisdictional bodies to amend jurisdictional safety arrangements as required;
  Harmonisation across jurisdictions would provide participants clarity on how to use Procedures.

## Slide 9: PCF Processes:
Risk & Issues – management plan
  Raised by participants / working groups / PCF / AEMO
  Reviewed, collated and published by AEMO
  Reviewed and monitored by PCF
Raising discussion points / PCF agenda items
  Paper > one week prior to PCF
  AEMO circulate with meeting pack, make agenda item
  Paper should:
    Purpose
    Background: brief overview
    Body: issues/problem/discussion points, identify affected parties
    Provide recommendation(s)
  Keep it succinct and to a few pages

## Slide 10: PCF Forward Plan

## Slide 11: Forward Meeting Plan
POC-PCF meeting dates | Dates
POC-PCF Meeting #1 | 16-Sep-16
POC-PCF Meeting #2 | 7-Oct-16
POC-PCF Meeting #3 | 15-Nov-16
POC-PCF Meeting #4 | 15-Dec-16
POC-PCF Meeting #5 | 06-Feb-17
POC-PCF Meeting #6 | 23-Feb-17
POC-PCF Meeting #7 | 23-Mar-17
POC-PCF Meeting #8 | 20-Apr-17
POC-PCF Meeting #9 | 25-May-17
POC-PCF Meeting #10 | 22-Jun-17
POC-PCF Meeting #11 | 27-Jul-17
POC-PCF Meeting #12 | 24-Aug-17
POC-PCF Meeting #13 | 28-Sep-17
POC-PCF Meeting #14 | 26-Oct-17
POC-PCF Meeting #15 | 23-Nov-17
POC-PCF Meeting #16 | 14-Dec-17
POC-PCF forward meeting plan:
Monthly meetings
Ad-hoc meetings can be arranged
Facilities:
Melbourne, Sydney, Brisbane, Adelaide offices
Video conference
Webinar (when required)

## Slide 12: Questions & Contacts
Program:
Antara Mascarenhas
Ben Healy
Mike Ryan
Procedures:
Tim Sheridan
B2B Procedures:
Chris Cormack
Readiness:
Slavko Jovanoski
Kerry Galloway
Systems:
James Kevil
Email:
poc@aemo.com.au

## Slide 13: Program Overview

## Slide 14
2015 |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 |  |  |  |  |  |  |  |  |  |  |  | 2018 | 
JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Working Groups’
Today
Planned Transitional and New IEC Meetings
Power of Choice (PoC) Program Overview
High Level Program V4.5 – 17 November 16
For Information: poc@aemo.com.au
26 Nov
MC
Final Determination
17 Dec
EN Final Determination
MRP Draft Determination
10 Mar
MRP
Final Determination
1 Sep
EN & MC & MRP
Procedures Published
1 Mar
MC
Registration & EN MSL and Accreditation Documentation Published
1 Dec
EN & MC & MRP & B2B
Effective Date (Go-Live)
DNSPs & Retailers to publish amended standard contracts
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
Oct
SMP Advice published
EN/MC/MRP WP 1 Procedure Consultation
EN/MC/MRP Package 2 Development
EN/MC/MRP WP 2
Procedure Consultation
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Package 3 ‘As Built’ Development
WP 3 & ‘As built’ Procedure Consultation (If required)
MC /
EN /
MRP
30 Jun
SMP Final Determination
1 Aug
IEC Election Procedures Finalised
MC B2B Recommendation
1 Sep
IEC Election Complete - IEC Formed
1 May
B2B – IEC recommends B2B Procedures Finalised
07 Apr
SMP Draft Determination
1 Dec
MC & EN Ring fencing and network exemption guidelines
1 Sep
DNSPs to publish standard terms and conditions on which it will act as the initial Metering Coordinator
AEMO Requirements
SMP Conceptual IT Designs
SMP B2B Procedure Consultation
TRANS IEC
IEC Election
Election Procedures
& Operating Manual
Fee methodology *(if required)
1 Jun
B2B – AEMO publish B2B Procedures & Accreditation Process
Heightened Support
Procedures
Market Readiness
Supporting Activities
IT Systems
P
P
P
P
Market Readiness Strategy
Industry Training
Industry Testing
Transition / Cut Over
AEMO Design
All - IT Development / Internal Testing
Industry Testing
P
P
SMP Procedure Development
P
EN/MC/MRP Package 1 Development
MC Draft Procedures
P
Publish
SMP
Plan
Execute
Plan
Execute
Plan
Execute
Registration & Accreditation
Pre-Prod Release
Trans
Trans
Prod Release
P
P
P
AER - Electricity ring-fencing guideline 2016
Readiness Reporting Commences
Milestone
Working group meeting
Proposed IEC Meetings (Trans & New)
Program Milestones
10 Sep
MRP Direction paper published
EN Draft Determination
P
P

## Slide 15
2016 |  |  |  |  |  |  |  |  | 2017 |  | 
APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR
Planned Transitional and IEC Meetings
Today
Power of Choice (PoC) Program Overview – Procedure Workstreams (6 month outlook)
High Level Program V4.5 – 17 November 16
For Information: poc@aemo.com.au
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
AEMO Review
Stage 2
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Group 1
Accreditation / Deregistration Procedures
Consultation Stage 1
Stage 3
AEMO Review
Stage 4
P
P
P
WORK PACKAGE 1
AEMO Review
Stage 2
Consultation Stage 1
Stage 3
AEMO Review
Stage 4
P
P
P
WORK PACKAGE 2
Group 2
ENM SLP / Accred Procedures
Group 3
NMI Procedure / Glossary
Communication Mapping
30 Jun
SMP Final Determination
29 Jun
AEMO WP1 publishes Draft Determination
Scope / Procedure Structure
Payload / Transaction Design
AEMO Procedure Drafting / Updating
MC /
EN /
MRP
Procedures
Work Package #2
B2B
Procedures
Establish WG
P
Publish
Milestone
Working group meeting
Proposed IEC Meetings (Trans & New)
MC /
EN /
MRP
Procedures
Work Package #1
22 Apr
WP1 Consultation begins
31 May
WP1 Submissions Close
20 Jul
WP1 second stage submissions close
31 Aug
WP1 AEMO publishes final determination
17 Oct
IEC ‘Request’ AEMO to conduct Procedure Consultation
10 Oct
WP2 Consultation begins
15 Nov
WP2 Submissions Close
13 Dec
AEMO WP2 publishes Draft Determination
16 Jan
WP2 second stage submissions close
B2B Review Stage 2
Consultation Stage 1
Stage 3
B2B Review
Stage 4
P
P
P
B2B PROCEDURES
W/C 19 Dec
B2B IEC endorse draft procedures for consultation
W/C 20 Feb
IEC ‘Recommends’ final Procedures
28 Feb
MC
Registration & EN MSL and Accreditation Documentation Published
Trans
Trans
Industry Review
27 Oct
B2B Consultation begins
02 Dec
B2B Submissions Close
23 Dec
B2B AEMO publishes Draft Determination
20 Jan
B2B second stage submission close
06 Mar
B2B Procedures Published
Iterative process

## Slide 16: Power of Choice Milestones
Deliverable / Milestone | Project / Stream | Description / Notes | Planned date | Expected date | Status
AEMC publish MRP Directions paper & EN draft determination | EN, MRP |  | 10 Sep 15 |  | 
AEMC publish SMP advice paper | SMP |  | Early-Oct 15 | 10 Oct 15 | 
AEMC publish final rule determination | MC |  | 24 Nov 15 | 26 Nov 15 | 
AEMC release final determination | EN |  | 17 Dec 15 |  | 
AEMC release draft determination | MRP |  | 17 Dec 15 |  | 
AEMC publish draft rule determination | SMP |  | Early-Feb 16 | 07 Apr 16 | 
AEMC publish final rule determination | MRP |  | 10 Mar 16 |  | 
AEMO pre-consultation workshops conclude | MC,EN,MRP |  | 11 Mar 16 |  | 
AEMO releases Pre-Consultation Paper | MC,EN,MRP |  | 08 Apr 16 |  | 
AEMO publishes notice first stage consultation | MC,EN,MRP |  | 22 Apr 16 |  | 
AEMC publish final rule determination | SMP |  | 26 May 16 | 30 Jun 16 | 
AEMO concludes first stage consultation | MC,EN,MRP |  | 31 May 16 |  | 
AEMO commences Readiness Work Stream engagement | MC,EN,MRP |  | 20 Jun 16 | 21 Jun 16 | 
AEMO publish draft procedure determination | MC,EN,MRP |  | 30 Jun 16 | 29 Jun 16 | 
AEMO concludes second stage consultation | MC,EN,MRP |  | 15 Jul 16 | 20 Jul 16 | 
AEMO publishes final procedure determination | MC,EN,MRP | No later than 1 Sep 16 | 26 Aug 16 | 31 Aug 16 | 
AEMO publishes notice first stage consultation (WP2) | MC,EN,MRP |  | 10 Oct 16 |  | 
AEMO publishes notice first stage consultation | B2B: All |  | 10 Oct 16 | 27 Oct 16 | 
IEC Election complete – IEC formed | SMP | Noting this is a no later than date. | 01 Sep 16 | 01 Sep 16 | 
AEMO finalises Industry Readiness Reporting Plan | Readiness |  | 06 Oct 16 |  | 
AEMO commences Systems Work Stream engagement | Systems |  | 07 Oct 16 |  | 
Readiness Reporting commences | Readiness |  | 14 Nov 16 |  | 
AEMO concludes first stage consultation | MC,EN,MRP |  | 15 Nov 16 |  | 
Notes: Intent to Publish

## Slide 17: Power of Choice Milestones
Deliverable / Milestone | Project / Stream | Description | Planned date | Expected date | Status
AEMO concludes first stage consultation | B2B: All |  | 15 Nov 16 | 02 Dec 16 | 
AEMO commences consultation of Fee Methodology | All |  | Nov 16 | 03 Nov 16 | 
AER publishes ring fencing & network exemption guidelines | - |  | 01 Dec 16 |  | 
AEMO publish draft procedure determination | MC,EN,MRP |  | 13 Dec 16 |  | 
AEMO publish draft procedure determination | B2B: All |  | 13 Dec 16 | 23 Dec 16 | 
System implementation period commences | All |  | Mid Dec 16 |  | 
AEMO concludes Fee Methodology first stage consultation | All |  | 16 Dec 16 |  | 
AEMO concludes second stage consultation | MC,EN,MRP |  | 30 Dec 16 | 16 Jan 17 | 
AEMO concludes second stage consultation | B2B: All |  | 30 Dec 16 | 20 Jan 17 | 
AEMO seeks IEC recommendation for B2B changes | B2B: All | TBC Preceding AMEO Feb Board | 22 Jan 17 | Late Feb 17 | 
AEMO publishes final procedure determination | MC,EN,MRP | Obligation is no later than 1 Mar 17 | 01 Mar 17 | 28 Feb 17 | 
AEMO publishes final procedure determination | B2B: All | Obligation is no later than 1 Jun 17 | 01 Mar 17 | 06 Mar 17 | 
AEMO publishes Fee Methodology (participant fee structure) | SMP | If required | 01 Mar 17 |  | 
Commencement of registration / accreditation activities | Readiness | To be determined in readiness strategy | Mar 17 |  | 
Industry testing period detailed planning commences | Readiness |  | Mar 17 |  | 
Industry detailed cut-over and transition planning commences | Readiness |  | Apr 17 |  | 
Industry testing and trial period commences | Readiness | To be determined in test plan | Aug 17 |  | 
DNSPs publish T&C’s on which it will act as the initial MC | MC |  | 1 Sep 17 |  | 
Industry Accreditation and Registration activities completed | Readiness |  | Oct 17 |  | 
Industry cut-over and transition plan completed | Readiness |  | Oct 17 |  | 
DNSPs publish distributor deemed standard connection contracts | MC |  | 1 Dec 17 |  | 
Retailers publish Elect & Gas standard retail contracts | MC |  | 1 Dec 17 |  | 
PoC Effective date | All |  | 1 Dec 17 |  | 
Notes: Intent to Publish

## Slide 18: PoC - Program Overview Version history
This table summarises the changes between the Program Overview as information changes or becomes available.
Version | Date | Amendments
3.2 | 11 Feb 16 | Updated SMP DD and FD dates in accordance with AEMC update 11 Feb 16
3.3 | 19 Feb 16 | Updated DRM DD date from 18 Feb to 9 Jun – Removed the DRM FD until advice is available from AEMC Included milestone for ring-fencing & exemption guidelines and DNSPs to publish standard T&C’s
3.4 | 04 Mar 16 | Removed MTR following guidance published by AEMC on 25 Feb 2016 Separated initial B2B consultation – scheduled to begin on 8 Apr Amended dates according to AEMC update (2 March 2016) – SMP dates moved back/DRM FD date released
3.5 | 22 Apr 16 | Removed DRM/ASU until further guidance – expanded timeline to focus on the Dec 2017 delivery and heightened support into Q1 2018 Combined MC/EM/MRP into single project Included SMP draft rule dates as published by AEMC – included proposed timeline for conducting SMP procedure consultation
3.6 | 10 May 16 | Expanded key milestone dates.
3.7 | 1 Jun 16 | Included proposed dates for testing periods (Aug 17 – Nov 17). Expanded on proposed fee methodology timetable to accommodate consultation process.
4.0 | 10 Jun 16 | Arranged Program Overview into key workstreams Removed IEC milestones in lieu of SMP Draft Determination
4.1 | 23 Jun 16 | Increased AEMO’s “design phase” to carry on until the end of consultation (1 Mar 17) Altered WP 1 Procedure Change Process dates to accommodate additional four business days of consultation.
4.2 | 19 Aug 16 | Updated tracking; removed dates associated with B2B Procedures as a result of B2B Framework Rule being published
4.3 | 02 Sep 16 | Updated B2B Procedure consultation with AEMO’s proposed dates (pending IEC approval)
4.4 | 10 Oct 16 | Updated terminology – added ‘6 month outlook’ for Procedure development / consultation processes Updated key dates in relation to AEMO WP2 Procedures and B2B Procedure development / consultation Included key dates identified in Readiness strategy
4.5 | 17 Nov 16 | Amended dates for Fee Methodology consultation Updated B2B Procedure Consultation dates

## Slide 19: Risk Workshop