## Overview
Version | 1
Last Updated By: | AEMO
Date: | 2016-08-17
Power of Choice Industry Risks & Issues Register
Purpose
The Power of Choice Industry Risks & Issues Register aims to facilitate the monitoring and reporting on industry risks and issues identified within the program.
This register contains 3 tabs: • Overview (this tab) – provides a brief introduction to the register. Also contains the register version number as well as the date it was last updated. • Industry Risk Register – contains all Power of Choice Industry Risks as detailed in the Power of Choice Industry Management Plan. • Industry Issue Register – contains all Power of Choice Industry Issues as detailed in the Power of Choice Industry Management Plan.

## Industry Risk Register
ID# | Status | Work stream | Initiating Party | Title | Description | Likelihood | Consequence | Rating | Actions | Owner | Date Raised | Date Last Updated | Target Resolution Date | Date Resolved | Related Issue ID # | Related Issue Title | Comments
R01 | Open | B2B Procedures | B2B-WG | Delay to B2B Consultation Process | There is a risk that a significant issue is raised requiring an extension to the first stage consultation review period. • The first round review period can be extended by a further 25 business day. • There is no contingency in the timeframe, any delay would directly impact the proposed publication date of Monday 6th March 17 and subsequent system builds. | Low | High | Medium | • AEMO will make available as much information prior to consultation as possible. • The B2B-WG will collate any issues raised during the consultation to seek to address any unforeseen issues as they arise |  | 2016-09-02 | 2016-09-22
R02 | Open | Program | AEMO | Risk that there is one or more participants that aren’t ‘ready’ at go-live | There is a risk that one or more participants are have inadequately prepared systems to operate in the market within the new market conditions at Rules effective date. | Medium | Medium | Medium | • AEMO facilitates the development of a comprehensive testing plan that seeks to provide the opportunity for all market participants to interactively test their systems. This activity may include the conduct of ‘Market Trial’ which seeks to replicate the operation of business as usual (BAU) market operation and functionality. • AEMO will provide reports of test outcomes and progress against planned milestones. |  | 2016-07-27
R03 | Closed | B2B Procedures | B2B-WG | Timetable for delivery of B2B procedures | Following the release of the AEMC’s final 'Updating B2B Framework' rule change determination, the timetable to deliver the B2B changes is aggressive | Medium | Medium | Medium | • To manage this risk, the B2B working group is being established as soon as practicable and guided by the IEC decisions around priorities as discussed at the first transitional IEC meeting. • Key issues will be escalated to the IEC for directions, should issues arise. |  | 2016-07-27 | 2016-09-02 |  | 2016-09-02 |  |  | Closed and risk updated under R04
R04 | Open | B2B Procedures | B2B-WG | Delays in Drafting B2B Procedures | There is a risk that Procedures won’t be ready on the 20 October to begin consultation. • Delay to the commencement of consultation directly impacts on the preparation of the draft procedures by end of December 16. • The consultation process would occur over Christmas/NY shutdown periods. • Direct delays could occur to the subsequent system builds. | Medium | High | High | • AEMO has recently appointed new staff members in order to facilitate procedure development • AEMO will make available as much information prior to consultation as possible. • Scheduled B2B-WG review periods |  | 2016-09-02 | 2016-09-22
R05 | Open | Program | AEMO | Risk of a substantial procedural issue being discovered during system development or testing | There remains a possibility that industry testing exposes a previously un-identified procedural issue that could impact efficient market operations post go-live | Medium | Low | Low | • AEMO plans to conduct an ‘as built’ procedure consultation throughout August to December 2017 that aims at capturing and incorporating any agreed amendments required to facilitate go-live • Scheduled B2B-WG review periods | AEMO | 2016-07-27 | 2016-10-04
R06 | Open | B2B Procedures | B2B-WG | Jurisdictional variations | There is a risk that the B2B-WG haven't adequately considered jurisdictional nuisances to processes. • Inadequate Procedures released into initial consultation • Significant re-work required for second stage consultation | Low | Medium | Low | • B2B-WG have invited representation into specific working group sessions prior the commencement of formal consultation • B2B-WG members encouraged to circulate and discuss changes with the broader industry they represent. | B2B-WG | 2016-09-02 | 2016-10-04
R07
R08
R09
R10
R11
R12
R13
R14
R15
R16
R17
R18
R19
R20
R21
R22
R23
R24
R25
R26
R27
R28
R29
R30
R31
R32
R33
R34
R35
R36
R37
R38
R39
R40
R41
R42
R43
R44
R45
R46
R47
R48
R49
R50

## Industry Issue Register
ID # | Status | Workstream | Initiating Party | Title | Description | Rating | Actions | Owner | Date Raised | Date Last Updated | Target Resolution Date | Date Resolved | Related Risk ID # | Related Risk Title | Comments
I01
I02
I03
I04
I05
I07
I08
I09
I10
I11
I12
I13
I14
I15
I16
I17
I18
I19
I20
I21
I22
I23
I24
I25
I26
I27
I28
I29
I30
I31
I32
I33
I34
I35
I36
I37
I38
I39
I40
I41
I42
I43
I44
I45
I46
I47
I48
I49
I50

## Lookups (hidden)
| Status | Stream |  | Likelihood | Consequence
| Open | Procedures |  | Low | Low
| Closed | Technical |  | Medium | Medium
|  | Readiness |  | High | High
Program
B2B Procedures
Consequence
| Option | Low | Medium | High
Likelihood | High | Medium | Medium | High
| Medium | Low | Medium | High
| Low | Low | Low | Medium