## Input Recieved for Risk Session
ID# | Status | Work stream | Initiating Party | Title | Description | Likelihood | Consequence | Rating | Actions | Owner | Date Raised | Date Last Updated | Target Resolution Date | Date Resolved | Related Issue ID # | Related Issue Title | Comments
R07 | New | B2B Procedures |  | B2B Procedure Quality Impacted due to compressed timeframes | There is a risk that B2B procedure updates are incomplete and/or do not work effectively. This risk may be higher than normal due to the large number of participants involved, the complexity of this change and compressed timeframes for procedure development. Impacts include late design changes, issues during testing or post go-live customer and operational impacts | High | High | High | • suggest early test scenario planning and then testing procedures with a range of scenarios prior to final consultation |  | 2016-11-23
R08 | New | B2B Procedures |  | Work package 1 procedures impacted by B2B procedure updates | B2B procedure updates impact CATS procedures necessitating further consultation. May impact participant design and build that is already underway. | Medium | High | High |  |  | 2016-11-23
R09 | New | B2B Procedures |  | Industry benefits from faster B2B transaction processing via eHub not realised due to limited uptake of eHub solution | Participants may be slow to develop faster B2B service offerings. This may erode expected customer benefits of having better access to meter information | Medium | Medium | Medium | • AEMO could consider imposing an end date on existing message based processing for some or all message types |  | 2016-11-23
R10 | New | Readiness |  | Industry testing impacted due to late participant accreditation | MC accreditation timelines overlap with industry testing timeframes. As such, there is an increased risk of changes occurring while industry testing is in progress. This may impact test planning and execution. Impacts may also include delays to test completion and a higher rate of defects and operational issues post go-live | High | High | High | • consider pre-certification and specific entry criteria for industry testing |  | 2016-11-23
R11 | New | Readiness |  | Industry test timeframe is too compressed given size of change and number of participants involved | Power of Choice is a complex change with many new and existing participants. NARGP for example had approx. 5 months for industry testing. PoC is a larger change but allows only 3 months for testing. There is a significant risk that this duration is too short for comprehensive test coverage. Impacts include significant system and operational issues post go-live | High | High | High | • create more detailed plan for testing now - needs to consider AEMO approvals, market notices lead times • ensure test planning commences as early as possible • consider pre-certification test runs • sandpit environments? • clear test prioritisation |  | 2016-11-23
R12 | New | Procedures |  | Safety protocols for de-energisation and re-energisation not agreed at national level in time for PoC | There is a risk that safety protocols for de-energisation and re-energisation are not agreed at national level in time for PoC. This may impact solution design plus benefits associated with a harmonised approach for re-en/de-energisation processes | High | High | High | • create and publish a plan with dates for standards to be agreed |  | 2016-11-23
R13 | New | Readiness |  | WP3 updates and/or transition planning identifies changes that affect WP1 or WP2 procedures | There is a risk that impacts to WP1 and WP2 are identified when WP3 and/or transition plans are developed. Impacts may include limited or no time to respond | Low | High | Medium |  |  | 2016-11-23
R14 | New | B2B Procedures |  | New connections communication process sub optimal | There are substantial changes to new connections processes including new steps and additional parties that need to communicate effectively. (eg, Retail, MP, MC, LNSP - allocate NMI, install line, install meter, energisation etc). This increases the risk of communication issues causing delays that impact customers and result in operational impacts. | High | High | High | • ensure streamlined B2B communications process • use "Lean" practices to ensure efficiently designed process (eg, eliminate waste and re-work, cater for and handle exceptions efficiently etc) |  | 2016-11-23
R15
R16
R17
R18
R19
R20
R21
R22
R23
R24
R25
R26
R27
R28
R29
R30
R31
R32
R33
R34
R35
R36
R37
R38
R39
R40
R41
R42
R43
R44
R45
R46
R47
R48
R49
R50

## Lookups (hidden)
| Status | Stream |  | Likelihood | Consequence
| Open | Procedures |  | Low | Low
| Closed | Technical |  | Medium | Medium
|  | Readiness |  | High | High
Program
B2B Procedures
Consequence
| Option | Low | Medium | High
Likelihood | High | Medium | Medium | High
| Medium | Low | Medium | High
| Low | Low | Low | Medium