## Slide 1: EXECUTIVE forum
DATE: 15 DECEMBER 2016
TIME: 10.30 AM – 12.00 PM
VENUE: AEMO OFFICES, TELECONFERENCE

## Slide 2: Agenda
Welcome and Introduction
Apologies and Minutes
Power of Choice – Program Update
Work Stream Updates
Meeting Close

## Slide 3: AEMO Program Update
General:
B2B Procedure Consultation is underway and working through submissions from the Initial Draft.
AEMO Procedures
Package 2 consultation – 26 first stage submissions have been received.
AEMO intends on publishing the Draft Determination on 13th December.
POC-PWG meeting on 20 December to discuss key issues from the Draft Determination.
B2B Procedures
B2B-WG consultation underway – 30 first stage submissions have been received.
AEMO intends on publishing the Draft Determination on 23rd December.
Systems
Notified Parties solution presented to the B2B working group.
New Interfacing protocols & interoperability solution identified by the focus group.
Readiness:
Considering split industry testing (EN/MC and e-hub).
Refining the Reporting Template.

## Slide 4: AEMO Program Update – upcoming tasks
Program:
PCF next session will be 15 December (PM).
AEMO Procedures (Package 2):
POC-PWG meeting on 20 December to discuss key issues from the Draft Determination.
B2B Procedures:
B2B WG are considering guidance received from the IEC. Updates to Procedures will be incorporated into Draft scheduled for release on 23rd December.
Systems:
SWG focus is contributing to the development of the Technical Design Specification (TDS).
AEMO will present the proposed schema changes required for B2B & B2M to the group on 19th December.
LVI & Peer to Peer discussions planned for the new year.
Readiness:
Review first draft of Registration & Accreditation Plan on the 13th Feb.
Review first draft of Industry Testing Plan for e-Hub (market trial) on 8th Mar.

## Slide 5
2015 |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 |  |  |  |  |  |  |  |  |  |  |  | 2018 | 
JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Working Groups’
Today
Planned Transitional and New IEC Meetings
Power of Choice (PoC) Program Overview
High Level Program V4.6 – 16 December 16
For Information: poc@aemo.com.au
26 Nov
MC
Final Determination
17 Dec
EN Final Determination
MRP Draft Determination
10 Mar
MRP
Final Determination
1 Sep
EN & MC & MRP
Procedures Published
1 Mar
MC
Registration & EN MSL and Accreditation Documentation Published
1 Dec
EN & MC & MRP & B2B
Effective Date (Go-Live)
DNSPs & Retailers to publish amended standard contracts
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
Oct
SMP Advice published
EN/MC/MRP WP 1 Procedure Consultation
EN/MC/MRP Package 2 Development
EN/MC/MRP WP 2
Procedure Consultation
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Package 3 ‘As Built’ Development
WP 3 & ‘As built’ Procedure Consultation (If required)
MC /
EN /
MRP
30 Jun
SMP Final Determination
1 Aug
IEC Election Procedures Finalised
MC B2B Recommendation
1 Sep
IEC Election Complete - IEC Formed
1 May
B2B – IEC recommends B2B Procedures Finalised
07 Apr
SMP Draft Determination
1 Dec
MC & EN Ring fencing and network exemption guidelines
1 Sep
DNSPs to publish standard terms and conditions on which it will act as the initial Metering Coordinator
AEMO Requirements
SMP Conceptual IT Designs
SMP B2B Procedure Consultation
TRANS IEC
IEC Election
Election Procedures
& Operating Manual
Fee methodology *(if required)
1 Jun
B2B – AEMO publish B2B Procedures & Accreditation Process
Heightened Support
Procedures
Market Readiness
Supporting Activities
IT Systems
P
P
P
P
Market Readiness Strategy
Industry Training
Industry Testing
Transition / Cut Over
AEMO Design
All - IT Development / Internal Testing
Industry Testing
P
P
SMP Procedure Development
P
EN/MC/MRP Package 1 Development
MC Draft Procedures
P
Publish
SMP
Plan
Execute
Plan
Execute
Plan
Execute
Registration & Accreditation
Pre-Prod Release
Trans
Trans
Prod Release
P
P
P
AER - Electricity ring-fencing guideline 2016
Readiness Reporting Commences
Milestone
Working group meeting
Proposed IEC Meetings (Trans & New)
Program Milestones
10 Sep
MRP Direction paper published
EN Draft Determination
P
P

## Slide 6
2016 |  |  |  |  |  |  |  |  | 2017 |  | 
APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR
Planned Transitional and IEC Meetings
Today
Power of Choice (PoC) Program Overview – Procedure Workstreams (6 month outlook)
High Level Program V4.6 – 16 December 16
For Information: poc@aemo.com.au
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
AEMO Review
Stage 2
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Group 1
Accreditation / Deregistration Procedures
Consultation Stage 1
Stage 3
AEMO Review
Stage 4
P
P
P
WORK PACKAGE 1
AEMO Review
Stage 2
Consultation Stage 1
Stage 3
AEMO Review
Stage 4
P
P
P
WORK PACKAGE 2
Group 2
ENM SLP / Accred Procedures
Group 3
NMI Procedure / Glossary
Communication Mapping
30 Jun
SMP Final Determination
29 Jun
AEMO WP1 publishes Draft Determination
Scope / Procedure Structure
Payload / Transaction Design
AEMO Procedure Drafting / Updating
MC /
EN /
MRP
Procedures
Work Package #2
B2B
Procedures
Establish WG
P
Publish
Milestone
Working group meeting
Proposed IEC Meetings (Trans & New)
MC /
EN /
MRP
Procedures
Work Package #1
22 Apr
WP1 Consultation begins
31 May
WP1 Submissions Close
20 Jul
WP1 second stage submissions close
31 Aug
WP1 AEMO publishes final determination
17 Oct
IEC ‘Request’ AEMO to conduct Procedure Consultation
10 Oct
WP2 Consultation begins
15 Nov
WP2 Submissions Close
13 Dec
AEMO WP2 publishes Draft Determination
16 Jan
WP2 second stage submissions close
B2B Review Stage 2
Consultation Stage 1
Stage 3
B2B Review
Stage 4
P
P
P
B2B PROCEDURES
W/C 19 Dec
B2B IEC endorse draft procedures for consultation
W/C 20 Feb
IEC ‘Recommends’ final Procedures
28 Feb
MC
Registration & EN MSL and Accreditation Documentation Published
Trans
Trans
Industry Review
27 Oct
B2B Consultation begins
02 Dec
B2B Submissions Close
23 Dec
B2B AEMO publishes Draft Determination
20 Jan
B2B second stage submission close
06 Mar
B2B Procedures Published
Iterative process

## Slide 7: PoC - Program Overview Version history
Deliverable / Milestone | Project / Stream | Description / Notes | Planned date | Expected date | Status
AEMC publish MRP Directions paper & EN draft determination | EN, MRP |  | 10 Sep 15 |  | 
AEMC publish SMP advice paper | SMP |  | Early-Oct 15 | 10 Oct 15 | 
AEMC publish final rule determination | MC |  | 24 Nov 15 | 26 Nov 15 | 
AEMC release final determination | EN |  | 17 Dec 15 |  | 
AEMC release draft determination | MRP |  | 17 Dec 15 |  | 
AEMC publish draft rule determination | SMP |  | Early-Feb 16 | 07 Apr 16 | 
AEMC publish final rule determination | MRP |  | 10 Mar 16 |  | 
AEMO pre-consultation workshops conclude | MC,EN,MRP |  | 11 Mar 16 |  | 
AEMO releases Pre-Consultation Paper | MC,EN,MRP |  | 08 Apr 16 |  | 
AEMO publishes notice first stage consultation | MC,EN,MRP |  | 22 Apr 16 |  | 
AEMC publish final rule determination | SMP |  | 26 May 16 | 30 Jun 16 | 
AEMO concludes first stage consultation | MC,EN,MRP |  | 31 May 16 |  | 
AEMO commences Readiness Work Stream engagement | MC,EN,MRP |  | 20 Jun 16 | 21 Jun 16 | 
AEMO publish draft procedure determination | MC,EN,MRP |  | 30 Jun 16 | 29 Jun 16 | 
AEMO concludes second stage consultation | MC,EN,MRP |  | 15 Jul 16 | 20 Jul 16 | 
AEMO publishes final procedure determination | MC,EN,MRP | No later than 1 Sep 16 | 26 Aug 16 | 31 Aug 16 | 
AEMO publishes notice first stage consultation (WP2) | MC,EN,MRP |  | 10 Oct 16 |  | 
AEMO publishes notice first stage consultation | B2B: All |  | 10 Oct 16 | 27 Oct 16 | 
IEC Election complete – IEC formed | SMP | Noting this is a no later than date. | 01 Sep 16 | 01 Sep 16 | 
AEMO finalises Industry Readiness Reporting Plan | Readiness |  | 06 Oct 16 |  | 
AEMO commences Systems Work Stream engagement | Systems |  | 07 Oct 16 |  | 
Readiness Reporting commences | Readiness |  | 14 Nov 16 |  | 
AEMO concludes first stage consultation | MC,EN,MRP |  | 15 Nov 16 |  | 

## Slide 8: PoC - Program Overview Version history
Deliverable / Milestone | Project / Stream | Description | Planned date | Expected date | Status
AEMO concludes first stage consultation | B2B: All |  | 15 Nov 16 | 02 Dec 16 | 
AEMO commences consultation of Fee Methodology | All |  | Nov 16 | 03 Nov 16 | 
AER publishes ring fencing & network exemption guidelines | - |  | 01 Dec 16 |  | 
AEMO publish draft procedure determination | MC,EN,MRP |  | 13 Dec 16 |  | 
AEMO publish draft procedure determination | B2B: All | No later than 4 January 2017 | 13 Dec 16 | 23 Dec 16 | 
System implementation period commences | All |  | Mid Dec 16 |  | 
AEMO concludes Fee Methodology first stage consultation | All |  | 16 Dec 16 |  | 
AEMO concludes second stage consultation | MC,EN,MRP |  | 30 Dec 16 | 16 Jan 17 | 
AEMO concludes second stage consultation | B2B: All |  | 30 Dec 16 | 20 Jan 17 | 
AEMO seeks IEC recommendation for B2B changes | B2B: All | TBC Preceding AMEO Feb Board | 22 Jan 17 | Late Feb 17 | 
AEMO publishes final procedure determination | MC,EN,MRP | Obligation is no later than 1 Mar 17 | 01 Mar 17 | 28 Feb 17 | 
AEMO publishes final procedure determination | B2B: All | Obligation is no later than 1 Jun 17 | 01 Mar 17 | 06 Mar 17 | 
AEMO publishes Fee Methodology (participant fee structure) | SMP | If required | 01 Mar 17 |  | 
Commencement of registration / accreditation activities | Readiness | To be determined in readiness strategy | Mar 17 |  | 
Industry testing period detailed planning commences | Readiness |  | Mar 17 |  | 
Industry detailed cut-over and transition planning commences | Readiness |  | Apr 17 |  | 
Industry testing and trial period commences | Readiness | To be determined in test plan | Aug 17 |  | 
DNSPs publish T&C’s on which it will act as the initial MC | MC |  | 1 Sep 17 |  | 
Industry Accreditation and Registration activities completed | Readiness |  | Oct 17 |  | 
Industry cut-over and transition plan completed | Readiness |  | Oct 17 |  | 
DNSPs publish distributor deemed standard connection contracts | MC |  | 1 Dec 17 |  | 
Retailers publish Elect & Gas standard retail contracts | MC |  | 1 Dec 17 |  | 
PoC Effective date | All |  | 1 Dec 17 |  | 


## Slide 9: PoC - Program Overview Version history
This table summarises the changes between the Program Overview as information changes or becomes available.
Version | Date | Amendments
3.2 | 11 Feb 16 | Updated SMP DD and FD dates in accordance with AEMC update 11 Feb 16
3.3 | 19 Feb 16 | Updated DRM DD date from 18 Feb to 9 Jun – Removed the DRM FD until advice is available from AEMC Included milestone for ring-fencing & exemption guidelines and DNSPs to publish standard T&C’s
3.4 | 04 Mar 16 | Removed MTR following guidance published by AEMC on 25 Feb 2016 Separated initial B2B consultation – scheduled to begin on 8 Apr Amended dates according to AEMC update (2 March 2016) – SMP dates moved back/DRM FD date released
3.5 | 22 Apr 16 | Removed DRM/ASU until further guidance – expanded timeline to focus on the Dec 2017 delivery and heightened support into Q1 2018 Combined MC/EM/MRP into single project Included SMP draft rule dates as published by AEMC – included proposed timeline for conducting SMP procedure consultation
3.6 | 10 May 16 | Expanded key milestone dates.
3.7 | 1 Jun 16 | Included proposed dates for testing periods (Aug 17 – Nov 17). Expanded on proposed fee methodology timetable to accommodate consultation process.
4.0 | 10 Jun 16 | Arranged Program Overview into key workstreams Removed IEC milestones in lieu of SMP Draft Determination
4.1 | 23 Jun 16 | Increased AEMO’s “design phase” to carry on until the end of consultation (1 Mar 17) Altered WP 1 Procedure Change Process dates to accommodate additional four business days of consultation.
4.2 | 19 Aug 16 | Updated tracking; removed dates associated with B2B Procedures as a result of B2B Framework Rule being published
4.3 | 02 Sep 16 | Updated B2B Procedure consultation with AEMO’s proposed dates (pending IEC approval)
4.4 | 10 Oct 16 | Updated terminology – added ‘6 month outlook’ for Procedure development / consultation processes Updated key dates in relation to AEMO WP2 Procedures and B2B Procedure development / consultation Included key dates identified in Readiness strategy
4.5 | 17 Nov 16 | Amended dates for Fee Methodology consultation Updated B2B Procedure Consultation dates
4.6 | 16 Dec 16 | Updated Tracking

## Slide 10: PoC - Program Overview Version history
This table summarises the changes between the Program Overview as information changes or becomes available.
Version | Date | Amendments
3.2 | 11 Feb 16 | Updated SMP DD and FD dates in accordance with AEMC update 11 Feb 16
3.3 | 19 Feb 16 | Updated DRM DD date from 18 Feb to 9 Jun – Removed the DRM FD until advice is available from AEMC Included milestone for ring-fencing & exemption guidelines and DNSPs to publish standard T&C’s
3.4 | 04 Mar 16 | Removed MTR following guidance published by AEMC on 25 Feb 2016 Separated initial B2B consultation – scheduled to begin on 8 Apr Amended dates according to AEMC update (2 March 2016) – SMP dates moved back/DRM FD date released
3.5 | 22 Apr 16 | Removed DRM/ASU until further guidance – expanded timeline to focus on the Dec 2017 delivery and heightened support into Q1 2018 Combined MC/EM/MRP into single project Included SMP draft rule dates as published by AEMC – included proposed timeline for conducting SMP procedure consultation
3.6 | 10 May 16 | Expanded key milestone dates.
3.7 | 1 Jun 16 | Included proposed dates for testing periods (Aug 17 – Nov 17). Expanded on proposed fee methodology timetable to accommodate consultation process.
4.0 | 10 Jun 16 | Arranged Program Overview into key workstreams Removed IEC milestones in lieu of SMP Draft Determination
4.1 | 23 Jun 16 | Increased AEMO’s “design phase” to carry on until the end of consultation (1 Mar 17) Altered WP 1 Procedure Change Process dates to accommodate additional four business days of consultation.
4.2 | 19 Aug 16 | Updated tracking; removed dates associated with B2B Procedures as a result of B2B Framework Rule being published
4.3 | 02 Sep 16 | Updated B2B Procedure consultation with AEMO’s proposed dates (pending IEC approval)
4.4 | 10 Oct 16 | Updated terminology – added ‘6 month outlook’ for Procedure development / consultation processes Updated key dates in relation to AEMO WP2 Procedures and B2B Procedure development / consultation Included key dates identified in Readiness strategy
4.5 | 17 Nov 16 | Amended dates for Fee Methodology consultation Updated B2B Procedure Consultation dates

## Slide 11: Power of choice Procedures
Work Package 2
AEMO to publish the Draft Determination on 13 December.
POC-PWG meeting on 20 December (via teleconference) to discuss key issues from the Draft Determination.
2nd stage submissions close on 16 January.
AEMO will publish the Final Determination on 28 February.
AEMO will release all other Package 2 guidelines and checklists not subject to NER consultation following the publication of the Draft Determination.
All consultation materials are available on AEMO’s website – click here for link.

## Slide 12: Power of choice Procedures
B2B Procedures
We have received 30 submissions (including a handful of late submissions) and just over 2000 individual comments in the first stage consultation period.
The B2B Working Group and the AEMO drafting team have collated, synthesised and commenced redrafting procedures to be reviewed and recommended to the IEC to publish draft procedures.
Provide responses to all industry comments and reasoning for including or not including recommended. changes.
B2B-WGG meeting on the 14th and 15th December to consider draft B2B procedures.
IEC meeting on 21st December
Four key Procedures updates:
  Service Order Process
  Customer Site Details Notification
  Meter Data Process
  One Way Notification
Other documents:
  Technical Delivery Specification
  Business Guide
  Glossary update for B2B terminology
  ROLR Procedure Part B

## Slide 13: B2b Procedures update
B2B Working Group Schedule

## Slide 14: market readiness update
Readiness Working Group – 28 November meeting
RWG considered the following matters at its meeting:
  Reviewed the November monthly readiness reports;
  Provided feedback and considered possible minor refinements to the reporting template;
  Considered the potential for AEMO to split industry testing into two testing periods (one for MC/EN, one for e-Hub);
  Noted the RWG’s upcoming work program.
Industry readiness progress reports
RWG reviewed the first monthly readiness reports (industry “within schedule”, “medium risk”).
Reflecting RWG feedback, AEMO will distribute a mildly revised reporting template to RWG members.
The next monthly readiness report – a consolidated Dec/Jan report – is due to AEMO by 16 January.
Potential for splitting industry testing into two test periods
MC/EN industry testing in April, and e-Hub industry testing in August (as per Market Readiness Strategy).
AEMO aiming to have all system changes, including for schema, in pre-production environment by 3 April 2017.
RWG members asked to provide feedback to AEMO on whether their organisations would be ready to test in April.
Readiness Working Group – future meetings
13 Feb – Review 1st draft of Registration & Accreditation Plan, and discuss industry testing for MC/EN system changes.
8 Mar – Review 1st draft of Industry Testing Plan for e-Hub (market trial).
24 Mar – Q1 readiness update.
5 Apr – Review 1st draft of Transition & Cutover Plan.