## Market Readiness Report Page 1
2016-11-01
AEMO Power of Choice Implementation Program
|  | Monthly Readiness Report | 2016-11-01
Overall Status |  | Commentary |  |  | Project Risk Rating
AEMO and NEM Participants Readiness Criteria |  |  | AEMO |  | Retailers |  | Distributors |  | Metering |  | Other (3rd party, ENM)
# | Category | Criterion | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note
1. Assessment and preparation
1.1 | Assessment and preparation | Consequences of the POC reforms for your business considered, and appropriate implementation plans are in place | ü |  |  |  |  | #1 |  | #2
1.2 |  | Key readiness planning documents delivered
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | Updated retail electricity market procedures and associated documents published
2.2 |  | Internal policies updated for consistency with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Operationally critical commercial contracts in place
2.4 |  | Accreditation and registration activities completed
3. People
3.1 | People | Operational roles specified, assigned to staff, and training delivered
4. Business processes
4.1 | Business processes | Updated, validated and approved business processes in place
4.2 |  | Successfully validated critical business processes during industry testing
4.3 |  | Process work‑arounds in place for any issues identified during industry testing
5. Market systems
5.1 | Market systems | Successfully tested market systems capable of being moved into production
5.2 |  | Performance of, and communication between, market systems validated during industry testing
6. Transition planning
6.1 | Transition planning | Transition and cutover plan(s) in place
6.2 |  | Prerequisite transition and cutover processes completed (e.g. trial data conversions and cutover dress rehearsals)
Highlighted Risks and Issues
# | Category | Title | Mitigating Controls | [5 empty] | Status |  | Rating
1 | Risk
2
3
1 | Issue
2
3

## Market Readiness Report Page 2
AEMO Power of Choice Implementation Program
Monthly Readiness Report
2016-11-01
Variances
Note # | Explanation of Variance |  | Mitigating Actions
1
2
Notes
Key - Progress and Status |  |  |  |  | Key - Risk and Issue
Progress |  | Status
Harvey balls represent progress towards achieving the criterion |  | Colour indicates the readiness status |  |  | Rating
~100% |  | Criterion is within agreed schedule and deliverable requirements |  |  | High
~75% |  | Criterion is at risk of not meeting requirements and corrective action may be required |  |  | Medium
~50% |  | Criterion not meeting requirements. Immediate corrective action required |  |  | Low
~25%
~0% |  | Criterion has been achieved |  | ü

## Retailer Reports
| 2016-11-01 | Retailers Participants' Readiness Assessment Reports
| Participant | Overall project comment |  | Project status | Project risk rating
| Retailer A |  |  | Within schedule | Medium
# | Category | Criteria: What is your progress towards completing… | 1 | Progress (%)
|  |  | 1 | Retailer A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation | [18 empty] | 0%
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business |  | 100% | [14 empty] | 25%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date |  | 50% | [14 empty] | 50%
2. Legal, regulatory, contractual and policy | [18 empty] | 75%
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [16 empty] | 100%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [16 empty] | N/A
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities | [16 empty] | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [16 empty] | At risk
3. People | [18 empty] | Not within schedule
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [16 empty] | N/A
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [16 empty] | Completed
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes | [18 empty] | Low
4.1 | Business processes | A detailed assessment of business process impacts for your business | [16 empty] | Medium
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [16 empty] | High
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | 1 | Traffic Light Status
|  |  | 1 | Retailer A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business |  | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | 1 | Explanation of variance
|  |  | 1 | Retailer A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | 1 | Mitigating actions
|  |  | 1 | Retailer A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)

## Distributor Reports
| 2016-11-01 | Distributors Participants' Readiness Assessment Reports
| Participant | Overall project comment |  | Project status | Project risk rating
| Distributor A |  |  | Within schedule | Medium
# | Category | Criteria: What is your progress towards completing… | 1 | Progress (%)
|  |  | 1 | Distributor A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation | [18 empty] | 0%
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business |  | 100% | [14 empty] | 25%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date |  | 50% | [14 empty] | 50%
2. Legal, regulatory, contractual and policy | [18 empty] | 75%
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [16 empty] | 100%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [16 empty] | N/A
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities | [16 empty] | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [16 empty] | At risk
3. People | [18 empty] | Not within schedule
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [16 empty] | N/A
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [16 empty] | Completed
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes | [18 empty] | Low
4.1 | Business processes | A detailed assessment of business process impacts for your business | [16 empty] | Medium
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [16 empty] | High
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | 1 | Traffic Light Status
|  |  | 1 | Distributor A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business |  | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | 1 | Explanation of variance
|  |  | 1 | Distributor A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | 1 | Mitigating actions
|  |  | 1 | Distributor A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)

## Metering Reports
| 2016-11-01 | Metering Participants' Readiness Assessment Reports
| Participant | Overall project comment |  | Project status | Project risk rating
| Metering A |  |  | Within schedule | Medium
# | Category | Criteria: What is your progress towards completing… | 1 | Progress (%)
|  |  | 1 | Metering A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation | [18 empty] | 0%
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business |  | 100% | [14 empty] | 25%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date |  | 50% | [14 empty] | 50%
2. Legal, regulatory, contractual and policy | [18 empty] | 75%
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [16 empty] | 100%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [16 empty] | N/A
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities | [16 empty] | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [16 empty] | At risk
3. People | [18 empty] | Not within schedule
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [16 empty] | N/A
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [16 empty] | Completed
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes | [18 empty] | Low
4.1 | Business processes | A detailed assessment of business process impacts for your business | [16 empty] | Medium
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [16 empty] | High
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | 1 | Traffic Light Status
|  |  | 1 | Metering A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business |  | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | 1 | Explanation of variance
|  |  | 1 | Metering A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | 1 | Mitigating actions
|  |  | 1 | Metering A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)

## Other Reports
| 2016-11-01 | Metering Participants' Readiness Assessment Reports
| Participant | Overall project comment |  | Project status | Project risk rating
| ENM A |  |  | Within schedule | Medium
# | Category | Criteria: What is your progress towards completing… | 1 | Progress (%)
|  |  | 1 | ENM A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation | [18 empty] | 0%
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business |  | 100% | [14 empty] | 25%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date |  | 50% | [14 empty] | 50%
2. Legal, regulatory, contractual and policy | [18 empty] | 75%
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [16 empty] | 100%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [16 empty] | N/A
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities | [16 empty] | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [16 empty] | At risk
3. People | [18 empty] | Not within schedule
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [16 empty] | N/A
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [16 empty] | Completed
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes | [18 empty] | Low
4.1 | Business processes | A detailed assessment of business process impacts for your business | [16 empty] | Medium
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [16 empty] | High
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | 1 | Traffic Light Status
|  |  | 1 | ENM A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business |  | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | 1 | Explanation of variance
|  |  | 1 | ENM A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | 1 | Mitigating actions
|  |  | 1 | ENM A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)

## AEMO Report
AEMO Readiness Assessment Report
|  |  |  | Overall | Project status | Project risk rating
| Date | 2016-11-01 |  | Status | Within schedule | Medium
| Participant | AEMO |  | Comment
# | Category | Criteria: What is your progress towards completing… | Progress (%) | Traffic light status | Explanation of variance | Mitigating actions
1. Assessment and preparation | [6 empty] | 0%
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | 100% | Completed |  |  | 25%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | 50% | At risk |  |  | 50%
1.3 |  | Delivery of the Market Readiness Strategy and associated plans | 50% | Within schedule |  |  | 75%
2. Legal, regulatory, contractual and policy | [6 empty] | 100%
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | 50% | Not within schedule |  |  | N/A
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements |  |  |  |  | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities |  |  |  |  | At risk
2.5 |  | The fulfilment of accreditation and registration obligations |  |  |  |  | Not within schedule
2.6 |  | The publication of updated retail electricity market procedures and associated documentation |  |  |  |  | N/A
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business |  |  |  |  | Low
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business |  |  |  |  | Medium
3.3 |  | The development and delivery of training to staff in operational roles |  |  |  |  | High
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
4.4 |  | The delivery of POC training workshops to participants
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)

## HIDDEN (hidden)
ü
| 100 | 75 | 50 | 25 | 0
| 0 | 25 | 50 | 75 | 100
WITHIN SCHEDULE | [5 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE