## Slide 1: AEMO ‘Power of choice’ Readiness Working Group (POC-RWG)
8 September 2016

## Slide 2: Agenda
Welcome and introduction (13:30-13:40)
Administration (13:40-13:50)
Market Readiness Strategy (13:50-14:20)
Industry Readiness Reporting Plan (14:20-15:00)
Participant information sessions scoping (15:00-15:40)
Closing – Actions & next steps (15:40-16:00)

## Slide 3: 1. Welcome and introduction
POC-RWG members
38 members
Meeting papers will be emailed to POC-RWG distribution list in future, not AEMO’s global POC email list
Therefore, if you have not joined the POC-RWG, but are participating today, please notify POC@aemo.com.au of your company’s primary/alternate contacts after today’s meeting
AEMO POC webpage update
The POC webpages are being redeveloped over the next couple of months and will be populated with project management and detailed work stream information

## Slide 4: 2. Administration – Actions summary
Market Readiness Strategy
POC-RWG members to email feedback on Strategy (v0.2)
AEMO to update Strategy (v0.3)
Industry Readiness Reporting Plan
POC-RWG members to email feedback on IRRP (0.1)
AEMO to update IRRP (v0.2)
Participant information sessions scoping (training w/shops)
Members to email ideas/thoughts on future sessions
AEMO to prepare scoping document on info sessions (v0.1)
General
AEMO to invite AER to attend POC-RWG meetings
AEMO to inform its Consumer Forum of the POC-RWG’s offer to share and develop end-user key messages on the start of the new regulatory arrangements

## Slide 5: 3. Market Readiness Strategy
Strategy v0.2 – Previous meeting
Discussed with POC-RWG at 5 August meeting
Received email feedback from POC-RWG members
Strategy v0.3 – Today’s meeting
Attachments – Includes ‘clean’ and ‘tracked’ versions
Any further comments on Strategy v0.3?
Any comments on AEMO’s responses to feedback?
Strategy v1.0 (final) – Next steps
AEMO to finalise the Strategy after today’s discussion
AEMO to distribute the finalised Strategy to POC-RWG members to inform their own readiness programs/plans

## Slide 6: 4. Industry readiness reporting plan
IRRP and templates v0.1 – Previous meeting
Discussed with POC-RWG at 5 August meeting
Received email feedback from POC-RWG members
IRRP and templates v0.2 – Today’s meeting
Attachments – POC-RWG feedback incorporated
Any comments on IRRP v0.2?
POC-RWG to email comments to POC@aemo.com.au
IRRP and templates v1.0 (final) – Next meeting
Finalise at October meeting, for November reporting

## Slide 7: 4. Industry readiness reporting plan – FEEDBACK AND CHANGES
Participant versus Organisation
Propose that organisations complete one report per participant role, with exceptions:
  MP and MDP combined
  DNSP include initial MC
Propose that reporting be aggregated into these roles:
  Retailer
  DNSP (including initial MC)
  MP and MDP
  MC
  Other (ENM and 3rd party B2B participants)

## Slide 8: 4. Industry readiness reporting plan – FEEDBACK AND CHANGES
Jurisdictional reporting
Requesting AEMO and participants to report by jurisdiction:
  Overall traffic light status
  Overall risk rating
  Comments on specific jurisdictional readiness issues
Participants can choose to submit a separate report per jurisdiction

## Slide 9: 4. Industry readiness reporting plan – FEEDBACK AND CHANGES
Other
Reporting on the number of open risks and issues
Added specific criteria on readiness of B2B e-hub for industry testing
Notes field for general comments included
Contingency plans
No specific criteria asking participants if they have contingency measures in place
Implementation and Transition plans expected to have contingency planning incorporated
Purpose of reporting is to highlight areas where industry may need to develop industry-wide contingency measures

## Slide 10: 5. Participant information Sessions – Scoping
Strategy outlines six (6) ½ day info sessions (‘training’)
AEMO to scope sessions with POC-RWG input
Needs? Format? Materials? Other requirements?
POC-RWG to email comments to POC@aemo.com.au
Participant information session | POC industry meeting calendar
1. Overview of POC key obligations (targeting a general skills audience) | 13/14 Oct 2016
2. Detailed walk-through of POC key obligations (metering competition / meter replacement processes) | 14/15 Nov 2016
3. Detailed walk-through of POC key obligations: (embedded networks) | Apr 2017
4. Detailed walk-through of POC key obligations: (electricity B2B framework / e-hub) | Apr 2017
5. Overview of AEMO accreditation & registration process | Apr 2017
6. Overview of AEMO industry testing process | Jul 2017

## Slide 11: 5. Participant information Sessions – Scoping
POC-RWG suggestions
Be clear on purpose and intended audience
Walk-through on procedures and obligations
Overview of update-to-date procedure changes as at Sept 2016
Recap at later sessions (audience/procedure changes, MC/MRP)
Face-to-face delivery method
PowerPoint slides with notes (easier to incorporate by participants)
Split out sessions into functional grouping, if possible (package for retailers, package for LNSPs, etc)
FAQs, simplified guides, info packs for use in staff meetings (both at call centre and management level)
Clarify (i) training plan for updated AEMO systems/processes, and (ii) training environments that will be available for MSATS, e-hub, other systems, and when [AEMO: Industry Testing Plan]

## Slide 12: 5. Participant Information sessions – Example “run Sheet” (4hrs)
Overview of the information sessions program (10:00-10:05)
Overview of today’s information session (10:05-10:10)
Topic 1 – [insert here] (10:10-10.35)
Topic 2 – [insert here] (10:35-11:00)
Topic 3 – [insert here] (11:00-11:25)
Tea break (11:25-12:00)
Topic 4 – [insert here] (12:00-12:25)
Topic 5 – [insert here] (12:25-12:50)
Topic 6 – [insert here] (12:50-13:15)
Recap (13:15-13:30)
Questions (13:30-14:00)

## Slide 13: [example only] Participant information session #1 “overview of POC key obligations”

## Slide 14: 5. Participant Information session #1 – scoping
Topic 1 – Overview of rules, procedures and guidelines
Rules made – Obligations/requirements under 4 rule changes
Procedures & guidelines under development – AEMO, IEC, AER
Implementation timeline – AEMO, IEC, AER
Topic 2 – Expanding competition in metering
Key rules obligations (current/future obligations)
Key procedure obligations (current/future obligations)
Implementation timetable
Topic 3 – Meter replacement processes
Key rules obligations (current/future obligations)
Key procedure obligations (current/future obligations)
Implementation timetable

## Slide 15: 5. Participant Information session #1 – scoping
Topic 4 – Embedded networks
Key rules obligations (current/future obligations)
Key procedure obligations (current/future obligations)
Implementation timetable
Topic 5 – Updating the electricity B2B framework / e-hub
Key rules obligations (current/future obligations)
Key procedure obligations (current/future obligations)
Implementation timetable
Topic 6 – AEMO’s POC Implementation Program
Program governance overview – structure of project
Work streams overview – procedures, technical, readiness, B2B
Follow developments – working groups and forums

## Slide 16: 6. Closing
Actions
POC-RWG comments to POC@aemo.com.au by 22 Sept on:
  Industry Readiness Reporting Plan v0.2
  Participant information sessions scoping
AEMO to prepare summary note of today’s meeting
Next steps
AEMO to distribute meeting summary note to POC-RWG
AEMO to distribute finalised Strategy v1.0 to POC-RWG
AEMO to update IRRP, incorporating POC-RWG comments, for October POC-RWG meeting
AEMO to prepare information session #1 material, incorporating POC-RWG comments, for October info session
Next meeting
13/14 October (tbc)