## AEMO
AEMO Readiness Assessment Report
|  |  |  | Overall | Project status | Project risk rating
| Date | 2016-11-01 |  | Status | Within schedule | Medium
| Participant | AEMO
| Project commentary |  |  | Jurisdiction | Jurisdictional status | Jurisdictional risk rating
| Comment here on overall project status |  |  | ACT
NSW
QLD
SA
TAS
|  |  |  | VIC | Within schedule | Medium
# | Category | Criteria: What is your progress towards completing… | Progress (%) | Traffic light status | Explanation of variance/Notes | Mitigating actions
1. Assessment and preparation | [6 empty] | 0
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | 100% | Completed |  |  | 0.25
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | 50% | At risk |  |  | 0.5
1.3 |  | Delivery of the Market Readiness Strategy and associated plans | 50% | Within schedule |  |  | 0.75
2. Legal, regulatory, contractual and policy | [6 empty] | 100%
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | 50% | Not within schedule |  |  | N/A
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements |  |  |  |  | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities |  |  |  |  | At risk
2.5 |  | The fulfilment of accreditation and registration obligations |  |  |  |  | Not within schedule
2.6 |  | The publication of updated retail electricity market procedures and associated documentation |  |  |  |  | N/A
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business |  |  |  |  | Low
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business |  |  |  |  | Medium
3.3 |  | The development and delivery of training to staff in operational roles |  |  |  |  | High
4. Business processes | [6 empty] | N/A
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
4.4 |  | The delivery of POC training workshops to participants
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
5.6 |  | Delivery of the re-developed B2B e-hub for industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
AEMO's notes

## Participant
Participant Readiness Assessment Report
|  |  |  | Overall | Project status | Project risk rating
| Date | 2016-11-01 |  | Status | Within schedule | Medium
| Participant | Retailer A
| Project commentary |  |  | Jurisdiction | Jurisdictional status | Jurisdictional risk rating
| Comment here on overall project status |  |  | ACT
NSW
QLD
SA
TAS
|  |  |  | VIC | Within schedule | Medium
# | Category | Criteria: What is your progress towards completing… | Progress (%) | Traffic light status | Explanation of variance/Notes | Mitigating actions
1. Assessment and preparation | [6 empty] | 0
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | 75% | Within schedule |  |  | 0.25
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | 50% | At risk |  |  | 0.5
2. Legal, regulatory, contractual and policy | [6 empty] | 0.75
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | 50% | Not within schedule |  |  | 100%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) |  |  |  |  | N/A
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities |  |  |  |  | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations |  |  |  |  | At risk
3. People | [6 empty] | Not within schedule
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business |  |  |  |  | N/A
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business |  |  |  |  | Completed
3.3 |  | The development and delivery of training to staff in operational roles
4. Business processes | [6 empty] | Low
4.1 | Business processes | A detailed assessment of business process impacts for your business |  |  |  |  | Medium
4.2 |  | The development, documentation and approval of appropriate business processes for your business |  |  |  |  | High
4.3 |  | The validation of business processes during industry testing |  |  |  |  | N/A
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Participant notes

## Monthly dates
Report to be submitted to AEMO POC mailbox:
mailto:poc@aemo.com.au
# | Due date (indicative only - will be two weeks prior to the POC-PCF)
1 | 2016-11-14
2 | 2016-12-12
3 | 2017-01-09
4 | 2017-02-06
5 | 2017-03-06
6 | 2017-04-03
7 | 2017-05-01
8 | 2017-05-29
9 | 2017-06-26
10 | 2017-07-24
11 | 2017-08-21
12 | 2017-09-18
13 | 2017-10-16
14 | 2017-11-13
15 | 2017-12-11