## Current
Power of Choice - PoC - Issues/Questions Log - as at 18 November 2015
Item | Date Raised | Proponent | Topic | Description of issue | Actions required | AEMC Initiative | B2B - refer to IEC | Responsible | Next milestone date | Targeted Resolution Date | Date closed | Priority H/L | Current Status | Actions taken | Comments
MC1 | 2015-06-01 | AGL | Consultation | There is strong concern that the workshops will end up being information briefing sessions with the directive coming from AEMO, as opposed to working sessions which will involve industry participants collaborating to develop effective industry processes .AEMO stakeholder engagement strategy for consultation on procedures to be confirmed | AEMO submitted draft program plan to RMCF in July for MC development. This is still a work in progress and will be provided to Industry, RMCF and IEC once approved. In the plan, AEMO will be communicating the proposed meeting schedule for the MC development program in the October RMCF meeting pack. Workshops will be scheduled to involve industry participants in discussions on developing procedures. | MC | y | AEMO | RMCF meeting 30 October | Post final determination plan will be locked in |  |  | Open | Nov 15: Has been presented to IEC for their awarness. Oct 15: Draft working group meeting schedule presented to RMCF, IEC. Supporting documents were circulated for comment and feedback.structure was presented to RMCF. This included structure and references to support BAU and project based WGs.
MC2 | 2015-06-01 | EA, Ausnet, AGL, UE/Multinet | Overall work plan - AEMC customer switching outcomes - Data cleansing request from COAG | Participants have requested visibility of the review of Electricity Customer Switching project in the overall POC workplan. (Include the data cleansing activity into the program plan once approach determined.) | Intent is to include data cleansing once formalised. COAG has instructed AEMO to do this work in consultation with industry. AEMO are still to determine the scope and approach regarding this work. It is expected that the use of working groups - as required - will follow the same conventions for the rest of the PoC program. Will be included in overall POC workplan once scope of work has been identified and confirmed with COAG. | POC |  | AEMO | TBD | TBD |  |  | Open | Oct 15: Include the data cleansing activity into the program once approach determined. NOTE: This work is still at advice paper stage
MC3 | 2015-06-01 | UE/Multinet | Jurisdictional matters | Metrology procedure (pack 1a) • The tables of difference need to be reviewed and the ongoing arrangements confirmed with the jurisdiction • The matters that expire on certain dates also need to be agreed as to whether they continue Clarity is required on approach to Metrology Procedure drafting regarding tables of difference, harmonisation, etc. | Review tables once final determination has been received. Identify required changes. | MC |  | AEMO, Jurisdictional Regulators, participants | 2015-11-26 | To be reviewed post final determination |  |  | Open | Jun 15: Added to issues log NOTE: existing jurisdictional differences in the metrology procedure only apply to type 5, 6, and 7 metering installations, and so will not / cannot apply to the new meters to be rolled out.
MC4 | 2015-06-01 | UE/Multinet | AEMC meter replacement process Rule change | Metering service level procedures and meter churn arrangements (pack 1a) UE notes that there is a meter replacement (MR) rule change being progressed commencing rule consultation today. UE note that AEMO said that this would impact the metering arrangements for the implementation of the MC rule change. We have not had an opportunity to review in detail, however this rule change could impact the meter churn and the meter service level documents, CATS and B2B procedures in packs 1a/1b and at the earliest will not be finalised until 19 Nov 15. Therefore there is no real surety of the process and the business requirements for the procedure changes until this other rule change is finalised. This makes it difficult to commence with reasonable certainty round 1 consultation on pack 1a which by the current draft plan would be expected to be consulted on by around Nov 15. (The EN rule change which is not due to be finalised until Dec 15 will have a lesser but similar impact on pack 1a/1b) | It is recognised as a dependency, but the current assumption is that it will have no impact. AEMO will reassess with the AEMC as the AEMC works through the early stages of discussion on the Meter Replacement proposal. | MC MR |  | AEMO | 2015-12-17 | To be reviewed post final dteremination on meter replacement rule change |  |  | Open | Oct 15: AEMO is aware of this, and is monitoring progress.
MC5 | 2015-06-01 | AGL | Procedure changes - MC role | Participants requested that references to RP are assessed for context when amending to MC. We would like to understand how AEMO has come to the conclusion that using the existing RP role for the new MC responsibilities is going to work. AEMO is suggesting only minimal changes (e.g. RP will = MC) are required. The obligations appear to be different when comparing the draft rules. Existing MSATS transactions will need to be reviewed and modified to reflect this. (E.g. currently the FRMP as RP can change the MDP/MPC moving forward the MC appears to be the one to do this with some exceptions (e.g. transmission) | The Role of the MC and how it integrates into the NEM metrology framework, is being assessed through the role mapping and process mapping exercises. | MC |  | AEMO | 2015-10-22 | To be reviewed post final determination |  |  | Open | Oct 15: This analysis is being carried through the role mapping and process flow modelling in the MC workshops
MC6 | 2015-06-01 | WG, Endeavor | Sample metering | PoC - Is there a procedure impact with how sample metering (for profiling) operates. Endeavour - AEMO need to consider how sample metering should be managed in light of the changes due to Metering Competition. | AEMO to ensure that the management of sample metering is considered in the Metrology procedure review | MC |  | AEMO | 2015-11-25 | To be reviewed post final determination |  |  | Open | Oct 15: The impact of the interval meter rollout on sample meters will be analysed to see if the current methodology is still relevant considering the reducing requirement for profiling and the constantly changing sample population.
MC7 | 2015-06-01 | UE/Multinet | Remote disconnection & reconnection | Determine requirements and method to progress discussions on operation of remote reconnection and remote disconnection service. Minimum services specification procedures (pack 1a) – input may be required from jurisdictions, regulators and safety regulators, for example; • Does there need to be a visible supply status indicator on the meter, • Does the safety regulator require an auto-disconnect if load is on when a remote re-en occurs as was required and may still be required in Vic, • Does the ESC wish to have the same remote de-en and re-en service timeframes, will there need to be a table of difference by jurisdiction and presumably the regulator and jurisdiction will wish to set such important customer protection measures • Retailers and distributors need to deliver in Vic to certain meter infrastructure performance and service levels for a few of the services, the Vic Dbs are keen to ensure that these commensurate performance levels and service levels prevail | This is being considered in the process mapping work being done as part of the pre-final determination work stream. | MC |  | AEMO | 2015-10-22 |  |  |  | Open | Oct 15: Jurisdictional safety regulators will need to be consulted to get a view on how to manage the safety aspects of remote en and de-en across the NEM jurisdictions.
MC8 | 2015-06-01 | AGL | Program management | There is concern that AEMO does not have adequate resources with the required skill set and knowledge to: o Identify the necessary requirements, o Undertake an impact assessment of the changes, o Produce a strawman and o Deliver efficient, cost effective processes on behalf of industry participants. | AEMO is running a set of 4 workshops prior to the release of the final determination to develop these items. AEMO to confirm PM for the PoC program. | MC | y | AEMO | 2015-10-22 | 2017-12-01 |  |  | Open | Nov 15: Has been presented to IEC for their awarness. Oct 15: Workshop #3 on 22 Oct, #4 on 25 November. Ben Healy has been appointed as PM for the POC program. AEMO in process of recruiting PM for B2B work.
MC9 | 2015-06-01 | Ausnet | NECF 2 | In the IEC Gantt chart the other rules change in the MC release was the NECF2 (COAG drafted NERR changes for smart meters). It is unclear whether this is to be included in the release (MC?) and if not is some of the regulatory framework for the smart metering services missing? | Consider the inclusion of changes required to the MDFF for NECF2. | MC |  | AEMO |  | 2015-10-22 |  |  | Open | Oct 15: MDFF will be discussed at workshop #4.
MC10 | 2015-06-01 | MCWG | Type 4A requirements | The issue was raised as to how the type 4A meters must be treated/governed. Are they the same as type 5? If so, the type 4 provisions need to Include requirements for contestable “MRIM” installations (e.g. NSRDs, forward estimation, etc etc). | Under discussion in the workshops | MC |  | AEMO |  | To be reviewed post final determination |  |  | Open | Oct 15: Type 4A requirements to be discussed at October 15 workshop. AEMC confirmed in the October workshop that the new rule has provisions for Type 4A as a separate type on its own. Type 4A is expected to be treated as an exception subject to a rigorous exemption requitrement.
MC11 | 2015-09-01 | Lumo | Customer classifications | There is still uncertainty around the use and definition of the large and small customers classification in the MC rule change. Is this still a jurisdictional issue? AEMC expected to clarify in Final Determination. Thresholds for large customers are different from NMI classifications in MSATS for NSW and VIC. | Covered in workshop #2 (Demi). Final Determination to clarify. | MC |  | AEMO / AEMC |  | To be reviewed post final determination |  |  | Open | Oct 15: AEMC have advised that there will be clarification in the final determination on the upper thresholds for Vic and NSW large customers to the extent that AEMC will explain that these thresholds are set by jurisdictions. There will therefore be no amendments to the draft rule on this point. AEMC have requested jurisdiction to review their "X" and "Y" values in the metrology procedure for continued relevance and appropriateness.
MC12 | 2015-09-01 | NSW DBs, UE/Jemena, Vector | ASP | Clarify how the ASP scheme works for MC - can the Metrology Procedure clarify this issue? - How will the new connection and abolishment work in NSW? - Who will educate the ASP on the new processes for new connection and abolishment? - Who will authorise/accredit/allow ASPs to install meters? - Where will the ASP collect the meter from for new connections? - Can the ASP install the meter and perform all the communication and configuration work? - Will the MP authorise and coordinate the work with the ASP and how will they perform this work? | NSW govt review of ASP scheme required through draft determination | MC |  | AEMO/AEMC/Dept Fair Trading |  | To be reviewed post final determination, and post NSW govt review. |  |  | Open | Oct 15:The MC draft determination requires the NSW jurisdiction to the review the operation of the ASP scheme, and this is being done now.
MC13 | 2015-09-01 | MCWG | Metering coordinator - gate keeper role | Does MC act as gate keeper for non-market services? Clarify in role maps. | AEMO to seek clarifications from AEMC. | MC | y | AEMO | 2015-10-22 | To be reviewed post final determination |  |  | Open | Nov 15: Has been presented to IEC for their awarness. 9 Oct 15: Clarifcations obtained from AEMC. | It is AEMC’s intention that MDPs will only be able to provide services to DNSPs or other parties with MC approval. The rules don’t seek to regulate contractual arrangements as such. But given the MC must approve parties that wish to access services and have a range of other obligations to oversee the provision of metering services they will need to be involved in some way.
MC14 | 2015-09-01 | MCWG, Vector | New connection Process | Can FRMP nominate service providers in MSATS? Currently the LNSP must specify the roles and relationships when creating the NMI in MSATS (i.e. FRMP, RP, and service providers). Some participants suggested making a change to MSATS to allow also the FRMP or MC to be able to nominate service providers in MSATS instead of only having the LNSP as the only one who can perform that. | AEMO to clarify how MSATS operates in this context. | MC |  | AEMO | 2015-10-22 | To be reviewed post final determination |  |  | Open | Oct 15: The option for changing MSATS create NMI CR to allow FRMP or MC to nominate service providers has been noted on the new connection process flow and is currently under review and discussion with participants
MC15 | 2015-09-01 | MCWG | Role mapping | Transaction models - need to define how Metering Coordinator role works. | Diagrams to be updated once decision has been made. | MC |  | AEMO | 2015-10-22 | To be reviewed post final determination |  |  | Open | Oct 15: Issue noted and added to issues log
MC16 | 2015-09-01 | MCWG, Vector | Process flows | Process flow diagrams to highlight regulated and/or required steps | To be included in updated process flows. Refer to IEC | MC | y | AEMO | 2015-10-22 | To be reviewed post final determination |  |  | Open | Nov 15: Has been presented to IEC for their awarness. Oct 15: The process flow has been updated to show regulated steps and suggested operational steps, this is to be discussed in workshop 3 pre final determination with participants
MC17 | 2015-09-01 | MCWG | Notifications in process flows | We need to clarify the reasons for notifications to determine who needs to be notified. The suggested number of notifications at workshop 2 in the process flows seemed to have gotten out of hand and they may not be possible/practical with the (hopeful) introduction of new and innovative products. - some participants suggested multi party transactions where all parties get notified of services when they are requested and when they are completed - some participants suggested notifications should only occur when the service provider accepts the service request - some participants suggested that the parties sending notifications should be the initiator of the request sending notifications when they request the service, and the service provider sending notifications when they complete the service - some parties suggested that notifications should happen through B2B multi party transactions - some participants suggested that MSATS notifications sent to all participants should be sufficient | Justify who needs to be notified and when, and reflect that on the process flows, refer to IEC the suggestion of the B2B multi party transactions | MC | y | AEMO, Participants, IEC | 2015-10-22 | To be reviewed post final determination and clarity obrained on SMP. |  |  | Open | Nov 15: Has been presented to IEC for their awarness. Oct 15: Process flows have been updated to show mandated notifications, unnecessary notifications have been removed. No further decisions can be made until the MC final determination and SMP clairty have been obtained.
MC18 | 2015-09-01 | MCWG, Vector | Life support | Clarify obligations on different parties in relation to life support. Is the obligation only on the retailer for remote services? | Included in workshop discussion, and to be referred to IEC for B2B requirements | MC | y | AEMO | 2015-10-22 | To be reviewed post final determination |  |  | Open | Nov 15: Has been presented to IEC for their awarness. Oct 15: Included in workshop discussion, and to be referred to IEC for B2B requirements. AEMC clarified that only "deemed" MCs will be obligated to use B2B (ie current type 5 and 6 RPs).
MC19 | 2015-09-01 | MCWG, Vector | SORs | Are additional reason codes required for rejections of service orders? | Review existing B2B service order rejection codes and feed suggestions to IEC | MC | y | AEMO | 2015-10-22 | To be reviewed post final determination |  |  | Open | Nov 15: Has been presented to IEC for their awarness. Oct 15: Included in workshop discussion, and to be referred to IEC for B2B requirements
MC20 | 2015-09-01 | MCWG, Vector | MSATS | Are new MSATS objection codes required? | AEMO to analyse with working group through use of process maps. | MC |  | AEMO/ MCWG | 2015-10-22 | To be reviewed post final determination |  |  | Open | Oct 15: Included in workshop discussion
MC21 | 2015-10-01 | Momentum | MC and TNSPs | Wrt transmission connection points: - Will market system development include validation process to ensure exclusivity of LNSP or FRMP to be the appointed MC only when the connection point is transmission? And; - Will market systems and procedures be developed to allow LNSP and FRMP access to MC role for these type of sites only and exclude them from all other sites? - Will AEMO update MSATS to appoint LNSP or FRMP as MCs on day 1 (same as process for small customers) or will current RPs for these be required to submit appropriate CRs affecting the change of role? | Market systems will not be updated to include this validation. As is done currently, these value can be checked afer the event through exception reporting using PMS (performance management system) | MC |  | AEMO |  |  | 2015-10-01 |  | Closed | Oct 15: This validation can be done as a post event exception report, as is done now, using PMS.
MC22 | 2015-10-01 | AEMO | Vic AMI transition | At the commencement of the MC rule, 2.8 million meters in Victoria will need to be migrated from type 5 or 6 to type 4 or 4A. There is no transitional period defined yet and no specific statement in the Draft Determination requiring this to occur. | This item needs to included as an action in the business readiness stream to explore options and determine if meter type can be updated with the BCT. Alternatively, if meter types cannot be updated on go live date, we need to engage with the AEMC to determine transitional arrangements. | MC |  | AEMO, participants, AEMC | TBC |  |  |  | Open | 9 Oct 15: Confirmations obtained from AEMC. Oct 15: This will be dealt with in the market readiness workstream. | The recommendations do not give VIC AMI providers the ability to maintain their remotely read interval fleet as type 5. They will be required to become type 4 on day one. Type 4 meters that have been deemed type 5 under the Victorian derogation will also be required to be type 4 from day one.
MC23 | 2015-10-01 | AEMO | Registration eligibility criteria | The registration eligibility requirements include the applicant must have insurance as considered appropriate by AEMO. What risk is the Metering Co-ordinator to be insured for? | AEMC to clarify | MC |  | AEMC | 2015-11-26 | To be reviewed post final determination |  |  | Open | Oct 15: AEMO to raise issue with AEMC for clarification.
MC24 | 2015-10-01 | AEMO | Registration eligibility criteria | AEMO needs to assess what information it needs from the MC registration applicant to demonstrate that an adequate security control management strategy is in place | AEMO to determine registration requirements based on final Rule. | MC |  | Retail | 2015-11-26 | To be reviewed post final determination |  |  | Open | Oct 15: Issue noted and added to issues log
MC25 | 2015-10-01 | AEMO | Registration eligibility criteria | AEMO needs to assess what information it needs from the MC registration applicant to determine the access parties identified for the service (as listed in Table S7.5.1.1) is correct | AEMO to determine registration requirements based on final Rule. | MC |  | Rego, Legal, Retail | 2015-11-26 | To be reviewed post final determination |  |  | Open | Oct 15: Issue noted and added to issues log
MC26 | 2015-10-01 | AEMO | Registration eligibility criteria | It is unclear what registration eligibility requirements may not be applicable to a TNSP. AEMO needs to assess which eligibility requirements TNSPs may need to be exempt from and whether be a separate exemption is needed or included in the MC registration application form | AEMO to assess which registration eligibility requirements may be inappropriate for TNSPS based on final Rule. | MC |  | Rego, Legal, Retail | 2015-11-26 | To be reviewed post final determination |  |  | Open | Oct 15: Issue noted and added to issues log
MC27 | 2015-10-01 | MCWG | New Connection Process | The draft NER rule mentions that the Metering Coordinator must apply to the LNSP for a NMI and must register the NMI with AEMO, previously this obligation was on the RP and there was no issues as the RP was the FRMP or the LNSP, however now the MC is not the FRMP or the LNSP, does the current process for new connection need to change so that the MC has to be the one obtaining the NMI from LNSP and registering it with AEMO instead of LNSP creating the NMI and registering it with AEMO based on the FRMP request? | AEMO to note the issue and review the process once the MC final determination is released as this issue has been raised with the AEMC | MC |  | AEMO, Participants | 2015-11-26 | To be reviewed post final determination |  |  | Open | Oct 15: New connection process flow is developed, issues and different options are noted and is currently under review and discussion with participants and awaiting MC final determination as this issue has been raised with the AEMC | This new connection process issue with regards to who should be obtaining the NMI from the LNSP and who should be registering it has been raised and discussed with the AEMC in the July 2015 workshop, Final determination might contain changes that might resolve the issues raised and clarify the new connection process
MC28 | 2015-10-01 | MCWG | Re-energisation/de-energisation process | The draft NERR mentions that the retailer and DNSP must notify each other of re-energisation/de-energisation, the reason of it and how it is performed (remotely or manually) however it doesn't clarify when should the notification occur as it mentions as soon as practicable, there is different views between participants on when should the notification occur | Notifications timing needs to be discussed with participants and agreed. To be referred to IEC | MC | y | AEMO, Participants | 2015-10-22 | To be reviewed post final determination |  |  | Open | Nov 15: Has been presented to IEC for their awarness. Oct 15: Notifications timings noted on the process flow for manual and remote re-en/de-en and is currently under discussion and review with participants | When considering when notifications should occur, it is recommended that an approach is agreed between participants to confirm what the source of truth would be
MC29 | 2015-10-01 | ERM Power | Type 4A identification | ERM have raised an issue relating to how we are going to capture the meter type 4A in MSATS? Also, suggesting that the meter capabilities need to be identifiable via a NMI Discovery in MSATS. | AEMO / WG to determine approach once the design phase has commenced post the Final Rule being published. | MC |  | AEMO, participants | 2015-11-26 | To be reviewed post final determination |  |  | Open | Oct 15: AEMO / WG will determine approach once the design phase has commenced post the Final Rule being published.
MC30 | 2015-10-01 | AEMO | MC participant ID | Where LNSP is the RP for Types 5, 6, and 7s, will a new participant ID be required for their role as MC. | AEMO to determine if new participant IDs are needed. This is an action item for market readiness workstream. | MC |  | AEMO, Participants | TBD |  |  |  | Open | Oct 15: To be considered in the market readiness workstream. AEMC clarified that new Particip[ant IDs are not required.
MC31 | 2015-10-01 | AEMO | Registration requirement | It is unclear whether a person seeking registration as a Metering Coordinator needs to have been appointed by at least one FRMP or large customer. Clause 2.4A.1 suggests that an appointment needs to have occurred to be a Metering Coordinator, however this is not included as an eligibility requirement under clause 2.4A.2 | Clarify with the AEMC | MC |  | AEMO, AEMC | TBD |  |  |  | Open | Oct 15: This will be dealt with in the market readiness workstream. AEMC clarified that MCs can regsiter before getting clients.
MC32 | 2015-10-01 | Ausnet, MCWG | Type 4 metrology | Current type 4 meters are low volume high value devices, whereas the new smart type 4 will be the mass market meters, is low value high volume. Will existing type 4 metrology and arrangements (e.g. testing, inspection, substitution methodology etc) be suitable for the new smart type 4s? | These issues will need to be considered in the analysis for drafting the amendments for the Metrology Procedure parts A and B | MC |  | AEMO, participants | 2015-11-25 | To be reviewed post final determination |  |  | Open | Oct 15: Initial analysis to be included in draft Metrology Procedure for MC workshop #4 (25 Nov)
MC33 | 2015-09-01 | Vector, MC WG | MSATS | What are the Metering Coordinator’s operational responsibilities. Are they expected to be a registered MSATS participant with IT systems sending, receiving and coordinating requests? | AEMO to clarify the operational responsibilities of the MC in the role mapping and the process flows | MC |  | AEMO | 2015-10-22 | To be reviewed post final determination |  |  | Open | Oct 15: The role maps and process flows presented in the workshops pre final determination clarified that the MC will be a registered MSATS participant receiving MSATS notifications, objecting to MSATS CRs, and raising MSATS CRs, and it clarified that with regards to coordinating service requests this will be optional depending on the MC's contractual arrangements with FRMP and other participants | As per the NER all Registered participants must comply with the MSATS procedures, this means that the MC as a registered participant must comply with the MSATS procedures, and as the MC performs the same roles as the RP then they will have access to MSATS
MC34 | 2015-09-01 | Vector, Ausnet, united energy | New connection Process | Participants suggested that once the DNSP issues the unique NMI for new connection then the FRMP or MC should obtain the NMI immediately to use it in coordinating the connection work between the DNSP, REC, and the service providers, a suggestion was to use Allocate NMI B2B service order as the service order response is sent immediately after NMI is created and contains the NMI details, but with the new connection B2B service order the response is not sent until the new connection work is completed | AEMO to note suggested options on the new connection process, and to feed suggested B2B changes to IEC | MC | y | AEMO. Participants | 2015-10-22 | To be reviewed post final determination |  |  | Open | Nov 15: Has been presented to IEC for their awarness. Oct 15: Using Allocate NMI B2B service order as an an option in the new connection process in noted on the process flow diagram | It might be more logical to use the Allocate NMI B2B service order instead of the New connection B2B service order for all new connection requests, as the DNSP will not be performing all the connection work including the Meter installation as previously they used to do , so it is more logical for retailer/MC to use allocate NMI to obtain the NMI from the DNSP then coordinate the connection work with the other service providers once the NMI is obtained.
MC35 | 2015-09-01 | MCWG | New Connection Process | In the new connection process can it all go through the Metering Coordinator, for example FRMP requests new connection from the MC and then the MC sends the B2B service order to the DNSP, and coordinates the new connection work between the DNSP, the REC, and the service providers? | AEMO to note options for the new connection process. Suggestions for B2B changes to be referred to the IEC | MC | y | AEMO, Participants | 2015-10-22 | To be reviewed post final determination |  |  | Open | Nov 15: Has been presented to IEC for their awarness. Oct 15: Options for MC or FRMP to coordinate the new connection work is noted on the new connection process flow diagram | as the draft rule is about introducing competition in the market, whether the metering coordinator or the FRMP will be performing the coordination work in the new connection process this is left to commercial agreements between those parties to determine who will be performing the work as long as they both FRMP and MC meet their obligations under the rules
MC36 | 2015-10-01 | United energy | New connection process | A suggestion is to make changes to the New connection B2B service order as the following: - MP and MDP fields to change from Mandatory to not required even if the DNSP was not the RP/MC - include subtype for new connections activities to be provided by the DNSP or by the service provider | Options for changes to B2B to be noted and referred to the IEC | MC | y | AEMO | 2015-11-26 | To be reviewed post final determination |  |  | Open | Nov 15: Has been presented to IEC for their awarness. Oct 15: options for changes to new connection service order is noted
MC37 | 2015-09-01 | Powershop | Manual Re-en/De-en | An option for the manual re-energisation/de-energisation is for the retailer to go through the MC to request those services instead of going to the DNSP directly, the MC will manage and coordinate the manual re-en/de-en work between all parties and send the outcome at the end of the process to the retailer, this might require B2B changes | Options for the manual re-en/de-en process to be managed and coordinated by the MC are to be noted on the manual re-en/de-en process flow diagram. Suggestions for B2B changes to be referred to the IEC | MC | y | AEMO | 2015-11-26 | To be reviewed post final determination |  |  | Open | Nov 15: Has been presented to IEC for their awarness. Oct 15:Options for MC or FRMP to coordinate the manual re-en/de-en work is noted on the manual re-en/de-en process flow diagram | as the draft rule is about introducing competition in the market, whether the FRMP requests the manual re-en/de-en from the DNSP directly or goes through the MC to request it, this is left to commercial agreements between the FRMP and the DNSP as long as they both the FRMP and MC meet their obligations under the rules
MC38 | 2015-09-01 | MCWG | Re-energisation/de-energisation process | Clarification on meter read is required when the re-en/de-en occurs manually or remotely. If the meter is manually read then the DNSP should read it as they currently do, if the meter is remote interval meter then it will have half hourly reads which can be obtained anytime, does the MDP need to be involved in meter reads when re-en/de-en occurs manually or remotely? | Question noted and to be discussed in the workshop 3 pre MC final determination | MC |  | AEMO, participants | 2015-11-26 | To be reviewed post final determination |  |  | Open | Oct 15: Question noted for discussion in workshop 3 pre MC final determination
MC39 | 2015-09-01 | MCWG | MSATS | As the re-energisation/de-energisation can now be performed by DNSP or by service providers MP/MDP, it is important to be able to identify who performed the re-en/d-en and how it was performed, a suggestion is to add new sub field to the NMI status in MSATS to show who performed the NMI de-energisation and how they performed it | Suggestion for changing MSATS is noted and to be reviewed and discussed further with participants | MC |  | AEMO, participants | 2015-11-26 | To be reviewed post final determination |  |  | Open | Oct 15: suggestion to add NMI status subfield in MSATS is noted on the re-en/de-en process flow diagrams
MC40 | 2015-09-01 | MCWG | Remote disconnection & reconnection | Who will be performing the remote disconnection, is it the MP, the MDP or both or them | This item is to be discussed and agreed with participants | MC |  | AEMO, participants | 2015-11-26 | To be reviewed post final determination |  |  | Open | Oct 15 :Questions is captured and noted on the remote re-en/de-en process flow diagrams
MC41 | 2015-09-01 | MCWG | Remote disconnection & reconnection | Remote disconnection/reconnection requests can go directly from retailer or DNSP to the service provider (MP/MDP) , or another way would be for retailer or DNSP to request the service through the metering coordinator, which option will be selected? | the options for the remote disconnection/reconnection to be noted | MC |  | AEMO | 2015-11-26 | To be reviewed post final determination |  |  | Open | Oct 15: remote reconnection/disconnection process diagrams are developed for both models, where the requests go directly to the service provider (MP/MDP) and where the requests go through MC. Both options are valid under the new world of competition, it is decided and agreed through commercial agreements between the parties
MC42 | 2015-09-01 | United energy, MC WG | Remote disconnection & reconnection | Currently there are no B2B transactions for the remote disconnection/reconnection services, suggestions to change or create new B2B transactions as the following: - Change the existing B2B service order for re-en/de-en to include subtype for remote disconnection/reconnection, and change it to also allow MC and MP/MDP to send and receive B2B transactions or - Create new B2B transactions for remote disconnection/reconnection and allow MC and MP/MDP to send and receive B2B transactions | B2B changes suggestions are noted and to be referred to the IEC | MC | y | AEMO | 2015-11-26 | To be reviewed post final determination |  |  | Open | Nov 15: Has been presented to IEC for their awarness. Oct 15: B2B changes suggestions are noted
MC43 | 2015-09-01 | MCWG | MSATS | As the service providers (MP/MDP) can now perform remote disconnection/reconnection, they should be able to update the NMI status in MSATS, currently only the LNSP can initiate CR505X to update the NMI status, this might need to change to allow MP/MDP to also initiate CR505X to update the NMI status when they perform the re-energisation/de-energisation | suggestion to change MSATS is noted and to be discussed and agreed with participants | MC |  | AEMO, participants | 2015-11-26 | To be reviewed post final determination |  |  | Open | Oct 15: Suggestion to change MSATS is noted on the remote disconnection/reconnection process flow diagrams
MC44 | 2015-09-01 | MCWG | Jurisdictional matters | Need to check that other jurisdictional instruments don’t place obligation on the DNSP with regards to disconnection of customer with life support if the DNSP was not that one planning or undertaking the disconnection | Review other jurisdictional instruments to confirm DNSP has no obligations related to Life support if they were not the ones initiating or planning the disconnection | MC |  | AEMO, jurisdictional regulators | 2015-11-26 | To be reviewed post final determination |  |  | Open | Oct 15: Issue noted and added to issues log
MC45 | 2015-09-01 | CitiPower Powercor | Abolishment process | Participants raised that if the DNSP is abolishing a meter that is not theirs then possibly they might need to bill this work | suggestion noted and to be discussed with participants in workshop 3 prefinal determination | MC |  | AEMO, participants | 2015-11-26 | To be reviewed post final determination |  |  | Open | Oct 15: suggestion is noted on the developed abolishment process flow and will be discussed in workshop 3
MC46 | 2015-09-01 | MCWG | Abolishment process | How should the MC be involved in the abolishment process? should they just be notified of the abolishment as their contractual agreements ends when the NMI becomes extinct , when and how should the MC be notified | Question noted and to be discussed in the workshop 3 pre MC final determination | MC |  | AEMO, participants | 2015-11-26 | To be reviewed post final determination |  |  | Open | Oct 15: question is noted on the developed abolishment process flow and will be discussed in workshop 3
MC47 | 2015-09-01 | MCWG | Role Mapping | Given the appointment requirements in the draft rule, who should submit the CRs to change the respective roles in MSATS? Objection periods need to be considered when assessing process efficiency. | Assessment needs to be performed when MSATS procedures are updated. | MC |  | AEMO, participants | 2015-11-26 | To be reviewed post final determination |  |  | Open | Oct 15: Issue noted and added to issues log
MC48 | 2015-10-01 | MCWG | MC transition | Will MC for current type 1-4 meters need to be re-appointed by go-live date? | AEMO to confirm with AEMC | MC |  | AEMO, AEMC | 2015-10-22 |  | 2015-10-01 |  | Closed | Yes, Metering Coordinators will need to be appointed for existing type 1-4 meters by the go-live date.
MC49 | 2015-10-01 | MCWG | Terminology | Is there a difference between “appoint” and “contract” in the Rule? | AEMO to confirm with AEMC | MC |  | AEMO, AEMC | 2015-10-22 | 2015-11-26 |  |  | Open | AEMC advised that they are considering whether the rules need to be clearer around the responsibility to “appoint"
MC50 | 2015-10-01 | ActewAGL, Ausgrid | New connection Process | Consider an option in the new connection process where when a customer contacts the DNSP for new connection, the DNSP would create the NMI in MSATS without assigning any roles apart from the LNSP, this will require changing MSATS to allow creating NMIs without any roles, then the MC or the retailer can do NMI discovery to find the NMI in MSATS. This can also result in changes in B2B new connection service order where the MP, MDP roles don't have to be mandatory when the service provider is not the RP | AEMO to develop a process flow which explores the suggested new connection process model, and this to be further discussed with participants | MC |  | AEMO, participants | TBD | To be reviewed post final determination |  |  | Open | Nov 15: Added to issues log
MC51 | 2015-10-01 | AGL | New connection Process | New draft NERR rule mentions that the retailer should provide the DNSP with the contact details of the metering coordinator. How and when should this happen? Would the list that AEMO publishes on the website with registered participants contact details be sufficient and would cover this rule? | Question noted and to be discussed in the upcoming MC workshops | MC |  | AEMO, participants | TBD | To be reviewed post final determination |  |  | Open | Nov 15: Added to issues log
MC52 | 2015-10-01 | Endeavourenergy/Powershop | New connection Process | There are different participant views on whether or not the MC can request manual re-energisation/de-energisation from the DNSP? can the retailer have a commercial agreement with MC where the retailer requests the remote or manual reconnection/disconnection from the MC, and the MC requests it from the service provider whether it is the DNSP, the MP, or the MDP? | Question noted and to be discussed in the upcoming MC workshops | MC |  | AEMO, participants | TBD | To be reviewed post final determination |  |  | Open | Nov 15: Added to issues log
MC53 | 2015-10-01 | MCWG | remote and manual Re-en/De-en | How should the meter read be performed in the manual or remote re-en/de-n process? Who will be doing it? And how it will be coordinated... for the manual re-en/de-en process we need to consider the different meter types | Question noted and to be discussed in the upcoming MC workshops | MC |  | AEMO, participants | TBD | To be reviewed post final determination |  |  | Open | Nov 15: Added to issues log
MC54 | 2015-10-01 | ActewAGL | Metering installation components | Rule 7.8.2 (c) states that "The Metering Coordinator for a metering installation must apply to the Local Network Service Provider for a NMI." Will the MC have the ability to do NMI Discovery to improve processes and competition? | This will be reviewed as part of the MSATS review in light on new access to data arrangements. This will be added to the issues register. | MC |  | AEMO, participants |  | To be reviewed post final determination |  |  | Open | Nov 15: Added to issues log
MC55 | 2015-10-01 | ActewAGL | Metering installation components | Rule 7.8.2 (d) states that "The Local Network Service Provider must issue a unique NMI for each metering installation to the Metering Coordinator that is responsible for that metering installation." ActewAGL ask that as the FRMP is not involved yet, what will this allow the MC to do market-wise? | This is what the RP currently does. Again, being worked through, but MC is responsible for the MI and would pass NMI on to FRMP. | MC |  | AEMO, participants |  | To be reviewed post final determination |  |  | Open | Nov 15: Added to issues log
MC56 | 2015-10-01 | ActewAGL | Metering installation components | Rule 7.8.2 € requires that the MC registers NMIs with AEMO in accordance with relevant procedures. ActewAGL question how can this happen if only the DNSP can register a NMI? They believe the DNSP should publish a NMI without roles except 3 (ROLR, LNSP, LR) and allow NMI discovery by MC & FRMP | Same as current process with RP – will be reviewed for comtextual correctness. | MC |  | AEMO, participants |  | To be reviewed post final determination |  |  | Open | Nov 15: Added to issues log
MC57 | 2015-10-01 | Powershop | Type 4A | Is the identifier "4A" needed as such, or can a number be used (ie rather than alphanumeric)? Reduces confusion related to 4, and if participant systems only deal with numerical? | Review after Final Determination on metering competition | MC |  | AEMC |  | To be reviewed post final determination |  |  | Open | Nov 15: Note the 4A is an "external" idetifier - market systems use comms4, comms3 etc, that are alphanumeric.
MC58 | 2015-10-01 | AGL | Appointment of MC | AGL have raised this issue to AEMC. Certain generators that are not FRMPs should be treated like large customers and be allowed to appint own MC. AEMC will also review if other parties should also have this provision | Review after Final Determination on metering competition | MC |  | AEMC |  | To be reviewed post final determination |  |  | Open | Nov 15: Added to issues log
MC59 | 2015-10-01 | AGL | Industry data issues | Whilst working through the report, AGL have noted a number of instances where there are comments that AEMO procedures are inconsistent – i.e one requiring a field as mandatory – another procedure not requiring the field as mandatory. Given the substantial amount of work about to be undertaken by AEMO and industry on procedures, has this information been collated and fed into the retail change group to note these issues for inclusion in the redrafting ? | This issue is noted, and will be taken into account when drafting all new and changed procedures. Consistency checks are built into the QA process for procedure development. | PoC |  | AEMO, particiapnts |  | During procedure drafting |  |  | Open | Nov 15: Added to issues log
MC60 | 2015-10-01 | AGL | Customer classification | Under NECF all domestic acustomers are defined as ‘small’. However, there are domestic customers whose load is such that they use VT/CT metering. As such, a type 4 – min functional spec meter is not appropriate for these customers, nor will it meet the requirements of the National Measurement Act. Within Victoria, NECF does not apply. The Energy Retail Code only defines small customers and does not define what a large customer is. Therefore what will determine what a large customer is within Victoria, for the purposes of appointing an MC ? Under the NER, a groups of small customers under a corporate umbrella (eg a chain) can request to be treated as a large customer. As such, will these customers be able to appoint their own MC. If they can do so, what flag will be useds to identify this ? | 1) Clarification to be sought in the final determination as to whether small customer in this context is resttrcited to direct connected customers. 2) 40MWh/annum is the limit used in Victoria (as per draft determination and energy retail code). 3) The draft determination requires that an MC is appointed for eaco connection point, so the concept of a corporate umpbrella cannot apply. | MC |  | AEMO. Participants |  | To be reviewed post final determination |  |  | Open | Oct 15: Responses provided
MC61 | 2015-10-01 | Metering Dynamics | MPB Accreditation | AEMOs accreditation of Type 4A MPBs, is it going to be an extension of existing T4 or T5 MPB accreditation or a new accreditation? Will currently accredited MPBs need to register or will they be deemed to be accredited? | This will be considered as part of the accreditation development work that will be done following final determination. | MC |  | AEMO. Participants, AEMC |  |  |  |  | Open | Oct 15: AEMC have clarified that type 4A will be a distinct type, and will therefore needs its own accreditation (which may be based on an existing category).
M62 | 2015-11-01 | AEMO | Metering data services | In clause 7.10.1(a)(9), the reference to clause 7.15.5 seems incorrect - perhaps clause 7.10.5. | Confirm with the AEMC | MC |  | AEMC |  | To be reviewed post final determination |  |  | Open | Nov 15: Added to issues log
M63 | 2015-11-01 | AEMO | Periodic metering energy | In clause 7.10.4(b), the reference to clause 7.17.5 seems incorrect - perhaps refer to clause 7.5.2. | Confirm with the AEMC | MC |  | AEMC |  | To be reviewed post final determination |  |  | Open | Nov 15: Added to issues log
M64 | 2015-11-01 | AEMO | Metering data performance standards | In clause 7.10.6(c), the reference to clause 7.8.9(a) (refers to alterations or replacement metering installations) seems incorrect, perhaps clause 7.10.6(c). | Confirm with the AEMC | MC |  | AEMC |  | To be reviewed post final determination |  |  | Open | Nov 15: Added to issues log
MC65 | 2015-10-01 | AGL | Manual Re-en/De-en, Remote disconnection/reconnection | The draft NERR has obligations for notifications between Retailer and DNSP for re-energisation/de-energisation, the NERR doesn't operate in Victoria and there is no equivalent obligations, how will the notifications be handled in Victoria? | Question noted and to be discussed in the upcoming MC workshops | MC |  | AEMO, particiapnts | TBD | To be reviewed post final determination |  |  | Open | Nov 15: Added to issues log
MC66 | 2015-11-01 | Energex | New connection Process | To 'co-ordinate' with a Meter Provider for 'small' customer new connections would be a time consuming and costly exercise increasing costs for DBS exponentially given we had approximately 36,000 new connections in the last year.. We suggest that the MC engages the Meter Provider and the New Connection Service Order is not sent until metering has been installed. This will prevent wasted truck visits and additional costs to all consumers. | Suggestion noted and to be discussed in the upcoming MC workshops | MC |  | AEMO, particiapnts | TBD | To be reviewed post final determination |  |  | Open | Nov 15: Added to issues log
MC67 | 2015-11-01 | Energex | Manual re-en/de-en process | Where Data Streams are updated to I for Type 1-4 metered sites it is possible that energy consumed at the NMI may not be captured. Has happened in the past with serious implications where a NMI has been illegally reconnected, or incorrectly the NMI status has been updated to D. Should there be a timeframe for updating data streams subsequent to a De-en on a Type 1-4 meter where no consumption is registered prior to making the datastream inactive. Some DNSPs do not make data streams on De-en'd sites inactive. Sites are often disconnected and reconnected same day or within days of each other. | Suggestion noted and to be discussed in the upcoming MC workshops | MC |  | AEMO, particiapnts | TBD | To be reviewed post final determination |  |  | Open | Nov 15: Added to issues log
MC68 | 2015-11-01 | Energex | Meter replacement (due to faulty meter) | Whilst a one of meter fault (which is probably rare) requires some clarification about how Energex as a DNSP gets a customer back on supply in the shortest possible time given we will potentially no longer hold stock of meters, what would happen in a significant event. In the 2011 floods, Energex replaced 35,000 meters in a relatively short time. If the customer has to wait for the MP to come out and replace the meter, how will that effect our STPIS and not only will Energex have to make safe the site (remove the fuse) then instead of the efficiency of replacing the meter on the first visit and reconnecting, Energex will have to reattend to reinsert the fuse one the new meter is installed. What delay will we experience in being advised. This needs to be referred to the AEMC as it’s a significant issue. | This would be a commercial arrangement - this may also fall under some jurisdictional emergency process. | MC |  | Particiapnt, jurisdiction | TBD |  |  |  | Open | Nov 15: Added to issues log
MC69 | 2015-11-01 | Energex | Meter replacement (cost of DNSP site visit) | If the meter is faulty and the DNSP is not permitted to replace it, the fuse would be removed and Energex would again be required to attend site to reconnect. Who bears this costs - customer? | This would be a commercial arrangement. | MC |  | Participant |  |  |  |  | Open | Nov 15: Added to issues log
MC70 | 2015-11-01 | Energex | Meter replacement | Need to agree on a process to return old meter to old MP. What happens if meter is lost or not returned? | This would be a commercial arrangement. | MC |  | Participant |  |  |  |  | Open | Nov 15: Added to issues log
MC71 | 2015-11-01 | AGL | SLP MDP | SLP MDP should include service level requirements for remotely read type 5 meters. | No head of power to do this now - the Rules have no provisons for or concept of remotely read type 5. | MC | [6 empty] | Open | Nov 15: Added to issues log