## Sheet1
IESS Market Trial Test Schedule | time axis 2024-03-31 to 2024-05-24
PHASE 1 | Retail | 2024-04-25: PUBLIC HOLIDAY
Verify NMI class has updated NCC | bar: 2024-04-03 to 2024-04-24; 2024-04-26 to 2024-05-24
Verify participant category change to IRP | bar: 2024-04-03 to 2024-04-24; 2024-04-26 to 2024-05-24
PHASE 2 | Metering estimation file | 2024-03-31: PUBLIC HOLIDAY; 2024-04-01: PUBLIC HOLIDAY; 2024-04-02: ORACLE UPGRADE OUTAGE; 2024-04-08: Mock Go-Live
| Estimate settlement billing run |  |  |  | 2024-02-08 | 2024-02-09 | 2024-02-10 |  |  | 2024-02-11 | 2024-02-12 | 2024-02-13 | 2024-02-14 | 15-Feb 16-Feb |  |  | 2024-02-17 | 2024-02-18 | 2024-02-19 | 2024-02-20 | 2024-02-21 |  |  | 2024-02-22 | 2024-02-23 | 2024-02-24 |  | 25-Feb 26-Feb |  |  | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-02 |  |  | 2024-03-03 | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 |  |  | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 2024-03-12 |  |  | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16
Invoices and associated metering data
| Initial | 2024-04-04: 03/02 - 07/02; 2024-04-11: 08/02 - 12/02; 2024-04-15: 11/02 - 15/02
| Preliminary | 2024-04-05: 2024Wk5 28-Jan- 03 Feb; 2024-04-08: Feb04-10 Week 6; 2024-04-16: 2024Wk7; 2024-04-22: 2024Wk8
| Final | 2024-04-09: 2024Wk5 28-Jan- 03 Feb; 2024-04-18: 2024Wk7 including direction payment; 2024-04-24: 2024Wk8 including direction payment
| R1- First Revision | 2024-04-29: 2024Wk7 including direction payment; 2024-05-06: 2024Wk8
Settlement reports
Verify settlement reports | bar: 2024-04-04 to 2024-04-20
[18 empty] | * | * | * | * | * |  |  | * | * |  | * |  |  |  | * | * | * | * |  |  |  | * | * | * | * | * |  |  | * | * | * | * | * |  |  | * | * | * | *
PHASE 3 | BDU: Simulated Cutover1
| BDU available in pre-prod | 2024-04-19: SC1
| Submit MT PASA Offers | 2024-04-19: SC1
| Notification from AEMO to commence bidding (window) | 2024-04-19: SC1
| Participant BDU bid submissions opens (window) | 2024-04-19: SC1
| First 7day PD and ST PASA runs data available for cutover day | 2024-04-25: SC1
| Participant cutover day bid submission cut off | 2024-04-25: PUBLIC HOLIDAY; 2024-04-30: SC1
| First Pre-dispatch and PD PASA runs | 2024-04-30: SC1
| Simulated cutover day activities | 2024-05-01: SC1
Bidding (cutover1)
Verify submission of bids pre-cutover | bar: 2024-04-19 to 2024-04-24; 2024-04-26 to 2024-05-01
Verify submission of bids on cutover day | bar: 2024-05-01
Verify submission of bids post-cutover | bar: 2024-05-01 to 2024-05-08
BDU: Simulated Cutover2
| BDU available in pre-prod | 2024-05-03: SC2
| Submit MT PASA Offers | 2024-05-03: SC2
| Notification from AEMO to commence bidding (window) | 2024-05-03: SC2
| Participant BDU bid submissions opens (window) | 2024-05-03: SC2
| First 7day PD and ST PASA runs data available for cutover day | 2024-05-09: SC2
| Participant cutover day bid submission cut off | 2024-05-14: SC2
| First Pre-dispatch and PD PASA runs | 2024-05-14: SC2
| Simulated cutover day activities | 2024-05-15: SC2
Bidding (cutover2)
Verify submission of bids pre-cutover | bar: 2024-05-03 to 2024-05-15
Verify submission of bids on cutover day | bar: 2024-05-15
Verify submission of bids post-cutover | bar: 2024-05-15 to 2024-05-22
RELEASES | Code Drops (Defect Fixes or Releases) | bar: 2024-04-10 to 2024-04-11; 2024-04-16 to 2024-04-17; 2024-04-23 to 2024-04-24
Legend:
Version: Draft 0.1 published 19 Jan 2024 for discussion with ITWG
Legend:
Green represents old settlement calculations
Yellow represents settlement transition period
Purple represents new settlement calculations
Blue represents BDU testing for simulated cutover #1
Orange represents bdu testing for simulated cutover #2
Version: 1.1