## Cover
NEM Reform Implementation Roadmap |  | Version 1
Regulatory Implementation Roadmap |  | Version 7
NEM2025 Implementation Roadmap |  | Version 2
Published: | 2022-09-01
Overview:
The NEM Reform Implementation Roadmap (the Roadmap), provides AEMO and stakeholders with a holistic view of the reform program impacting National Electricity and Gas Markets. It does so by bringing together AEMO's former Regulatory Implementation Roadmap and NEM2025 Implementation Roadmap into one central Roadmap. The Roadmap will be revised periodically to reflect changes in scope or timelines as policy or designs are being finalised or as new rule determinations are made. Regulatory Implementation Roadmap In April-May 2020, the Australian Energy Market Commission (AEMC), Australian Energy Regulator (AER) and AEMO (the Market Bodies) undertook a process with stakeholders to prioritise the energy market regulatory program in response to the impacts of the COVID-19 pandemic, and in recognition of the cumulative regulatory implementation burden or the increasing number of significant processes. This work resulted in the production of the Regulatory Implementation Roadmap. The RI Roadmap, now in version 7, has been regularly updated in consultation with stakeholders since its inaugural release. NEM2025 Implementation Roadmap One of the main enablers for the Energy Security Board’s (ESB’s) recommended Post-2025 reforms is the development of IT systems and business processes. An initial assessment of the impacts associated with the delivery of the reforms was prepared by AEMO and formed part of the ESB’s final advice to the Energy National Cabinet Reform Committee. The ESB’s final advice called for further consideration of how to deliver these changes together with industry stakeholders as part of an integrated roadmap approach for National Electricity Market (NEM) regulatory and IT systems implementation. AEMO, in partnership with the Reform Delivery Committee (RDC, or the Committee), has since compiled the NEM2025 Implementation Roadmap. The purpose of the NEM2025 Implementation Roadmap is to establish a basis upon which to navigate the breadth of ESB reforms over the coming few years, de-risking delivery and informing implementation timing. The current version of the NEM2025 Implementation Roadmap incorporates stakeholder feedback on possible alternative pathways, as well as AEMO's own business case assessment.

## Roadmap
Australian Energy Market Operator
NEM Reform Implementation Roadmap
Version 1
| Link to Legend & Assumptions | [16 empty] | Expand group for 2020 and 2021 roadmap info, codes, updates and callouts
| Impacted Sector | Reform Status | Reform Initiative | Code | Updates | Callouts | 2020 |  |  |  | 2021 | [5 empty] | 2022 | [9 empty] | 2023 | [11 empty] | 2024 | [6 empty] | 2025 | [6 empty] | 2026 |  |  |  | 2027
[7 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 |  | Q3 |  | Q4 | Q1 |  | Q2 |  |  | Q3 |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 | Q2 |  |  | Q3 | Q4 |  | Q1 | Q2 |  | Q3 |  | Q4 |  | Q1 | Q2 | Q3 | Q4 | Q1 |  | Q2 | Q3 | Q4
NEM2025 IMPLEMENTATION ROADMAP
PHASE 1 - NEM2025 REFORM INITIATIVES
| W | Committed | Efficient management of system strength on the power system | [22 empty] | l |  |  | l
| W | Committed | Frequency control - Fast Frequency Response | FFR | [19 empty] | MASS |  | l | [9 empty] | l
| W | In progress | Increased MT PASA information | MTP | + | [30 empty] | l
| W | Committed | Integrating Energy Storage | IES | [24 empty] | l | [12 empty] | l
| R | In progress | Flexible trading arrangements model 2 | FTA2 | [37 empty] | u
PHASE 2 - FOUNDATIONAL & NEM2025 REFORM INITIATIVES
| A |  | Portal Consolidation | PC | +
| A |  | Consolidated Master Data Repository (CoMaStR) Phase 2 | CMSTR2 | +
| A |  | Identity and access management | IDAM
On-boarding and transition plan (including discontinuation of existing systems) to be determined through consultation and collaboration with Participants.
| A |  | ESB Industry Data Exchange | IDX
| A |  | SCADA Lite | SCDL | [25 empty] | u | [14 empty] | u
| W | Conceptual | Scheduled Lite | SL | [40 empty] | u | [5 empty] | u | Assumes a single rule change for both models. 1st release reflects Visibility Model. 2nd release reflects Dispatchability Model.
| W | In progress | Frequency Performance Payments (part of PFR Incentive Arrangements rule) | FPP | + | [39 empty] | p |  |  | u
| W | In progress | Operational Security Mechanism | OSM | [35 empty] | u | [10 empty] | u
| W | In progress | Operating Reserves Market | ORM | [35 empty] | u | [17 empty] | u
| W, R | Conceptual | Capacity Mechanism | CM | [23 empty] | Placeholder: delivery timeframe is not yet known.Will be subject to final design recommendations by ESB and will depend on both model and transition period.
| W | Conceptual | Congestion Management Mechanism | CMM | [23 empty] | Placeholder: delivery timeframe is not yet known.Will be subject to final design recommendations by ESB and will depend on both model and transition period.
PHASE 4 - STRATEGIC, NEM2025 REFORM & DATA STRATEGY INITIATIVES
| W | Conceptual | Turn-up services | TU | [42 empty] | Indicative: Subject to ARENA trials
| N | Conceptual | Dynamic operating envelopes | DOE | [34 empty] | Indicative: DNSP-led, capabilities developed at different times with a range of entry points across participants
| IW | Conceptual | DER Data Hub and Registry Services | D-Hub | [35 empty] | Indicative: Iterative implementation; start simple and continually develop over time as required
| IW | Conceptual | DER Operational Tools | DER OT | [29 empty] | Indicative: Iterative implementation; start simple and continually develop over time as required
| N | Conceptual | Distribution / local network services | DLNS | [34 empty] | Iterative implementation; start simple and continually develop over time as required
| A |  | Dispatch Target State | DSTM | [17 empty] | Indicative development range of 2 - 4 years subject to further analysis on scope
| A |  | Bids/Offers Target State | DSTM | [17 empty] | Indicative development range of 2 - 4 years subject to further analysis on scope
| A |  | Constraints Target State | DSTM | [17 empty] | Indicative development range of 2 - 4 years subject to further analysis on scope
| A |  | FRC Target State | FRC | [17 empty] | Indicative development range of 2 - 4 years subject to further analysis on scope
| IW | Conceptual | Data Services | [23 empty] | Includes various stages of stakeholder engagement and public consultation, issues paper, draft options paper, and options report and recommendations
| IW | Conceptual | Bill Transparency | [31 empty] | Includes various stages of stakeholder engagement and public consultation, issues paper, draft options paper, and options report and recommendations
| IW | Conceptual | Electric Vehicles | [29 empty] | Includes various stages of alignment with DER and DEIP work, current process report, draft options paper, and options report and recommendations
| N | Conceptual | Network Visibility | [31 empty] | Includes various stages of public consultation, AER Data Register development, gap analysis and case studies report, draft gap assessment report, recommendations report.
DEPENDENT PROJECTS NOT DELIVERED BY THE NEM2025 REFORM PROGRAM
| A |  | ST PASA - Replacement project and methodology update | STP | [44 empty] | u
| A |  | Business Rules Engine | BRE | [44 empty] | Indicative range for incremental delivery; use cases delivered with reforms as required
| A |  | Operational Decision-Making Tools | ODMT | [12 empty] | Delivered via AEMO's Operational Technology Roadmap (OTR). Additional use cases needed by NEM 2025 reforms will be integrated into the design of those reforms as needed
| A |  | Operational Data Store | ODS | [14 empty] | Delivered via AEMO's OTR. Additional use cases needed by NEM 2025 reforms will be integrated into the design of those reforms as needed
| A |  | Forecasting Platform Uplift | FPU | [19 empty] | Delivered via AEMO's OTR. Additional use cases needed by NEM 2025 reforms will be integrated into the design of those reforms as needed
REGULATORY IMPLEMENTATION ROADMAP
INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
| IW | Committed | Global Settlements | GS | [8 empty] | GS soft start |  |  | l |  | GS (extern) |  | l | AEMC final determination - go-live 1 May 2022
| R | Committed | Metering Coordinator Planned Interruptions | MCPI | [15 empty] | l | AEMO notice to reschedule to 1 May 2022, bundled with MSDR
| R | Committed | MSATS Standing Data Review | MSDR | [14 empty] | v1 | l |  |  |  | v2 | l | v1 MCPI and schema for MSDR go-live 1 May 2022 and v2 majority of MSDR go-live 7 Nov 2022
| R | Committed | Electricity B2B changes v3.7 | [21 empty] | l | v3.7 B2B changes go-live 7 Nov 2022
| R | Committed | Energy Consumer Data Right Rules | [20 empty] | T1 | l |  |  |  |  | T2 | l |  |  |  |  | T3 | l |  |  | T4 | l | CDR go-live has 4 tranches - 15 Nov 2022, 15 May 2023, 1 Nov 2023 and 1 May 2024
| R | Committed | Electricity B2B changes v3.8 | [27 empty] | l | v 3.8 B2B changes - go-live 30 May 2023
| R | Committed | Regulatory Arrangements for Stand Alone Power Systems Priority 1 | SAPS | + | [25 empty] | l | SA Energy Minister's final rule - go-live 30 May 2023
| R | In progress | Energy Consumer Data Right (NEL & NER) | [19 empty] | Indicative only, subject to SA Parliament and Ministerial processes
| R | Proposed - Review | Review of Regulatory Framework for Metering Services | [37 empty] | u | Indicative only, dependent on review outcomes
| W | Committed | ST PASA - Replacement project and methodology update |  | + | [43 empty] | l | AEMC final rule - go-live is 31 July 2025
INITIATIVES WITH LIMITED IT SYSTEM IMPLEMENTATION IMPACTS
| N | Proposed - Review | Transmission Planning and Investment Review | [29 empty] | Subject to review process - stages 2 and 3 expected to be completed in Q4 2022 and 2023
| N | In progress | Material change in network infrastructure project costs |  | + | [30 empty] | p | AEMC draft rule made - go-live 12 months after final rule (expected Q4 2022)
| W | Committed | Generator Registrations and Connections | [15 empty] | l
| N | Committed | Access, Pricing and Incentive Arrangements for Distributed Energy Resources | [11 empty] | l | [6 empty] | l
| IW | Committed | Enhancing Operational Resilience to Indistinct Events |  | + | [23 empty] | l | AEMC final rule - go-live 9 Mar 2023
GAS INITIATIVES
| G | Committed | DWGM simpler wholesale price | [22 empty] | l
Implemented as a single AEMO project (DWGM Enhancements) - AEMC final rule - go-live 1 Jan 2023
| G | Committed | DWGM improvement to AMDQ regime | [22 empty] | l
| G | Committed | Measures to Improve Transparency in the Gas Market | [22 empty] | l |  |  |  |  | NGL changes effective 23 June 2022, SA Energy Minister made final rule on 30 June 2022, staggered implementation with system go-live 15 Dec 2022
| G | Proposed - Review | Extending the Regulatory Framework to Hydrogen and Renewable Gases |  | + | [20 empty] | AEMC Review expected to be completed Sep 2022, Energy Ministers to consider in Nov 2022
| G | In progress | DWGM Distribution Connected Facilities |  | + | [30 empty] | p | AEMC draft rule - go-live 1 Oct 2023
INITIATIVES WITH LIMITED CERTAINTY
| R | In progress | Updating the Regulatory Frameworks for Embedded Networks | [34 empty] | u | Assumes rules development is re-initiated

## Implementation Schedule
Australian Energy Market Operator
NEM Reform Implementation Roadmap
Implementation Schedule & Schema Changes
| Reform Initiative | 2022 | [23 empty] | 2023
|  | Jan |  |  | Feb |  |  | Mar | Apr |  | May |  | Jun | Jul |  | Aug |  | Sep | Oct | Nov |  |  | Dec |  |  | Jan |  | Feb | Mar |  |  | Apr | May |  | Jun | Jul | Aug |  |  | Sep | Oct |  |  | Nov |  | Dec
| Global Settlements | [9 empty] | l | Global Settlements 1/5
| Electricity B2B changes (v3.7 and 3.8) | [18 empty] | l | B2B v3.7 Go-Live 7/11 | [12 empty] | l | B2B v3.8 Go-Live
[34 empty] | ¨ | Schema change
| MSATS Standing Data Review (MSDR and MCPI) | [9 empty] | l | MCPI in MSATS and schema released 1/5 | [7 empty] | l | New, amended and deprecated fields for MSDR 7/11
[11 empty] | ¨ | Schema change R42
| DWGM Enhancements | [12 empty] | l | Issue Auction Notice |  |  |  |  | l | Markets Systems Deployment |  |  |  |  | l | Go Live 1/1/23
(dormant)
| Energy Consumer Data Right | [15 empty] | Available |  |  |  | l | CDR Tranche 1 Go-Live 15/11/22 | [11 empty] | l | CDR Tranche 2 Go-Live | [8 empty] | l | CDR Tranche 3 Go-Live 1/11/23
[34 empty] | ¨ | If required
| Standalone Power Systems | [32 empty] | l | Go-live 30/5/23
[34 empty] | ¨ | If required
| Integrating Energy Storage Systems | [27 empty] | n | Final tech spec | l | Interim Release Go-live 31/3/23
| Fast Frequency Response | [22 empty] | n | Final tech spec (MASS) published | [14 empty] | TBC |  | l | Go-live 9/10/23
[38 empty] | l | TBC Registrations go-live
| Improving Gas Markets Transparency | [22 empty] | l | GBB reporting requirements go-live 15/12/22
Notes:
|  |  | Key | [6 empty] | - CDR deployment date will align with MSDR go-live date (7 Nov 2022)
|  |  |  | Pre-Production Test |  | l | Production Date |  |  | -IESS reflects interim release go-live of 31 March 2023 (introduces FCAS participation for SGAs and aggregate conformance for hybrid systems) noting the final release commences 3 June 2024. Final technical specification in March 2023 is for wholesale technical specification only (retail tech spec will be updated in 2024).
|  |  |  | Market Trial |  | ¨ | Schema Change |  |  | - IESS: Industry facing schema changes not required until June 2024
[6 empty] | n | Technical Specifications |  |  | - Electricity B2B changes v3.7 do not require schema change
[6 empty] | u | Checkpoint (Production Readiness)
[6 empty] | ¡ | Data Model release

## Legend and Assumptions
Australian Energy Market Operator
NEM Reform Implementation Roadmap
Legend and Implementation Assumptions
Legend
|  |  | Policy development and design |  |  |  |  | Proof of concept trial | [8 empty] | Rules development |  |  | AEMO scoping process
|  |  |  | Initiation, including high-level pre-execution design |  |  |  | Detailed pre-execution design | [8 empty] | AEMO process mapping and optimisation |  |  |  | AEMO Procedure/Guideline development
|  |  | Committed solution delivery |  |  |  |  | Indicative Solution delivery | [8 empty] | Industry testing and trials |  |  | Production roll Out
|  | l | Committed effective date |  | p | Proposed effective date |  |  |  | u | Estimated effective date
|  |  | Stage gate checkpoint |  |  |  | Grouped release
Updates / Callouts
|  | + | Initiative updated since last version
Initiatives will be delivered incrementally
An effective date for transition to target stage for the NEM that will be determined in collaboration with Participants
|  | NEM2025 Reform Pathways | [16 empty] | Impacted Sector
|  |  | Resource Adequacy Mechanisms and Ageing Thermal Generation | [5 empty] | Essential System Services, Scheduling and Ahead Mechanisms | [9 empty] | A |  | AEMO | IW | Industry Wide
|  |  | Integration of DER and Flexible Demand | [5 empty] | Transmission and Access | [9 empty] | N |  | Network | G | Gas | NEM2025 Program dependency
|  |  | Data Strategy | [15 empty] | W |  | Wholesale
[19 empty] | R |  | Retail
|  |  | AEMO Strategic / Foundational | [5 empty] | NEM2025 Program dependency
Standard implementation process and estimated timeframes
| # | Step | [7 empty] | Key on Roadmap
| 1 | Policy development and design
| 2 | Rules development (begins at open Rule Change, ends at Final Determination)
| 3 | Initiation (once Rules are defined), includes high-level pre-execution design
| 4 | Detailed pre-execution design
| 5 | Procedure/Guideline development
| 6 | Technology delivery
| 7 | Industry testing and trials
| 8 | Effective date | [7 empty] | l
Related processes - timeframes may vary across initiatives
Proof of concept trial
Internal scoping process (for pre-requisite initiatives; prior to initiation)
Internal process mapping and optimisation (for pre-requisite initiatives)
Production roll Out
| S | Non-complex reform/design with minor/minimal changes; or Non-complex and minor changes within existing frameworks and minimal system changes anticipated
| # | Step | [7 empty] | Estimated timeframe | [7 empty] | Assumptions
| 1 | Policy development and design | [7 empty] | 6
| 2 | Rules development (begins at open Rule Change, ends at Final Determination) | [7 empty] | 6
| 3 | Initiation (once Rules are defined), includes high-level pre-execution design | [7 empty] | 3
| 4 | Detailed pre-execution design | [7 empty] | N/A
| 5 | Procedure/Guideline development | [7 empty] | 6 | [7 empty] | 1 round of consultation; some overlap with Detailed pre-execution design and Solution delivery
| 6 | Technology delivery | [7 empty] | 9 | [7 empty] | After initiation phase completes
| 7 | Industry testing and trials | [7 empty] | 3 | [7 empty] | After Solution Delivery completes; includes time for required adjustments to the system arising to address issues arising during testing
| M | Some complexities; minor complexities in design but anticipated to require several changes; or Some complexity with implementation due to several system changes anticipated; non-complex design
| # | Step | [7 empty] | Estimated timeframe | [7 empty] | Assumptions
| 1 | Policy development and design | [7 empty] | 6 to 12
| 2 | Rules development (begins at open Rule Change, ends at Final Determination) | [7 empty] | 6 to 12 | 6 to 12 | 6 to 12 | 6 to 12 | 6 to 12 | 6 to 12 | 6 to 12
| 3 | Initiation (once Rules are defined), includes high-level pre-execution design | [7 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3
| 4 | Detailed pre-execution design | [7 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 5 | Procedure/Guideline development | [7 empty] | 9 | 9 | 9 | 9 | 9 | 9 | 9 |  | 2 rounds of consultation; some overlap with Detailed pre-execution design and Solution delivery
| 6 | Technology delivery | [7 empty] | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | After initiation phase completes
| 7 | Industry testing and trials | [7 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | After Solution Delivery completes; includes time for required adjustments to the system arising to address issues arising during testing
| L | Complex reform/design with significant system changes required. Complex reforms and changes; complex design, several anticipated system changes; or Non-complex design but significant procedural changes, system touch-points are anticipated
| # | Step | [7 empty] | Estimated timeframe | [7 empty] | Assumptions
| 1 | Policy development and design | [7 empty] | 12
| 2 | Rules development (begins at open Rule Change, ends at Final Determination) | [7 empty] | 12 to 24 | 12 to 24 | 12 to 24 | 12 to 24 | 12 to 24 | 12 to 24 | 12 to 24
| 3 | Initiation (once Rules are defined), includes high-level pre-execution design | [7 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4
| 4 | Detailed pre-execution design | [7 empty] | 6 to 12 | 6 to 12 | 6 to 12 | 6 to 12 | 6 to 12 | 6 to 12 | 6 to 12
| 5 | Procedure/Guideline development | [7 empty] | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 2 extended rounds of consultation; some overlap with Detailed pre-execution design and Solution delivery
| 6 | Technology delivery | [7 empty] | 18 | 18 | 18 | 18 | 18 | 18 | 18 |  | After initiation phase completes
| 7 | Industry testing and trials | [7 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  | After Solution Delivery completes; includes time for required adjustments to the system arising to address issues arising during testing

## Definitions
Australian Energy Market Operator
NEM Reform Implementation Roadmap
Definitions
DEFINITIONS AND INSTRUCTIONS (ROADMAP)
| Heading / Term | Definition and Instructions
| Impacted Industry Sector | Indicates the primary section of the industry that is impacted by the regulatory change. If two sections of industry are impacted, choose the primary section. If more that two sections are impacted, choose 'Industry-wide'. Wholesale = Generation, Wholesale Market and/or Contracting impacted by the rule change Networks = Transmission and Distribution networks impacted by the rule change Retail = Retailers, other contestable service providers and/or customers are primarily impacted by the rule change Industry-wide = More that two sections of the industry are impacted by the rule change AEMO = Represents a foundation or strategic initiative undertaken by AEMO to enable the NEM2025 reform initiatives
| Reform Status | Committed = Final determination made; and/or implementation in progress In progress = Rule development in process (i.e. open Rule with at least a Consultation on Draft Determination, or Consultation Paper with clear indication of design) Conceptual = Policy and market design in process (e..g Directions Paper on high-level design options, or Review of Framework, details of design remain uncertain) Note: A reference to rule change may also include a law change; or a reference to a review process where the outcome will be a law or rule change
| Effective Date Status | Committed = Final Rule has been published (i.e. certainty on requirements and Effective Date) Proposed = Effective date proposed in draft rule determination Estimated = AEMO estimated go-live date (where no proposed timeline currently exists or an effective date is uncertain or unknown)
| Implementation Status | Policy development and design = early stage of the reform process (i.e. prior to a rule change process commencing) Rules development = a rule change process is in progress (begins at open rule change through to final rule determination) Initiation = AEMO kicks-off an initiative once the rules are defined; includes high-level pre-execution design Detailed pre-execution design = Applied to some larger initiatives with complex changes and large procedure or guideline development – where it is not feasible to wait until they are final to commence IT Build because it would extend the rule effective date. Procedure/Guideline development = Procedural changes are in progress or required to implement the rule change; may run parallel to solution delivery Solution delivery = IT systems and processes implementation and engineering implementation Industry testing and trials = Runs within the solution delivery phase to test solution with market participants before the effective date.
DEFINITIONS AND INSTRUCTIONS (IMPLEMENTATION SCHEDULE)
| Heading / Term | Definition and Instructions
| Industry Test | Participants can get into the pre-prod environment and conduct unstructured tests as they see fit
| Invitation industry Test | Where a subset of participants agree (on a volunteer basis) to participate in an Industry Test. AEMO does not develop formal scenarios, but participants conduct bilateral testing on an agreed basis
| Market Trial | Where AEMO develops structured scenarios which are designed for widespread participation from our industry colleagues and structured to demonstrate/test particular scenarios. High effort required from all, generally reserved for new markets or big market changes (like 5MS)

## Previous View (hidden)
National Energy Market and Gas Markets
Regulatory Implementation Roadmap | [10 empty] | Key:
[12 empty] | Policy development/market design | [12 empty] | Rules development | [9 empty] | Procedure/guideline development
[12 empty] | Implementation - IT systems, processes | [12 empty] | Indicative IT implementation | [9 empty] | Engineering Implementation
[11 empty] | l | Committed Go-Live Date | [6 empty] | p | Proposed Go-Live | [6 empty] | n | Indicative Go-Live | [5 empty] | u | Estimated Go-Live |  |  |  | + | Updated for version 6
Impacted Industry Sector | Primary Objective | Reform Status | Reform Initiative |  | 2020 |  |  |  |  | 2021 | [9 empty] | 2022 | [11 empty] | 2023 | [7 empty] | 2024 |  |  |  |  | 2025 |  |  |  | 2026
[5 empty] | Q1 | Q2 |  | Q3 | Q4 | Q1 |  | Q2 |  |  | Q3 |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  | Q2 |  | Q3 | Q4 |  |  | Q1 |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide | Market | Committed | Five Minute Settlement (5MS) | [9 empty] | 5MS (IT platform) | l |  |  | l | AEMC final determination - go-live 1 Oct 2021
Retail | Consumer | Committed | Reducing Customer Switching Times | [13 empty] | l | Updated to align with 5MS go-live - 1 Oct 2021
Industry-wide | Consumer | Committed | Wholesale Demand Response Mechanism | [13 empty] | l | AEMC final determination - go live 24 Oct 2021
Retail | Consumer | Committed | Electricity B2B changes | [14 empty] | l | v3.5 and v3.6 - 10 Nov 2021
Gas |  | Committed | Gas B2B changes | [14 empty] | l | IN003/20 (business enhancements, schema uplift) - 29 Nov 2021
Industry-wide | Market | Committed | Global Settlements | [10 empty] | GS soft start |  |  | l |  |  |  | GS (extern) |  |  | l | AEMC final determination - go-live 1 May 2022
Retail | Consumer | Committed | Metering Coordinator Planned Interruptions (MCPI) | [20 empty] | l | AEMO notice to reschedule to 1 May 2022, bundled with MSDR
Retail | Operational | Committed | MSATS Standing Data Review (MSDR) | [19 empty] | v1 | l |  |  |  |  | v2 | l | v1 MCPI and schema for MSDR go-live 1 May 2022 and v2 majority of MSDR go-live 7 Nov 2022
Retail | Market | In progress | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | + | [25 empty] | n | AEMC recommended implementation 12 months after law and rule changes made
Retail | Consumer | In progress | Energy Consumer Data Right | + | [24 empty] | T1 | l | [6 empty] | T2 | l | CDR rules go-live Nov 2022 and Nov 2023
Retail | Market | Proposed - Review | Review of Regulatory Framework for Metering Services | + | [33 empty] | u | IT implementation likely but not yet clear, dependent on review outcomes
Wholesale | Reliability | In progress | ST PASA - Replacement project and methodology update | + | [23 empty] | n | Estimated timing, subject to rule change process
Wholesale | Market | In progress | Integrating Energy Storage Systems (IESS) (C) | [30 empty] | p | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | Committed | Fast Frequency Response Market Ancillary Services (B) | [33 empty] | l | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | In progress | Primary Frequency Response Incentive Arrangements (B) | + | [36 empty] | p | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Reliability | In progress | Operating Reserve Market (B) | [22 empty] | Indicative Execution Range: Procedures, IT | [16 empty] | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | In progress | Introduction of ramping services (B) | [22 empty] | Indicative Execution Range: Procedures, IT | [16 empty] | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | In progress | Synchronous Services Markets (B) | [22 empty] | Indicative Execution Range: Procedures, IT | [16 empty] | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | In progress | Capacity commitment mechanism for system security and reliability services (B) | [22 empty] | Indicative Execution Range: Procedures, IT | [16 empty] | Implementation planning co-ordinated through Reform Delivery Committee
ESB INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide |  | In progress | Resource Adequacy Mechanisms and Ageing Thermal Generation (A) | + | [5 empty] | Market Design | [6 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [22 empty] | Extended Execution Range
Immediate:
Initial:
Industry-wide | Market | In progress | Essential System Services, Scheduling and Ahead Mechanisms (B) | + | [5 empty] | Market Design | [6 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [22 empty] | Extended Execution Range
Immediate:
Initial:
Industry-wide | Market | In progress | Demand Side Participation (C) | + | [5 empty] | Market Design | [6 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [22 empty] | Extended Execution Range
Immediate:
Initial:
Industry-wide | Market | In progress | Transmission and Access (D) | + | [5 empty] | Market Design | [6 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [22 empty] | Extended Execution Range
Immediate:
Initial:
INITIATIVES WITH LIMITED IT SYSTEM IMPLEMENTATION IMPACTS (including ESB initiatives)
Wholesale | Security | Committed | Mandatory Primary Frequency Response |  |  |  | l | [18 empty] | Implementation timing shown is indicative and depends on individual generator circumstances, managed through the self-assessment process
Network |  | In progress | Technical Standards for Distributed Energy Resources | [15 empty] | l
Wholesale | Security | Committed | Efficient management of system strength on the power system (B) | + | [26 empty] | l |  | l
Wholesale |  | Committed | Generator Registrations and Connections | + | [17 empty] | l
Network |  | Committed | Access, Pricing and Incentive Arrangements for Distributed Energy Resources | + | [11 empty] | l | [9 empty] | l
Network |  | Committed | Implementing a General Power System Risk Review | [16 empty] | l
Industry-wide |  | In progress | Enhancing Operational Resilience to Indistinct Events | + | [22 empty] | p
Industry-wide | Market | In progress | Renewable Energy Zones - Implementation (Stage 2) (D)
Networks | Market | In progress | Governance of DER Technical Standards | + | [18 empty] | Indicative timing, subject to rule change process
GAS INITIATIVES
Gas |  | Committed | DWGM simpler wholesale price | [27 empty] | l
Implemented as a single AEMO project
Gas |  | Committed | DWGM improvement to AMDQ regime | + | [26 empty] | l
Gas |  | In progress | Measures to Improve Transparency in the Gas Market | [21 empty] | n | Subject to passage of legislation
Gas |  | Proposed - Review | Extending the Regulatory Framework to Hydrogen and Renewable Gases | +
INITIATIVES WITH LIMITED CERTAINTY
Retail | Consumer | In progress | Updating the Regulatory Frameworks for Embedded Networks | + | [34 empty] | u | Assumes rules development is re-initiated

## Version control
Australian Energy Market Operator
NEM Reform Implementation Roadmap
Version Control
REGULATORY AND NEM2025 IMPLEMENTATION ROADMAP
| Version | Date | Description
| V1 | 2022-08-04 | Integration of Version 7 of the Regulatory Implementation Roadmap and Version 2 of the NEM2025 Implementation Roadmap
NEM2025 IMPLEMENTATION ROADMAP
| Version | Date | Description
| Pre v. 0.01 | 2022-02-23 | First working draft for discussion and review by Design Authority on 16/2/2022. This version only considers known regulatory timeframes or assumptions, and implementation process assumptions, for initiatives within the NEM2025 reform program. It is not an integrated version that considers other initiatives within AEMO (e.g. Digital) that may impact the solution and/or the timeframes for delivery of the NEM2025 initiatives, with the exception of the ST PASA replacement initiative.
| Pre v. 0.02 | 2022-03-02 | Second draft incorporating Design Authority feedback, SME review and feedback. Updates made to each pathway, the implementation process and timeframes. Updates to DER Marketplace initiatives.
| v. 0.1 | 2022-03-11 | First working draft for discussion and review by the Reform Delivery Committee on 21/3/2022.
| v.0.2 | 2022-03-29 | Second draft incorporating RDC feedback for discussion with RDC at next workshop scheduled on Thursday 31/03/2022
| v1 | 2022-04-06 | Final draft for industry consultation incorporating RDC feedback.
| V.2 | 2022-08-04 | Draft of version 2 - based on Strategic Pathway but with modifications, including addition of Capacity Mechanism and Congestion Management Mechanism, removal of Operational Decision-Making Tools, Operational Data Store, Business Rules Engine and Forecasting Plafrom Uplift from NEM2025 Program delivery (will be delivered by Operational Technology Roadmap), inclusion of stage gate checkpoints, reflection of proposed integration design among other minor changes detailed in the Log of changes.
REGULATORY IMPLEMENTATION ROADMAP
| Version | Date | Description
| v1.0 | 2020-04-17 | First draft for review with industry and consumers at stakeholder forum of 21 April 2020.
| v2.0 | 2020-05-06 | Second iteration, following further AEMO internal review and participant feedback. Presented to stakeholder forum on 8 May 2020, and published as part of market bodies prioritisation advice on 17 May 2020.
| v3.0 - draft | 2020-08-04 | Next iteration, incorporating AEMC final determinations on WDR and 5MS/GS deferral, and other updates for presentation to stakeholder forum on 10 August 2020.
| v3.0 - final | 2020-08-31 | Finalised version 3, incorporating outcomes following stakeholder engagement in August 2020, including some additional minor updates.
| v4.0 - draft | 2021-02-24 | Draft version 4, incorporating implementation delays to 5MS retail solution, Metering Coordinator Planned Interruptions and MSATS standing data review go-live and other updates, for presentation at stakeholder forum on 24 Feb 2021.
| v4.0 - final | 2021-03-18 | Finalised version 4, incorporates implementation schedule for 2021 and schema changes for 2021-23. Delays to 5MS retail solution, Metering Coordinator Planned Interruptions and MSATS standing data review go-live dates,and other updates.
| v5.0 - draft | 2021-07-09 | Draft version 5, incorporating updates since version 4 including 5MS program and 5MS contingency scenario
| v5.0 - final | 2021-08-05 | Final version 5 incorporates final and draft rules on fast frequency response and integrating energy storage systems respectively. 5MS contingency scenario updated in align with AEMO's rule change request.
| v6.0 - draft | 2021-11-24 | Draft version 6 includes updates for MSATS standing data review, standalone power systems and consumer data right. Consolidation of the roadmap to remove initiatives that have been implemented.
| v6.0 - final | 2021-12-22 | Final version 6 incorporates final and draft rules for integrating energy storage systems and ST PASA update, as well as initiatives identified for inclusion by stakeholders e.g. Electricity B2B changes v3.7. The rule change process has been extended for a number of key initiatives.
| v7.0 - draft | 2022-05-11 | Draft version 7 reflects final rules for Standalone Power Systems and ST PASA update. Note ESB initiatives have been removed as these are being considered through the NEM2025 Implementation Roadmap. AEMO plans to integrate roadmaps for final version 7.

## Log of Changes
Australian Energy Market Operator
NEM Reform Implementation Roadmap
Log of Changes
REGULATORY AND NEM2025 IMPLEMENTATION ROADMAP
| Version | Date | Reform Initiative | Description
| V1 | TBC | Various | See latest updates to NEM2025 Implementation Roadmap and Regulatory Implementation Roadmap
NEM2025 IMPLEMENTATION ROADMAP
| Version | Date | Reform Initiative | Description
| v0.2 | 2022-03-29 | Scheduled Lite | Update both pathways to reflect releases for the Visibility Model and the Dispatchability Model
| v0.2 | 2022-03-29 | OSM | Developed a 'phased approach' option (row 69, hidden)
| v0.2 | 2022-03-29 | Ramping reserves | Developed a timeline for RDC discussion reflecting the date by which the rule change FD must be complete (by Dec 2022) for OR to be effective in 2025 (row 73, hidden)
| v0.2 | 2022-03-29 | SCADA Lite | Updated to reflect in-flight elements (release 1). Release 2 will enable the Schedule Lite Visibility model.
| V1 | 2022-04-06 | OSM | Updated OSM to reflect the phased approach as the preferred approach for both pathways.
| V1 | 2022-04-06 | Ramping reserves | Deleted hidden row. Only the pathway with current policy/regulatory process assumptions reflected on both pathways.
| V1 | 2022-04-14 | ST PASA Replacement | Updated the ST PASA timeline to reflect updated information published in AEMO's letter to the AEMC on proposed timing to implement the Updating Short-Term PASA rule change.
| V2 | 2022-08-04 | Various | Addition of Capacity Mechanism and Congestion Management Mechanism as place-markers. Removal of Operational Decision-Making Tools, Operational Data Store, Business Rules Engine and Forecasting Platform Uplift from NEM2025 Program delivery (will be delivered by AEMO's Operational Technology Roadmap project) - separated into a distinct category 'Dependent projects'. Inclusion of stage gate checkpoints. Included symbol for initiatives with an incremental delivery approach. Included symbol for initiatives where effective date for transition to target stage for NEM will be determined in collaboration with Participants. Extended implementation timeline for Portal Consolidation to align with expanded scope to include integration with IDAM. Extended implementation of Consolidated Master Data Repository Phase 2 to align with expanded scope for removing data dependencies and clean up. MT PASA - updated Procedures phase (brought forward 1 month) to be complete by April to align with Final Determination (RSIG and MT PASA process description to be updated by 30 April 23). Moved 'Remaining DER Reforms' group indicative date to align with ROR; subject to rule changes and market design, grouped 'final' release. Change in name for Primary Frequency Response incentive arrangements to Frequency Performance Payments. Due to the change in the publication date for the final determination, the deadline for Frequency Performance Payments (part of the PFR Incentive Arrangements rule) has been extended by 2 months.
REGULATORY IMPLEMENTATION ROADMAP
| Version | Date | Reform Initiative | Description
| Version 6 - Draft | 2021-11-24 | MSATS Standing Data Review | Note updated to reflect change of scope of v1 and v2 MSDR changes. v1 MCPI and schema for MSDR and v2 majority of MSDR.
| Version 6 - Draft | 2021-11-24 | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | Updated proposed go-live date to November 2022, consistent with AEMC's recommendation of 12 month implementation window following law/rules being made. Included AEMO's preferred implementation timeframe.
| Version 6 - Draft | 2021-11-24 | Energy Consumer Data Right | Updated CDR implementation for final CDR rules (published 15 Nov 2021). Staggered commencement in four tranches - 15 Nov 2022, 15 May 2023, 1 Nov 2023 and 1 May 2024. CDR included on implementation schedule.
| Version 6 - Draft | 2021-11-24 | Updating the Regulatory Frameworks for Embedded Networks | Moved to bottom of roadmap as initiative has limited certainty regarding regulatory process. Former COAG EC agreed to further consider AEMC's recommendations. Response being prepared for Energy Ministers consideration.
| Version 6 - Draft | 2021-11-24 | Review of Regulatory Framework for Metering Services | Updated review timeframes based on AEMC notification on 18 November 2021 that review would have a short pause and recommence in April 2022. Rule change process indicative only.
| Version 6 - Draft | 2021-11-24 | ST PASA - Replacement project and methodology update | Extended rules development phase to March 2022 as per AEMC consultation paper (26 Aug 2021).
| Version 6 - Draft | 2021-11-24 | MT PASA - Information Availability Enhancements | Included MT PASA rule change process, noting this is an immediate reform identified by the ESB. AEMO submitted rule change request on 15 Dec 2021.
| Version 6 - Draft | 2021-11-24 | Primary Frequency Response Incentive Arrangements | Draft determination (16 Sept 2021) proposed go-live date of March 2024. Included AEMO's preferred implementation timeframe.
| Version 6 - Draft | 2021-11-24 | Operating Reserve Market | Extended rule development phase until end of 2023 to reflect AEMC's notice to extend draft determination until 30 June 2023.
| Version 6 - Draft | 2021-11-24 | Introduction of ramping services | Extended rule development phase until end of 2023 to reflect AEMC's notice to extend draft determination until 30 June 2023.
| Version 6 - Draft | 2021-11-24 | Integrating Energy Storage Systems | Included AEMO's preferred implementation timeframe.
| Version 6 - Draft | 2021-11-24 | Interim Framework for Renewable Energy Zones - Implementation (Stage 2) | Updated to reflect final report published in June 2021.
| Version 6 - Draft | 2021-11-24 | Congestion Management Model | Included on the roadmap. Timeframes align with ESB's transmission access reform project initiation paper (published 18 November 2021).
| Version 6 - Draft | 2021-11-24 | Transmission Planning and Investment Review | Included on the roadmap. Timeframes align with Consultation Paper (published 19 August 2021).
| Version 6 - Draft | 2021-11-24 | Mandatory Primary Frequency Response | Extended engineering implementation given significant number of renewable generators are yet to implement changes for MPFR.
| Version 6 - Draft | 2021-11-24 | Efficient management of system strength on the power system | Final Determination made on 21 October 2021, with effective dates of 1 December 2022 and 15 March 2023. Status updated to committed.
| Version 6 - Draft | 2021-11-24 | Generator Registrations and Connections | Final Determination made on 21 October 2021, with implementation date of 21 April 2022. Status updated to committed.
| Version 6 - Draft | 2021-11-24 | Access, Pricing and Incentive Arrangements for Distributed Energy Resources | Final Determination made on 12 August 2021, with implementation dates of 19 August 2021 and 1 July 2022. Status updated to committed.
| Version 6 - Draft | 2021-11-24 | Enhancing Operational Resilience to Indistinct Events | Draft Determination made on 28 October 2021 with proposed go-live date of 18 August 2022. Final Determination and Rule expected in February 2022.
| Version 6 - Draft | 2021-11-24 | Governance of DER Technical Standards | Updated to reflect timeframes set out in AEMC consultation paper (2 Sept 2021). Status updated to "in progress" .
| Version 6 - Draft | 2021-11-24 | DWGM improvement to AMDQ regime | Updated go-live date to December 2022 (minor error correction).
| Version 6 - Draft | 2021-11-24 | Extending the Regulatory Framework to Hydrogen and Renewable Gases | Review commenced on 21 October 2021 and is expected to be completed by November 2022. This currently includes DWGM distribution connected facilitites rule change.
| Version 6 - Draft | 2021-11-24 | Five-minute settlement | Removed as initiative has been implemented
| Version 6 - Draft | 2021-11-24 | Customer switching | Removed as initiative has been implemented
| Version 6 - Draft | 2021-11-24 | Wholesale Demand Response | Removed as initiative has been implemented
| Version 6 - Draft | 2021-11-24 | Electricity B2B procedures | Removed as initiative has been implemented
| Version 6 - Draft | 2021-11-24 | NEM Settlement in Zero and Negative Demand Conditions | Removed as initiative has been implemented
| Version 6 - Draft | 2021-11-24 | Connection of Dedicated Connection Assets | Removed as initiative has been implemented
| Version 6 - Draft | 2021-11-24 | Renewable Energy Zones - Planning (Stage 1) | Removed as initiative has been implemented
| Version 6 - Draft | 2021-11-24 | Visibility and Security of Dispatch (Stage 1) - Interim | Removed as initiative has been implemented
| Version 6 - Final | 2021-12-22 | Electricity B2B procedures changes v3.7 | Included B2B Procedures v3.7 changes as some participant systems require changes on both roadmap and the implementation schedule.
| Version 6 - Final | 2021-12-22 | Energy Consumer Data Right (National Electricity Law and National Electricity Rules) | Updated to present CDR NEL and NER amendments as a separate line item.
| Version 6 - Final | 2021-12-22 | ST PASA - Replacement project and methodology update | Updated for draft determination published on 2 December 2021. Go-live date uncertain, earliest commencement is Q3 2023.
| Version 6 - Final | 2021-12-22 | Primary Frequency Response Incentive Arrangements | Extended rules development phase to 7 July 2022 to reflect AEMC's notice to extend final determination. Commencement date retained as March 2024 as well as AEMO's preferred go-live date of Sept 2024.
| Version 6 - Final | 2021-12-22 | Synchronous services market | Extended rules development phase until end of 2022 to reflect AEMC's notice to extend draft determination until 30 June 2022.
| Version 6 - Final | 2021-12-22 | Capacity commitment mechanism for system security and reliability services | Extended rules development phase until end of 2022 to reflect AEMC's notice to extend draft determination until 30 June 2022.
| Version 6 - Final | 2021-12-22 | Integrating Energy Storage Systems | Final Determination made on 2 December 2021, with an early implementation date of 31 March 2023 and a go-live date of 4 June 2024.
| Version 6 - Final | 2021-12-22 | Transmission Planning and Investment Review | Updated review timeframes based on AEMC notification on 2 December 2021 of a revised approach and information provided at 13 December directions forum.
| Version 6 - Final | 2021-12-22 | Material Change in Network Infrastructure Project Costs | Included this rule change request as a separate line item, noting that this has been progressed in parallel with the transmission planning and investment review.
| Version 6 - Final | 2021-12-22 | Measures to Improve Transparency in the Gas Market | Extended rules development phase to May 2022 given delay in legislative package being passed by SA Parliament.
| Version 6 - Final | 2021-12-22 | DWGM Distribution Connected Facilities | Included DWGM distribution connected facilities on the roadmap.
| Version 7 - Draft | 2022-05-11 | Gas B2B Changes | Removed from roadmap and schedule as initiative has been implemented (go-live 29 Nov 2021).
| Version 7 - Draft | 2022-05-11 | Inclusion of link to NEM2025 Implementation Roadmap
| Version 7 - Draft | 2022-05-11 | Electricity B2B Changes v3.8 | Included this initiative on the roadmap. AEMO consultation process commenced 4 Mar 2022 and is expected to be completed 5 Jul 2022. Indicative go-live date May 2023.
| Version 7 - Draft | 2022-05-11 | Electricity B2B Changes v3.8 (Implementation Schedule v7 Draft) | Included electricity B2B changes v3.8 on the implementation schedule. Reflects indicative go-live of May 2023.
| Version 7 - Draft | 2022-05-11 | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | SA Energy Minster made final rule specifying go-live dates are 1 Aug 2022 and 30 May 2023.
| Version 7 - Draft | 2022-05-11 | Regulatory Arrangements for Stand Alone Power Systems (Implementation Schedule v7 Draft) | Included this initiative on the implementation schedule. Reflects 30 May 2023 go-live and potential schema change.
| Version 7 - Draft | 2022-05-11 | Energy Consumer Data Rights Rules | Updated the reflect procedure development and solution consultation.
| Version 7 - Draft | 2022-05-11 | ST PASA - Replacement project and methodology update | AEMC final rule made on 5 May 2022 providing go-live date of 31 July 2025. Note AEMO to publish ST PASA procedures by 30 April 2025.
| Version 7 - Draft | 2022-05-11 | MT PASA - Information Availability Enhancements | Minor update to timeline, noting that AEMC initiated rule change process in Feb 2022.
| Version 7 - Draft | 2022-05-11 | ESB Initiatives | ESB initiatives removed from draft v7 as these are presented in the NEM2025 Implementation Roadmap.
| Version 7 - Draft | 2022-05-11 | Material change in network infrastructure project costs | Rule change process extended to reflect short delay in AEMC's draft determination (7 July 2022).
| Version 7 - Draft | 2022-05-11 | Mandatory Primary Frequency Response | Removed as generators understood to have completed self-assessment process by mid 2022.
| Version 7 - Draft | 2022-05-11 | Technical Standards for Distributed Energy Resources | Removed as initiative has been implemented (go-live 18 Dec 2021).
| Version 7 - Draft | 2022-05-11 | Implementing a General Power System Risk Review | Removed as initiative has been implemented (go-live 10 Jan 2022).
| Version 7 - Draft | 2022-05-11 | Enhancing Operational Resilience to Indistinct Events | AEMC Final Determination made on 3 March 2022, with a go-live date of 9 March 2023.
| Version 7 - Draft | 2022-05-11 | Governance of DER Technical Standards | AEMC did not make a final rule. Will be removed for final version 7.
| Version 7 - Draft | 2022-05-11 | Extending the Regulatory Framework to Hydrogen and Renewable Gases | AEMC Draft Report made on 31 March 2022. Final report expected Sep 2022 with Energy Ministers to consider in Nov 2022.
| Version 7 - Draft | 2022-05-11 | DWGM Distribution Connected Facilities | AEMC Draft Determination made on 31 March 2022, proposed go-live date of 1 Oct 2023.
| Version 7 - Draft | 2022-05-11 | DWGM Enhancements (Implementation Schedule v7 Draft) | Pre-Production Industry test scheduled for Oct 2022 to be confirmed. At this stage unlikely to be required.
| Version 7 - Draft | 2022-05-11 | Energy Consumer Data Right (Implementation Schedule v7 Draft) | Included potential schema change in May 2023 (if required).
| Version 7 - Draft | 2022-05-11 | Integrating Energy Storage Systems (Implementation Schedule v7 Draft) | Included this initiative on the implementation schedule. Reflects 31 March 2023 baseline release only. Final release will be captured on future roadmaps.
| Version 7 - Final | 2022-08-11 | Electricity B2B Changes v3.8 | Updated to reflect committed go-live date is 30 May 2023 in accordance with AEMO's final report published on 5 July 2022.
| Version 7 - Final | 2022-08-11 | Transmission Planning and Investment Review | Updated review timeframes to reflect stage 2 final report expected in Q4 2022 and stage 3 final report expected mid 2023.
| Version 7 - Final | 2022-08-11 | Material change in network infrastructure project costs | Updated to reflect AEMC's draft rule (made on 7 July 2022). Proposed go-live date is 12 months after final rule is made (approx October 2023).
| Version 7 - Final | 2022-08-11 | Governance of DER Technical Standards | Removed from roadmap as no final rule made
| Version 7 - Final | 2022-08-11 | Measures to Improve Transparency in the Gas Market | Updated roadmap to reflect NGL and NGR changes made in June 2022. Implementation is staggered with go-live dates through to 14 April 2023, system go-live is 15 Dec 2022.
| Version 7 - Final | 2022-08-11 | Measures to Improve Transparency in the Gas Market (Implementation schedule) | Updated the implementation schedule to include gas transparency measures.
| Version 7 - Final | 2022-08-11 | DWGM Enhancements (Implementation Schedule) | Updated the implementation schedule to remove second industry test in October 2022.
| Version 7 - Final | 2022-08-11 | Fast Frequency Response (Implementation Schedule) | Updated the implementation schedule to include fast frequency response.