## Version control
National Energy Market
Regulatory Implementation Roadmap
Version | Date | Description
v1.0 | 2020-04-17 | First draft for review with industry and consumers at stakeholder forum of 21 April 2020.
v2.0 | 2020-05-06 | Second iteration, following further AEMO internal review and participant feedback. Presented to stakeholder forum on 8 May 2020, and published as part of market bodies prioritisation advice on 17 May 2020.
v3.0 - draft | 2020-08-04 | Next iteration, incorporating AEMC final determinations on WDR and 5MS/GS deferral, and other updates for presentation to stakeholder forum on 10 August 2020.
v3.0 - final | 2020-08-31 | Finalised version 3, incorporating outcomes following stakeholder engagement in August 2020, including some additional minor updates.
v4.0 - draft | 2021-02-24 | Draft version 4, incorporating implementation delays to 5MS retail solution, Metering Coordinator Planned Interruptions and MSATS standing data review go-live and other updates, for presentation at stakeholder forum on 24 Feb 2021
v4.0 - final | 2021-03-18 | Finalised version 4, incorporates implementation schedule for 2021 and schema changes for 2021-23. Delays to 5MS retail solution, Metering Coordinator Planned Interruptions and MSATS standing data review go-live dates,and other updates.

## Roadmap v4 - final
National Energy Market and Gas Markets
Regulatory Implementation Roadmap |  |  |  |  | Key:
[6 empty] | Policy development/market design | [7 empty] | Rules development | [10 empty] | Procedure/guideline development
[6 empty] | Implementation - IT systems, processes | [7 empty] | Indicative IT implementation | [10 empty] | Engineering Implementation
[5 empty] | l | Committed Go-Live Date |  |  |  | p | Proposed Go-Live |  |  |  |  | n | Indicative Go-Live | [6 empty] | u | Estimated Go-Live | [6 empty] | + | Updated for version 4
Impacted Industry Sector | Primary Objective | Reform Status | Reform Initiative |  | 2020 | [6 empty] | 2021 | [10 empty] | 2022 | [11 empty] | 2023 | [7 empty] | 2024 |  |  |  | 2025 |  |  |  | 2026
[5 empty] | Q1 |  | Q2 |  | Q3 | Q4 |  | Q1 |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 | Q2 |  | Q3 |  | Q4 |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide | Market | Committed | Five Minute Settlement (5MS) and Global Settlement | + | [9 empty] | 5MS (IT platform) | l | 5MS (external) |  |  |  | l |  |  |  | GS (extern) |  |  | l | AEMC final determination - go-live 1 October 2021 (5MS), 1 May 2022 (GS)
Industry-wide | Consumer | Committed | Wholesale Demand Response Mechanism | [16 empty] | l | AEMC final determination - go live 24 October 2021
Retail | Consumer | Committed | Reducing Customer Switching Times | [16 empty] | l | Updated to align with 5MS go-live following stakeholder consultation in August 2020
Retail | Consumer | Committed | Metering Coordinator Planned Interruptions (MCPI) | + | [22 empty] | l | AEMO notice to reschedule to 1 May 2022, bundled with MSDR
Retail | Operational | Committed | MSATS Standing Data Review (MSDR) | + | [21 empty] | v1 | l |  |  | v2 (small) |  |  | l | v1 AEMO to reconsult on rescheduling to 1 May 2022, aligned with MCPI implementation
Retail | Consumer | Committed | Electricity B2B changes | [17 empty] | l | v3.5 (business enhancements, schema changes) and v3.6 (Life support procedural and WDR B2B guide changes only)
Gas |  | Committed | Gas B2B changes (life support) | [17 empty] | l | IN003/20 (business enhancements, schema uplift)
Retail | Market | In progress | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | + | [23 empty] | n | AEMC recommended implementation 12 months after law and rule changes made
Retail | Consumer | Proposed - Review | Energy Consumer Data Right | [27 empty] | n | Implementation dictated by Treasury timings, assumed to be Q3 2022
Retail | Consumer | In progress | Updating the Regulatory Frameworks for Embedded Networks | + | [28 empty] | u | Implementation subject to the scope of the change
Retail | Market | Proposed - Review | Review of Regulatory Framework for Metering Services | + | [28 empty] | u | (if required) | [6 empty] | u | IT implementation likely but not yet clear, dependent on review outcomes
Wholesale | Reliability | Proposed - Review | ST PASA - Replacement project and methodology update | + | [26 empty] | u | Estimated timing, subject to rule change process
Wholesale | Market | In progress | Integrating Energy Storage Systems (ESS) | + | [14 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [20 empty] | Rule change process co-ordinated with ESB initiatives. If Rule is made, IT implementation bundled with related ESB initiatives (where feasible)
Wholesale | Security | In progress | Fast Frequency Response Market Ancillary Services (B) | + | [13 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [26 empty] | Rule change process co-ordinated with ESB initiatives. If Rule is made, IT implementation bundled with related ESB initiatives (where feasible)
Wholesale | Security | In progress | Primary Frequency Response Incentive Arrangements (B) | + | [32 empty] | n | Indicative timing, subject to rule change process
Wholesale | Reliability | In progress | Operating Reserve Market (B) | + | [15 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [19 empty] | Rule change process co-ordinated with ESB initiatives. If Rule is made, IT implementation bundled with related ESB initiatives (where feasible)
Wholesale | Security | In progress | Introduction of ramping services (B) | + | [15 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [19 empty] | Rule change process co-ordinated with ESB initiatives. If Rule is made, IT implementation bundled with related ESB initiatives (where feasible)
Wholesale | Security | In progress | Synchronous Services Markets (B) | + | [13 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [20 empty] | Rule change process co-ordinated with ESB initiatives. If Rule is made, IT implementation bundled with related ESB initiatives (where feasible)
Wholesale | Security | In progress | Capacity commitment mechanism for system security and reliability services (B) | + | [13 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [20 empty] | Rule change process co-ordinated with ESB initiatives. If Rule is made, IT implementation bundled with related ESB initiatives (where feasible)
Wholesale | Security | In progress | Efficient management of system strength on the power system (B) | + | [13 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [20 empty] | Rule change process co-ordinated with ESB initiatives. If Rule is made, IT implementation bundled with related ESB initiatives (where feasible)
Wholesale |  | In progress | Generator Registrations and Connections | + | [18 empty] | Indicative Execution Range: Procedures, IT | [11 empty] | Indicative timing, subject to rule change process
Industry-wide | Security | Proposed - Review | Protecting Critical Infrastructure and Systems of National Security (Cth) | + | High Level Design | [6 empty] | Detailed Design |  |  |  |  | Indicative Execution Range: Legislation, Rules, Procedures, IT | [17 empty] | Extended Exec Range | [7 empty] | Indicative timing, subject to Cth processes
ESB INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide | Market | Proposed - Review | Resource Adequacy Mechanisms and Ageing Thermal Generation (A) | +
Industry-wide | Market | Proposed - Review | Essential System Services, Scheduling and Ahead Mechanisms (B) | + | High Level Design | [6 empty] | Market Design |  |  |  |  | Indicative Execution Range: Legislation, Rules, Procedures, IT | [20 empty] | Extended Execution Range
Industry-wide | Security | Proposed - Review | Demand Side Participation (C) | +
Industry-wide | Market | Proposed - Review | Transmission and Access (D) | +
INITIATIVES WITH LIMITED IT SYSTEM IMPLEMENTATION IMPACTS
Wholesale | Security | Committed | Mandatory Primary Frequency Response |  |  |  |  | l | [8 empty] | Implementation timing shown is indicative and depends on individual generator circumstances, managed through the self-assessment process
Network |  | In progress | Technical Standards for Distributed Energy Resources | + | [8 empty] | p
Industry-wide |  | Proposed - Pending | NEM Settlement in Zero and Negative Demand Conditions | +
Network |  | In progress | Network Planning and Access for Distributed Energy Resources | [19 empty] | Indicative Execution Range: Procedures, IT | [19 empty] | Indicative implementation only, subject to rule change process
Network |  | In progress | Allowing DNSPs to Charge for Exports to the Network | [19 empty] | Indicative Execution Range: Procedures, IT | [19 empty] | Indicative implementation only, subject to rule change process
Network |  | In progress | Access, Pricing and Incentive Arrangements for Distributed Energy Resources | [19 empty] | Indicative Execution Range: Procedures, IT | [19 empty] | Indicative implementation only, subject to rule change process
Network |  | In progress | Connection of Dedicated Connection Assets | + | [18 empty] | p
Network |  | In progress | Implementing a General Power System Risk Review | +
Industry-wide |  | In progress | Enhancing Operational Resilience to Indistinct Events | +
Wholesale |  | In progress | Prioritising arrangements for system security during Market Suspension | +
ESB INITIATIVES WITH LIMITED IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide | Market | In progress | Renewable Energy Zones - Planning (Stage 1) (D) | +
Industry-wide | Market | In progress | Renewable Energy Zones - Implementation (Stage 2) (D) | +
Wholesale | Security | In progress | Visibility and Security of Dispatch (Stage 1) - Interim | +
Wholesale | Security | Proposed - Review | Visibility and Security of Dispatch (Stage 2) - Interim | + | [18 empty] | Indicative, subject to determining the materiality of the issues
Networks | Market | Proposed - Pending | Governance of DER Technical Standards | + | [12 empty] | Indicative timing, subject to rule change process
GAS INITIATIVES
Gas |  | Committed | DWGM simpler wholesale price | [30 empty] | l
Implemented as a single AEMO project
Gas |  | Committed | DWGM improvement to AMDQ regime | [29 empty] | l
Gas |  | In progress | Measures to Improve Transparency in the Gas Market | + | [15 empty] | p | Subject to passage of legislation

## Schema changes v4 - final
Retail Go Live Roadmap |  |  |  | p | B2M/B2B Schema Release
Impacted Industry Sector | Primary Objective | Reform Status | Reform Initiative | 2021 | [6 empty] | 2022 | [8 empty] | 2023
|  |  |  | Q1 |  | Q2 |  | Q3 | Q4 |  | Q1 | Q2 |  |  | Q3 |  | Q4 |  |  | Q1 | Q2 | Q3 | Q4
Schema Changes
Industry-wide | Market | Committed | Five Minute Settlement (5MS) and Global Settlement |  |  |  | p
Retail | Consumer | Committed | Reducing Customer Switching Times |  |  |  | p
Retail |  | Committed | Electricity B2B changes | [6 empty] | p
Retail |  | Committed | Gas B2B changes | [6 empty] | p
Retail | Operational | In progress | MSATS Standing Data Review (includes MCPI) | [9 empty] | p |  |  |  |  | p
Retail | Market | Proposed - Review | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | [10 empty] | p | if required
`
Retail | Market | Proposed - Review | Energy Consumer Data Right | [12 empty] | p | if required
Retail | Market | In progress | Updating the Regulatory Frameworks for Embedded Networks | [14 empty] | p | if required
Retail | Market | Proposed - Review | Review of Competition in Metering | [14 empty] | p | if required |  |  |  |  | p | if required
Note: |  | AEMO notes schema releases in 2022 could be more aligned. Options for alignment will be explored once the scope and timing of initiatives have been firmed up.
No schema changes required for WDR

## Implem. schedule - final
National Energy Market and Gas Markets
Implementation Schedule |  | Key:
|  |  |  | Pre-Production Test |  |  |  | Market Trial
|  | l | Production Date |  |  | ¨ | Schema Change |  |  |  |  | n | Technical Specifications | [6 empty] | u | Checkpoint (Production Readiness) | [5 empty] | ¡ | Data Model release
Reform Initiative | 2021
| Jan |  |  |  | Feb |  |  | Mar |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul |  | Aug |  |  | Sep |  | Oct |  |  |  | Nov |  |  |  | Dec
Five Minute Settlement (5MS) and Global Settlement
Bidding and Dispatch | Pre-Production Bidding and Dispatch | [9 empty] | l | Bidding Platform 1/4
Settlements | [9 empty] | Pre-Production Settlements | [6 empty] | l | Settlement Platform 17/5
Retail | [8 empty] | u | Checkpoint |  |  |  | Pre-Production Metering |  |  |  |  | l | Metering Platform 31/5
[19 empty] | ¨ | Schema R39_P1
5MS Market | [24 empty] | 5MS Market Trial | [5 empty] | l | 5MS and UFE Markets 1/10
Reducing Customer Switching Times | [24 empty] | Pre-Production Industry Test | [5 empty] | l | Customer Switching 1/10
Wholesale Demand Response Mechanism | [21 empty] | l | WDR Registration Open 24/6 |  |  |  | ¡ | EMMS Data model release |  |  |  |  | l | WDR Rule Commencement 24/10
[19 empty] | n | Technical Specifications | [9 empty] | Pre-Production Industry Test |  |  |  |  | Pre-Production Industry Test
Electricity B2B changes | [30 empty] | Pre-Production Industry Test |  |  |  |  | l | B2B Go-Live 10/11
[36 empty] | ¨ | Schema Change R41
Gas B2B changes (life support) | [15 empty] | Pre-Production R40 Recertification | [17 empty] | Pre-Production Industry Test |  |  |  | l | Ghub 28/11 - 29/11
[38 empty] | ¨ | Schema Change R40
Notes:
5MS Staging available since December 2019
WDR - the pre-production industry test environment will be available on an ongoing, BAU basis post go-live. For the purposes of this initial schedule the ongoing availability of this environment has been reflected, however this will be removed for future schedules.
Electricity B2B changes - Electricity Validation Module (EVM) will be made available during the pre-production industry test period and by no later than 10 October 2021

## Log of changes
Log of Changes
Roadmap Version | Date | Reform | Change
Version 3 - draft | 2020-08-04 | Wholesale Demand Mechanism | Updated go-live date to 24 October 2021 (as per Final Determination)
Version 3 - draft | 2020-08-04 | Five-minute settlement and global settlement | updated go-lives dates for three-month deferral to 1 October 2021 and 1 May 2022 respectively (as per Final Determination)
Version 3 - draft | 2020-08-04 | Metering Coordinator Planned Interruptions | Updated for AEMO standing data and procedural changes no later than 30 March 2022 (previously November 2021)
Version 3 - draft | 2020-08-04 | MSATS | Updated release date to 30 March 2022 (previously November 2021)
Version 3 - draft | 2020-08-04 | Energy Consumer Data Right | Updated for indicative go-live date of end of Q3 2022 (previously November 2021)
Version 3 - draft | 2020-08-04 | Cyber security reform | Updated timetable indicating potential for go-live Q4 2022 recognising priority of these reforms. There is however uncertainty around this program of work as reflected by the extended implementation phase out to end of 2024 (if required)
Version 3 - draft | 2020-08-04 | Electricity B2B changes and gas B2B changes | Included on roadmap
Version 3 - draft | 2020-08-04 | ST PASA replacement and methodology update | Included on roadmap
Version 3 - draft | 2020-08-04 | System services rule changes | These have been initiated by the AEMC and will be considered along side the AEMC’s system strength framework review, the primary frequency response incentives rule change, and the ESB’s post-2025 program
Version 3 - draft | 2020-08-04 | ESB Initiatives with IT System impacts | The indicative execution range has been shortened slightly, recognising intentions to have some aspects of these reforms in place by mid 2023. The roadmap has maintained an extended implementation phase out to mid 2026 for the longer term initiatives.
Version 3 - draft | 2020-08-04 | DER technical standards | Updated timeframes with proposed go live date of December 2020
Version 3 - draft | 2020-08-04 | AER’s guidelines for actionable ISP | Minor delay to indicative go live date to 21 August 2020
Version 3 - draft | 2020-08-04 | Implementation of REZs | Minor delay of 2 months with draft rules expected end of July 2020
Version 3 - draft | 2020-08-04 | Network Planning and Access for Distributed Energy Resources | Included on roadmap. Rule change initiated in July 2020
Version 3 - draft | 2020-08-04 | Allowing DNSPs to Charge for Exports to the Network | Included on roadmap. Rule change initiated in July 2020
Version 3 - draft | 2020-08-04 | Access, Pricing and Incentive Arrangements for Distributed Energy Resources | Included on roadmap. Rule change initiated in July 2020
Version 3 - draft | 2020-08-04 | Making the ISP actionable | Removed - came into effect on 1 July 2020
Version 3 - draft | 2020-08-04 | Consumer Protection Review | Removed - completed as part of the retail competition review
Version 3 - draft | 2020-08-04 | Removal of Disincentives to Primary Frequency Response | Renamed Primary Frequency response Incentive arrangements
Version 3 - final | 2020-08-31 | Reducing Customer Switching Times | Changed the go-live date to 1 October 2021 (bundled with 5MS) following consultation process (short delay from July 2020 go-live date presented in version 3 draft on 10 August 2020). Updated status to committed.
Version 3 - final | 2020-08-31 | Wholesale Demand Response Mechanism | Updated status to committed. Final determination made 11 June 2020
Version 3 - final | 2020-08-31 | MSATS Standing Data Review | Updated status to committed.
Version 3 - final | 2020-08-31 | Reliability Measures - Interim | Updated timeframes in accordance with final rules that come into effect on 21 August 2020. Updated status to committed.
Version 3 - final | 2020-08-31 | Implementation of Renewable Energy Zones - Planning (Stage 1) | Updated name of reform to better reflect scope of the first stage of REZ implementation initiative. Updated status to In progress.
Version 3 - final | 2020-08-31 | Network Planning and Access for Distributed Energy Resources | Updated status to In progress as consultation has commenced
Version 3 - final | 2020-08-31 | Allowing DNSPs to Charge for Exports to the Network | Updated status to In progress as consultation has commenced
Version 3 - final | 2020-08-31 | Access, Pricing and Incentive Arrangements for Distributed Energy Resources | Updated status to In progress as consultation has commenced
Version 4 - Draft | 2021-02-24 | Schema Changes v3 - final | Deleted 'Schema changes v3 - final' tab as schema changes are incorporated into implementation view - draft. Note, this reflects schema changes in 2021 only. The only schema changes beyond 2021 for which there is certainty is for MCPI/MSDR.
Version 4 - Draft | 2021-02-24 | Implementation Sch v4 - draft | Included 'Implementation Sch v4 - draft' tab. Note, while this is the first time the Implementation Schedule has been included, it has been named v4 to align with same iteration of the roadmap.
Version 4 - Draft | 2021-02-24 | 5MS | IT platform implementation delayed from 9 March 2021 to 31 May 2021
Version 4 - Draft | 2021-02-24 | Metering Coordinator Planned Interruptions | Rescheduled to 1 May 2022
Version 4 - Draft | 2021-02-24 | MSATS standing data review | Rescheduled to 1 May 2022
Version 4 - Draft | 2021-02-24 | Standalone Power Systems | Delayed indicative go-live date by 3 months to Mar 2022 given NEL amendments have not passed SA Parliament and assuming one year implementation. Updated status to 'in progress'.
Version 4 - Draft | 2021-02-24 | MT PASA | Completed in Dec 2020 - removed
Version 4 - Draft | 2021-02-24 | Updating the Regulatory Frameworks for Embedded Networks | Extended rule development phase until March 2021
Version 4 - Draft | 2021-02-24 | Review of Competition in Metering | Updated rule development phase to Oct 2021 to align with consultation paper and extended rule development phase (if required)
Version 4 - Draft | 2021-02-24 | ST PASA replacement and methodology update | Updated rule development phase to March - December 2021 and updated estimated go-live date to Q3 2022
Version 4 - Draft | 2021-02-24 | Energy Storage Systems | Updated status to 'in progress' as consultation has commenced
Version 4 - Draft | 2021-02-24 | Synchronous services | 3 month delay to rule change process, Final Determination expected 1 July 2021
Version 4 - Draft | 2021-02-24 | Operating Reserve Market | 6 month delay to rule change process, Final Determination expected 16 Sept 2021
Version 4 - Draft | 2021-02-24 | Fast Frequency Response Market Ancillary Services | Rule change process shortened by 2 months, Final Determination expected 15 July 2021
Version 4 - Draft | 2021-02-24 | Efficient management of system strength on the power system | 4 month delay to rule change process, Final Determination expected 21 July 2021
Version 4 - Draft | 2021-02-24 | Capacity commitment mechanism for system security and reliability services | 3 month delay to rule change process, Final Determination expected 1 July 2021
Version 4 - Draft | 2021-02-24 | Introduction of ramping services | 6 month delay to rule change process, Final Determination expected 16 Sept 2021
Version 4 - Draft | 2021-02-24 | Primary Frequency Response Incentive Arrangements | 6 month delay to rule change process, Draft Determination expected 16 Sept 2021, Final Determination expected 17 Dec 2021, indicative implementation date of 1 July 2023
Version 4 - Draft | 2021-02-24 | Generator Registrations and Connections | Included on roadmap. Rule change process initiated in October 2020, assumes rules development phase longer than standard process, draft determination expected June 2021
Version 4 - Draft | 2021-02-24 | System Strength Framework Review | Removed as review completed in Oct 2020, recommendations being progressed through Efficient management of system strength on the power system rule change
Version 4 - Draft | 2021-02-24 | Economy wide Cyber Security Strategy and Systems of National Security (Cth) | Renamed initiative to Protecting Critical Infrastructure and Systems of National Significance, renamed technical design phase to detailed design phase
Version 4 - Draft | 2021-02-24 | Two-Sided Market - Intermediate | Consolidate with DER integration (intermediate) and rename Demand Side Participation
Version 4 - Draft | 2021-02-24 | Ahead Market - Intermediate | Consolidate with System Security Services and rename Essential System Services & Scheduling & Ahead Mechanisms
Version 4 - Draft | 2021-02-24 | System Security Services - Intermediate | Consolidate with Ahead Market (Intermediate) and rename Essential System Services & Scheduling & Ahead Mechanisms
Version 4 - Draft | 2021-02-24 | DER Integration - Intermediate | Consolidate with Two-sided Market (Intermediate) and rename Demand Side Participation
Version 4 - Draft | 2021-02-24 | Coordination of Generation and Transmission Investment - Intermediate | Rename Transmission and Access (reflects congestion information, transition pathways and locational marginal pricing and financial transmission rights initiatives only)
Version 4 - Draft | 2021-02-24 | Capacity Mechanisms - Long Term | Consolidate with Thermal Generation Strategy (Long Term) and rename Resource Adequacy Mechanisms and Ageing Thermal Generation Strategy
Version 4 - Draft | 2021-02-24 | Thermal Generation Strategy - Long Term | Consolidate with Capacity Mechanisms (Long Term) and rename Resource Adequacy Mechanisms and Ageing Thermal Generation Strategy
Version 4 - Draft | 2021-02-24 | NEM settlements under zero and negative demand conditions | Included on roadmap. Rule change submitted in Feb 2021
Version 4 - Draft | 2021-02-24 | Connection of Dedicated Connection Assets | Included on roadmap.
Version 4 - Draft | 2021-02-24 | Implementing a General Power System Risk Review | Included on roadmap. Rule change process initiated in Feb 2021
Version 4 - Draft | 2021-02-24 | Enhancing Operational Resilience to Indistinct Events | Included on roadmap. Rule change process initiated in Dec 2020
Version 4 - Draft | 2021-02-24 | Prioritising arrangements for system security during Market Suspension | Included on roadmap. Rule change process initiated in Dec 2020
Version 4 - Draft | 2021-02-24 | System restart services, standards and testing | Completed - removed
Version 4 - Draft | 2021-02-24 | Guidelines to make ISP actionable | Completed - removed
Version 4 - Draft | 2021-02-24 | Reliability Measures - Interim | Completed - removed
Version 4 - Draft | 2021-02-24 | Renewable Energy Zones - Planning (Stage 1) | Stage 1 near completed, rules development process extended by 2 months awaiting Energy Ministers approval
Version 4 - Draft | 2021-02-24 | Renewable Energy Zones - Implementation (Stage 2) | Included on roadmap. Stage 2 policy developed commenced in Q4 2020, recommendations to Ministers expected April 2021, with draft rules consultation to follow
Version 4 - Draft | 2021-02-24 | Visibility and Security of Dispatch (Stage 1) - Interim | 3 month delay to rule change process, Final Determination expected 11 March 2021, status updated to 'in progress'
Version 4 - Draft | 2021-02-24 | Visibility and Security of Dispatch (Stage 2) - Interim | Policy development phase extended by two months, status updated to 'proposed - review'
Version 4 - Draft | 2021-02-24 | Minimum Mandatory DER Technical Standards - Interim | Renamed Technical Standards for Distributed Energy Resources, updated the rules development phase to align with draft determination, re-categorised as non-ESB initative with limited IT system implementation impacts
Version 4 - Draft | 2021-02-24 | Governance for DER Technical Standards | Included. Rule Change Request submitted in Sept 2020
Version 4 - Draft | 2021-02-24 | Cost Allocation Methodology - Inter-Regional Transmission - Interim | Removed
Version 4 - Draft | 2021-02-24 | Measures to Improve Transparency in the Gas Market | Delayed with Final Rules package to go to SA Parliament Q1 2021, go-live date Oct 2021, GBB and GSOO procedures have to be updated (prior to go-live date)
Version 4 - Final | 2021-03-18 | Connection of Dedicated Connection Assets | Delay to Final Determination, expected 8 July 2021
Version 4 - Final | 2021-03-18 | Review of Competition in Metering | Renamed Review of Regulatory Framework for Metering Services
Version 4 - Final | 2021-03-18 | Schema changes v4 - final | Reintroduction of schema changes tab for period 2021-2023
Version 4 - Final | 2021-03-18 | Implementation Sch v4 - final | Inclusion of a note to clarify for the wholesale demand response initiative, the ongoing availability of pre-production industry test environment following go-live.
Version 4 - Final | 2021-03-18 | Implementation Sch v4 - final | Inclusion of a note on the timing of the availability of EVM for Electricity B2B changes
Version 4 - Final | 2021-03-18 | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | Extended rule development phase until June 2021, as Energy Senior Officials consulting on rule amendments. Energy Ministers expected to approve final rule change package in mid 2021.
Version 4 - Final | 2021-03-18 | Fast Frequency Response Market Ancillary Services | Extended indicative execution range to mid 2024

## Definitions
Definitions and Instructions for Regulatory Implementation Roadmap
Heading / Term | Definition and Instructions
Impacted Industry Sector | Indicates the primary section of the industry that is impacted by the regulatory change. If two sections of industry are impacted, choose the primary section. If more that two sections are impacted, choose 'Industry-wide'. Wholesale = Generation, Wholesale Market and/or Contracting impacted by the rule change Networks = Transmission and Distribution networks impacted by the rule change Retail = Retailers, other contestable service providers and/or customers are primarily impacted by the rule change Industry-wide = More that two sections of the industry are impacted by the rule change
Reform Status | Committed = Final determination made; and/or implementation in progress In progress = Rule change in process e.g. consultation and draft determination stages Proposed - Pending = Rule change has been proposed but not yet initiated Proposed - Review = Review underway but outcomes (including potential rule changes) not yet confirmed Note: A reference to rule change may also include a law change; or a reference to a review process where the outcome will be a law or rule change
Go-live Date Status | Committed = Go-live date decided in final rule determination Proposed = Go-live date proposed in draft rule determination Indicative = An indicative go-live date has been suggested by the proponent or foreshadowed during review process Estimated = AEMO estimated go-live date (where no proposed timeline currently exists)
Implementation Status | Policy development / market design = early stage of the reform process i.e. prior to a rule change process commencing Rules development = a rule change process is in progress i.e. from rule change request submitted through to final rule determination Procedure/Guideline development = Procedural changes are in progress or required to implement the rule change Implementation - IT systems, processes implementation and engineering implementation
Key IT regulatory projects | Signficant implementation impact = Medium or major IT/system capex project required to implement the rule change by AEMO and/or industry Strategic reform initiatives = Initiatives identified by COAG Energy Council and/or Energy Security Board
Include on Roadmap? | Yes - Material (i.e. High or Medium impact) IT, system or engineering implementation project Yes - Strategic Reform e.g. COAG EC priority No - Not Material or Strategic No - Complete
Definitions and Instructions for Detailed Implementation Schedule
Heading / Term | Definition and Instructions
Industry Test | Participants can get into the pre-prod environment and conduct unstructured tests as they see fit
Invitation industry Test | Where a subset of participants agree (on a volunteer basis) to participate in an Industry Test. AEMO does not develop formal scenarios, but participants conduct bilateral testing on an agreed basis
Market Trial | Where AEMO develops structured scenarios which are designed for widespread participation from our industry colleagues and structured to demonstrate/test particular scenarios. High effort required from all, generally reserved for new markets or big market changes (like 5MS)