## System Operations
Wholesale Demand Response Project: High-Level Impact Assessments for NEM System Operations Procedures
Prepared by Gareth Morrah and Basilisa Choi, August 2020
Document Title | Rule Consultation Req. | Priority | Business Owner | Consultation group | Consultation package | Link | Description of Document | Precedent Procedures / External Documents | Dependent Procedures / External Documents | Summary of Changes – Wholesale Demand Response | External Stakeholder Impacted | AEMO Business Units Impacted | Issues for Stakeholder Consultation | System Impact
Procedures for issue of directions and clause 4.8.9 instructions | 4.8.9(b) | Low | EMM (RTO review) |  | WP5 | Link | Provides information about how AEMO manages situations that require AEMO to issue a direction, or clause 4.8.9 instructions. |  |  | Minor change to section 2.1(b) - update the definition of scheduled plant to include ASL, and add WDRU to the clause 4.8.9 instruction example. | DRSP | EMM, RTO | Developed in accordance with the Rules consultation procedures. There is no NER clause allowing AEMO to make a minor change to this procedure without a Rules consultation. | none
Power System Security Guidelines | 3.8.10(c) | Low | Operations Planning |  | WP5 | Link | These Guidelines describe: (a) how AEMO seeks to operate the power system within the limits of the technical envelope; (b) how AEMO seeks to meet its power system security responsibilities generally; and (c) the information and actions required from registered participants to assist in maintaining or restoring power system security. |  |  | No significant change required. Rules consultation unlikely. | DRSP
Spot Market Operations Timetable | 3.4.3 | Low | EMM (Operations Planning review) |  | WP5 | Link | The purpose of the document is to specify the timetable for operating the spot market. It includes the timelines for participants to provide information to AMEO and AEMO to publish market information. The document is made in accordance with NER 3.4.3. |  |  | Minor change. Update the timetable to incorporate WDR rule changes. For example, include WDRU in section 2.2 PASA event description "Submit data for short term PASA, including: Scheduled generating units, scheduled load and scheduled network service availability; Network outages.". | DRSP | EMM, Operations Planning | Developed in accordance with the Rules consultation procedures. Clause 3.4.3(b1) allows AEMO to make minor changes without complying with the rules consultation procedure. Legal to confirm if the changes are minor. | Yes
Intervention pricing methodology | 3.9.3(e) | Low | EMM |  | WP5 | Link | Provides an overview of how intervention pricing works. |  |  | Relatively minor change. Update the methodology to describe how WDRU will be processed in the what-if pricing run. Specify that SCADA value will be used for WDRU if available in the feedback constraint RHS calculation. The treatment for WDRU will be consistent with the treatment for scheduled units. | DRSP |  | Developed in accordance with the Rules consultation procedures. Clause 3.9.3(g) allows AEMO to make minor changes without complying with the rules consultation procedure. Legal to confirm if the changes are minor. | Yes
Constraint Formulation Guidelines | 3.8.10(c) | Low | EMM (Congestion Modelling review) |  | WP5 | Link | This document sets out principles for translating the physical restrictions necessary for secure and sustainable power ststem operation into (i.e. formulating) constraint equations, grouped by type or purpose. It also covers the life cycle of constraint equations from business requirement identification through to notification of application in the operation of the NEM, and the process for applying and removing constraint equations from the dispatch process. |  |  | Assuming NEMDE will be changed to include WDRU as a new dispatchable entity, the document needs to be updated to describe how WDRU can be added to constraints. Minor change but it's information that depends on the system design. | DRSP |  | Developed in accordance with the Rules consultation procedures. There is no NER clause allowing AEMO to make a minior change to this procedure without a Rules consultation. | TBA
Market Suspension Compensation Methodology | 3.14.5A(h) | Low | EMM |  | WP5 | Link | The methodology is used for determining the classes of market suspension compensation claimants, benchmark values and AEMO’s administrative fees to be applicable following market suspension pricing schedule periods. |  |  | Update the methodology to include the compensation for WDR. | DRSP |  | Developed in accordance with the Rules consultation procedures. Clause 3.14.5A(i) allows AEMO to make minor changes without complying with the rules consultation procedure. Legal to confirm if the changes are minor. | none