## Retail
Wholesale Demand Response Project: High-Level Impact Assessments for NEM Retail Procedures
Prepared by G. Morrah and J. Krizmanic, July 2020
Document Title | Rule Consultation Req. | Priority | Business Owner | Consultation group | Consultation package | Link | Description of Document | Precedent Procedures / External Documents | Dependent Procedures / External Documents | Summary of Changes – Wholesale Demand Response | External Stakeholder Impacted | AEMO Business Units Impacted | Issues for Stakeholder Consultation | System Impact
MSATS Procedures: CATS Procedures | Rule 7.16 | Low | Metering team | ERCF | WP3 |  | Specifies the change request process to update MSATS. Procedure documents how Participants must select the most applicable Transaction Type Code or Change Request Code for their proposed transaction |  |  | Review and add new DRSP Participant Role as required. Potential for new AEMO only Change Reason Code and definitions. Possible changes would be to include the DRSP role in the NMI Discovery Process, AEMO only Change Request to be created or an existing one to be updated to allow the DRSP to be assigned to the NMI. Holding a role against the NMI provides the participant with access to standing data and the access to standing data area will need to include the DRSP. | DRSPs, Retailers, MCs, DNSPs | Metering, Market Change, Registrations, Settlements | Which tables NMI discovery will be represented. | TBC
MSATS Procedures: WIGS Procedures​ | Rule 7.16 | Low | Metering team | ERCF | WP3 |  | Specifies the change request process to update MSATS for WIGS. Procedure documents how Participants must select the most applicable Transaction Type Code or Change Request Code for their proposed transaction. |  |  | Updated to reflect version change only. WDR will not apply to Wholesale NMI's. | DRSPs, Retailers, MCs, DNSPs | Metering, Market Change, Registrations, Settlements |  | TBC
Metrology Procedure: Part A​ | Rule 7.16 | Low | Metering team | ERCF | WP3 |  | The metrology procedure applies to AEMO, registered participants, metering providers, and metering data providers, in relation to connection points in the NEM that may be classified as a first-tier load, second-tier load, market load, or intending load. The metrology procedure provides information on the application of metering installations to connection points, and sets out provisions for metering installations and metering data services. Part A includes: • Requirements for the provision, installation and maintenance of metering installations • The obligations of MCs, FRMPs, LNPS, MPs, MDPs and ENM • Responsibilities for metering data services • Minimum services specification procedures • Meter churn procedures • Network devices procedures • Emergency priority procedures | Service Level Procedures |  | Review impacts of new DRSP Participant Role and assess accordingly Don’t believe any major changes required as this is procedure is mainly about the metrology of the meters | DRSPs, Retailers, MCs, DNSPs, | Metering, Market Change, Registrations, Settlements |  | TBC
Metrology Procedure: Part B | Rule 7.16 | Low | Metering team | ERCF | WP3 |  | The metrology procedure applies to AEMO, registered participants, metering providers, and metering data providers, in relation to connection points in the NEM that may be classified as a first-tier load, second-tier load, market load, or intending load. Part B includes procedures for: • The validation and substitution of metering data • The estimation of metering data • The method by which accumulated metering data is converted by AEMO into trading interval metering data • Method by which calculated metering data is produced for unmetered market loads • Requirements regarding sample meters for controlled loads | Metrology Procedure: Part A | MDM Procedure | Review and add new DRSP Participant Role as required. Don’t believe any major changes required as this is procedure is mainly about the how meter data is validated, substituted and estimated. | DRSPs, Retailers, MCs, DNSPs | Metering, Market Change, Registrations, Settlements |  | TBC
Service Level Procedure (MDP)​ | Rule 7.16 | Low | Metering team | ERCF | WP3 |  | The SLP – MDP details the obligations, technical requirements, measurement processes and performance requirements to be met by MDPs in the provision of metering data services for all metering installations types and the maintenance of a metering data services database | Metrology Procedure Part B MSATS, MDM and NMI Procedures | MDFF Specification | Review and add new DRSP Participant Role as required. Changes to paragraphs to allow the DRSP to be a participant that is entitled to metering data. | DRSPs, Retailers, MCs, DNSPs | Metering, Market Change, Registrations, Settlements |  | TBC
Retail Markets Glossary & Framework doc | Rule 7.16 and 7.17 | Low | Metering team | ERCF | WP3 |  | Forms part of each of the Retail Electricity Market Procedures. Contains a dictionary of terms used with the Procedures and a description of each Procedure and supporting documentation, and how they fit together. | All Retail Electricity Market Procedures |  | Addition of DRSP Participant Role and any other associated terminology editioning or changes as a result of other Procedure/SLP updates. | DRSPs, Retailers, MCs, DNSPs | Metering, Market Change, Registrations, Settlements |  | TBC
Standing Data for MSATS | Rule 7.16 | Low | Metering team | ERCF | WP3 |  | Provides a detailed description of the data items populated in the MSATS NMI Standing Data tables and contains information on the type of data, a brief description of each data item and whether the input of the data is mandatory. | MSATS, MDM and NMI Procedures |  | Review impacts of new DRSP Participant Role and assess accordingly Don’t believe any major changes required as this is procedure is mainly about the standing data and who is responsible for it. The DRSP is not responsible for any Standing Data | DRSPs, Retailers, MCs, DNSPs | Metering, Market Change, Registrations, Settlements |  | TBC
NMI Procedures | Rule 7.16 | Low | Metering team | ERCF | WP3 |  | The NMI Procedure • Sets out the structure for NMIs to be used in the NEM • Describes the Process under which NMIs are allocated • Details Datastreams for each category of metering installation | Standing Data for MSATS |  | Review impacts of new DRSP Participant Role and assess accordingly Don’t believe any major changes required as this is procedure is mainly about the NMIs and their structure. The DRSP is not responsible for the creation of any NMIs | DRSPs, Retailers, MCs, DNSPs | Metering, Market Change, Registrations, Settlements |  | TBC
Note on O7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Gareth Morrah can you please advise if there is more information now available on System impacts please? e.g. could we assign a "High/Medium/Low" rating here?